AHRQ TASK ORDER REQUEST

Long Term Care Portfolio Expert Meeting, Sept. 13-14, 2006

Project Officer:   William Spector

Period of Performance –  June 15 – Nov 27, 2006

Statement of Work:

Provide support, as outlined below, for a two-day LTC Portfolio Expert Meeting

LTC Portfolio Expert Meeting.

The meeting will be held September 13-14, 2006 in the Watts Branch, Brighton Dam, Great Falls and Rock Creek rooms located in ARHQ’s Conference Center.  The PO will work with AHRQ’s conference center coordinators on room set-up. The meeting will be attended by AHRQ’s LTC Portfolio members and invited guest comprising of LTC experts, key stakeholders, current and recent grantees and contractors, and participating LTC providers. It is expected that 40 people will participate in this Conference. In the first part of the meeting AHRQ LTC projects will present summaries of interventions, lessons learned, and issues for discussion. In the second part of the meeting small workshops will address specific Portfolio questions. The third part of the meeting will be presentations of findings from the small workshops and a summary of lessons learned. The end product of this meeting will be a document that consolidates all lessons learned and presents a set of recommended strategies for helping the LTC Portfolio move its projects to a higher level of scale and to improve the quality of care for more long term care consumers.

Tentative meeting schedule:

Sept. 13  	7:30am	Breakfast

8:00am	Meeting begins

5:30 pm	Meeting ends

7:00 p.m.	Informal dinner

Sept 14	7:30am	Breakfast

8:00 am	Meeting begins

2:30 pm	Meeting ends

By July 14, The PO will provide the contractor with the names and addresses of the LTC Expert Panel who will be funded by AHRQ. The PO will also provide the contractor with contact information on participating AHRQ staff, and other attendees from Federal and private organizations that will attend the meeting. The PO will identify for the contractor who should receive briefing books. Letters of invitation will be FED-Exed to identified members by Aug 21 and e-mailed to all other invitees by Aug 25.  Invitation should state “You will not receive a briefing book if we do not receive a completed registration form.”

The contractor shall accomplish the following tasks:

Travel:

Arrange for travel for all attendees including making airline reservations in collaboration with attendees, purchasing tickets, etc.  Arrange payment of honoraria fees ($150 a day) to 25 non government participants. For the purpose of bidding, the contractor shall assume that there will be at least 20 non-local attendees who will need to travel to Rockville, MD that are non government participants.

Hotel/Accommodations:

Identify several potential hotels with lodging space to comfortably accommodate at least 20 persons in the Rockville, Maryland area. For the purpose of bidding, the contractor shall assume that there will be at least 7 people who will be staying for two nights and the remainder for one night only. Government per diem rates should apply.  If possible, the lodging space will be readily accessible to the AHRQ conference center and the airport.

Discuss the advantages/disadvantages of lodging spaces with the PO and, based on these discussions, reserve lodging space as directed.

Send hotel accommodation information to all meeting attendees who require them.

Ground Transportation:

The contractor will arrange appropriate round trip transportation from the hotel to the meeting site and return for two days, Sept. 13 and 14.

The contractor will arrange for transportation from the meeting site to the airports on Sept. 14.

The contractor will also arrange for transportation from the meeting site or dinner location to the hotel on Sept. 13.

Food:

Arrange for coffee and light beverages throughout the meeting.

Arrange for breakfast and lunch on both days for all meeting participants.  Federal and all non-funded participants will pay out-of-pocket for lunch; non-federal participants on official travel will have their per diem expenses reduced to cover the cost of the meal.

Identify appropriate location for an informal group dinner to be held Sept. 13.  Attendees will pay out-of-pocket if they wish to attend.  The contractor will send logistics information to all invitees and ask them to inform the contractor if they are going to attend.

Other:

Receive reimbursement claim forms and reimburse approved expenses to each Task Force member and invited guests.

In addition to the technical writer, provide one (1) staff member to provide on-site support during the meeting.

Prepare meeting materials such as name tags, name plates, supplies, agenda and background information as requested.  Depending on briefing book size, provide rings with cardstock covers or binders for briefing books.

Briefing Books:

AHRQ will forward electronic files to the contractor by close of business (COB) Sept. 28, and hard copy materials will be received by the contractor on Sept 29, so they can begin copying for the briefing books.  Most of the files will be in MS Word and some will be in Excel, PowerPoint or PDF format.  AHRQ will provide a mock-up briefing book to the contractor on Sept 27.  The mock-up briefing book will serve as the master copy for all materials, including any materials the contractor did not receive, or was unable to print successfully or completely.  The contractor will check all documents to ensure the copies documents match the Master Briefing Book and will correct any errors.

Oct 5, AHRQ will provide supplemental materials (some in electronic files and others in hard copy) for the contractor to copy and compile as handouts prior to the start of the meeting.

Unless otherwise specified, please use the following specifications for copying documents for the briefing book:

- Pages with text should be copied on 2-sided paper

- Pages with tables should be copied on 1-sided paper only

- PowerPoint slides should be 3 slides per page and copied on 2-sided paper

- PDF files should be copied on 2-sided paper

Timeline for Assembling Briefing Books for Sept 2006 Meeting

- Sept 22 – By COB, AHRQ and the contractor will start to receive any available electronic files (from AHRQ staff, and guest presenters) so that they can begin copying for briefing books.

- Sept 27 – AHRQ and the contractor will receive the rest of the electronic files and hard copy files in the morning (from AHRQ staff, and guest presenters) so that the contractor can complete copying.

- Sept 28 – AHRQ will assemble Master Briefing Book and deliver to the contractor by early afternoon.  The contractor copies any remaining materials to be included in the briefing books and will begin assembling briefing books for guest presenters.

- Sept 29 - The contractor will FED-EX briefing books to guest presenters Sept 30.

- Oct 5 - The contractor will deliver briefing books for AHRQ staff to William Spector (via courier) for distribution.

- Oct 5 – The contractor will FED-EX (two day delivery) briefing books to other participants.

- Oct 6-11 – The contractor will copy supplemental materials for distribution at the meeting.

Meeting Facilitator:

The Contractor will hire an experienced facilitator who at a minimum shall have the following responsibilities:

- Guide the group through each agenda item, asking questions as appropriate to elicit information and/or reach decisions.

- Direct/control verbal traffic flow and group dialogue to make sure each person has an opportunity to be heard and finish their train of thought.

The Government reserves the right to recommend a facilitator, and shall have final approval for the facilitator proposed by the Contractor.

Meeting Transcript:

The Contractor will hire an experienced writer to take minutes of the meetings, prepare a summary report and will also arrange to have the entire meeting tape recorded.  At the end of each meeting day, the contractor will provide AHRQ with an unedited disk with the rough notes of that day’s activities.  The Government reserves the right to recommend a writer, and shall have final approval for the writer proposed by the Contractor.

Prepare and deliver to the PO within 15 working days following the meeting a draft written report that accurately incorporates the discussions (including controversies and debates), recommendations, and decisions that were covered during the meeting. When the PO receives the draft transcript, the PO will send it to appropriate AHRQ staff for editing. AHRQ staff will have two weeks to make changes and return to PO who will then send all changes back to the contracted writer who will then finalize the report.  One week after the contractor receives the draft report with corrections, the final copy of the report will be sent to the PO along with the tapes and report diskette(s) in Microsoft Word.

To ensure information consistency, direct all questions related to this assignment to William Spector, AHRQ; telephone (301) 427-1446, e-mail: William.Spector@ahrq.hhs.gov.

Deliverables: Performance as stated above.