The Corps reviews the Sponsor’s request to determine if it fits within existing authorities or whether the request would require Congressional authorization.

If it fits within the Continuing Authorities Program (CAP), then the District requests funds from the Division to initiate a short reconnaissance effort (usually $10K to $20K) to determine Federal interest in proceeding with the study.  See descriptions of different authorities and typical timelines below.

TABLE A:  Continuing Authorities Program

| Section | Authority | Purpose | Cost share % (Fed/non-Fed) | Federal Project limit | National Program limit (per FY) (competitive funds) |
| --- | --- | --- | --- | --- | --- |
| 14 | Emergency Streambank Protection | Protection of public and nonprofit facilities | 65/35 | $1,000,000 | $15,000,000 |
| 103 | Beach Erosion Control | Protection of public shorelines | 65/35 | $3,000,000 | $30,000,000 |
| 107 | Small Navigation Projects | Small river and harbor improvements | 80/20* | $4,000,000 | $35,000,000 |
| 111 | Mitigation of Shore Damage attributable to navigation works | As a result to a Federal navigation project | Same as original project | $5,000,000 | N/A |
| 204 | Beneficial Uses of Dredged Material for Ecosystem Restoration | Restoration or creation of aquatic habitat associated with dredging for authorized projects | 75/25 | none | $25,000,000 |
| 205 | Flood Damage Protection | Small flood control projects | 65/35 | $7,000,000 | $40,000,000 |
| 206 | Aquatic Ecosystem Restoration | Restore degraded aquatic ecosystem in the public interest | 65/35 | $5,000,000 | $25,000,000 |
| 208 | Snagging & Clearing for Flood Control | Removal of snags & debris in navigable streams & tributaries in the interest of flood control | 65/35 | $500,000 | $7,500,000 |
| 1135 | Modifications for Improvement of the Environment | Restore a degraded ecosystem that resulted from Corps project operation | 75/25 | $5,000,000 | $25,000,000 |

* Non-Federal pay 10% of cost during construction and 10% over a 30-year period

TABLE B:  Phases, rules and typical timelines for Continuing Authorities (CAP) Projects

| Authority | (Note: Sponsor provides lands, easements, rights-of-way, relocations (LERRDs) under each authority. Credit for LERRDs counts towards sponsor cost share. The sponsor is also responsible for operation and maintenance costs. Construction seasons may be dependent on in-water work windows.) |
| --- | --- |
| Section 14 Emergency Streambank Protection | Planning & Design Analysis 1st $40K full Fed, anything over is cost shared 65/35 Fed up-front financed Sponsor costs recouped at time of construction. Up to 12 months | Construction Cost shared 65/35 (at least 5% in cash) Project Cooperation Agreement (PCA) must be executed by Govt. and Sponsor before construction begins. No in-kind credits 1 to 2 seasons |
| Section 208 Snagging and Clearing for Flood Control | Planning & Design Analysis 1st $40K full Fed, anything over is cost shared 65/35 Fed up-front financed, Sponsor costs recouped at time of construction. Up to 12 months | Construction Cost shared 65/35 (at least 5% in cash) Project Cooperation Agreement (PCA) must be executed by Govt. and Sponsor before construction begins. No in-kind credits 1 to 2 seasons |
| Section 205 Flood Damage Protection | Feasibility Study Initial $20K Federal funds to determine Fed interest. Additional $80K Federal funds for feasibility. Any amount > is cost shared 50/50 with Sponsor through Feasibility Study Cost Share Agreement (FCSA). Up to 25% can be in-kind. 12-16 months typical | Plans & specs Cost shared 65/35 Minimum sponsor cash contribution of 5%. Fed up-front financed Sponsor costs recouped at time of construction (No in-kind). 6 months typical | Construction Cost shared 65/35 Project Cooperation Agreement (PCA) must be executed by Got and Sponsor before construction begins. (No in-kind) 1 to 2 seasons |
| Section 1135 Modifications for Improvement of the Environment | Preliminary Restoration Plan (PRP) Full Federal cost not to exceed $10,000 2 to 6 months | Feasibility Study * Ecosystem Restoration Report Cost shared 75/25 Fed up-front financed, Sponsor costs recouped at time of construction 12 months | Plans & specs Cost shared 75/25 Fed up-front financed Sponsor costs recouped at time of construction. 6 months | Construction Cost shared 75/25 Govt. & sponsor execute PCA before construction begins. 80% of cost share can be in-kind. PCA must be executed to get credit for in-kind. (1 to 2 seasons) |
| Section 206 Aquatic Ecosystem Restoration | Preliminary Restoration Plan (PRP) Full Federal cost not to exceed $10,000 2 to 6 months | Feasibility Study * Ecosystem Restoration Report Cost shared 65/35 Fed up-front financed, Sponsor costs recouped at time of construction. 12 months | Plans & specs Cost shared 65/35 Fed up-front financed, Sponsor costs recouped at time of construction. 6 months | Construction Cost shared 65/35 Govt. & sponsor execute PCA before construction begins. 100% of cost share can be in-kind. PCA must be executed to get credit for in-kind. 1 to 2 seasons |

| Typical Continuing Authorities Program Timelines (Months) |
| --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 |
| Section 14 | Planning & Design Analysis (PDA) (12 months) | Construction (1 to 2 seasons) |  |
| Section 208 | Planning & Design Analysis (PDA) (12 months) | Construction (1 to 2 seasons) |  |
| Section 205 | Feasibility Study (If > $100k, Project Study Plan – PSP is required) (12 –16 months) | Plans & specs (6 months) | Construction (1 to 2 seasons) |  |
| Section 1135 | Preliminary Restoration Plan (PRP) (2-6 mos) | Feasibility Study/Ecosystem Restoration Report (ERR) * (12 months) | Plans & specs * (6 months) | Construction (1 to 2 seasons) |
| Section 206 | Preliminary Restoration Plan (PRP) (2-6 mos) | Feasibility Study/Ecosystem Restoration Report (ERR) * (12 months) | Plans & specs * (6 months) | Construction (1 to 2 seasons) |

*  For Section 1135 and 206, projects with an estimated Federal share of $300,000 or less do not have separate Feasibility and Plans and Specifications phases.  The formulation, analysis, justification and design tasks as well as NEPA coordination/ environmental compliance documentation take place in the one-step planning and design process (approximately 12 months).

If the problem does not fit within the Continuing Authorities Program (CAP), then the Corps has to have Congressional study resolution/authorization.  This would come from either a Senate Resolution (Environment and Public Works Committee) or House Resolution (Transportation and Infrastructure Committee) or language in a Water Resources Development Act (WRDA) usually passed by Congress and signed by the President every 2 years.  The Corps District would work with the sponsor and Corps Headquarters to submit a General Investigations New Start Project.

The Corps budget cycle for this initial funding process is:

January 			OMB provide budget guidance for the Budget Year (Current Fiscal Year + 2)

March 			HQ guidance to the District offices

April-May 			District offices develop program requirements

May-June 			HQ review and approval

July-August			Budget presented to Sec Army

September 			Budget submitted to OMB

#### November 			OMB passback

February	 		President’s budget to Congress

March–April			Congressional hearings

July–September		Appropriations bills

September–October	President signs appropriations bill

October–December		Funding allocations to District offices

TABLE C:  Typical timeline for a General Investigation New Start Project upon receipt of first Federal funds

| Reconnaissance Phase Full Federal cost of $100K Identifies Project Study Plan and cost share responsibilities for sponsor 9 to 12 months | Feasibility Phase Cost share with Sponsor 50/50 Avg. cost $700K to $1.5 million, up to 25% can be in-kind 1 to 3 years | Preliminary Engineering & Design (PED) Cost share with Sponsor, % varies – see below * 1 to 2 years | Construction Cost share with Sponsor, % varies – see below * time varies |
| --- | --- | --- | --- |

* Cost share ranges for PED and Construction:

Flood Damage Reduction	65% Federal, 35% non-Federal

Navigation			50% Federal, 50% Trust fund

Ecosystem Restoration	65% Federal, 35% non-Federal

Recreation			50% Federal, 50% non-Federal

TABLE D:  Floodplain Management Services Program (FPMS)

| Funding | Purpose of program | Examples |
| --- | --- | --- |
| 100% Federal funding at the request of the sponsor | Support comprehensive flood plain management planning to encourage and guide sponsors to prudent use of the Nation's flood plains for the benefit of the national economy and welfare. | Flood warning and flood emergency preparedness, flood proofing measures, helping a community identify the future of the flood plain and related problems (present or future), flood plain delineation, dam break analysis, flood damage reduction studies, regulatory floodway studies, studies to improve methods and procedures for mitigating flood damages, preparation of guides and pamphlets on topics such as flood proofing and flood plain regulations. |

# TABLE E:  Planning Assistance to States (and Tribes) Program (Section 22 of the 1974 Water Resources Development Act, as amended)

| Funding | Purpose of program | Examples |
| --- | --- | --- |
| 50/50 cost share with sponsor, limited to $500,000 per state or Tribe per year, based on availability of annual appropriations | Planning assistance to help States and Indian Tribes deal with their water resource problems. | Flood damage reduction, hydrologic analysis, hydraulic analysis, bank stabilization, flood hazard mitigation, environmental preservation and enhancement, water conservation, water quality, surface water, hydropower, erosion, sedimentation, cultural resources, ecosystem and watershed planning, streambed degradation, methodology to evaluate a wetland or other resource, and navigation studies. Scopes vary from environmental investigations for an individual reservoir to a comprehensive study to establish a State or Tribal water budget. |

Table F:  Disaster Preparedness and Response Program

| Flood Control and Coastal Emergencies | Authority | Purpose | Cost share % (Fed/non-Fed) | Federal Project Limit |
| --- | --- | --- | --- | --- |
| Code 100 | Disaster Preparedness | Federal preparation, local coordination and training | 100/0 | Annual budget |
| Code 200 | Flood Emergency Response | Emergency flood fight assistance to local Governments | 100/0 | Unlimited |
| Code 300 | Rehabilitation Assistance | Repair locally sponsored flood control projects | 100/0 (Federal Projects) 80/20 (nonfederal Projects) | Unlimited |
| Code 350/360 | Flood Control Project Inspection | Inspection and eligibility determination of nonfederal flood control projects | 100/0 | Annual budget |
| Code 400 | Water assistance | Provide water due to contaminated source or drought | 100/0 (water transport) 0/100 (construction of wells) | Unlimited |
| Code 500 | Advance Measures | Emergency preventative work prior to a predicted flood event | 100/0 | Unlimited |

# Text boxes

Solution fits within Disaster Preparedness and Response Program Refer to Table F for Guidance

Emergency

Study

Study

Local Sponsor Identifies a Problem

and Requests Corps Assistance

Solution fits within Floodplain Management Services Program Refer to Table D for Study Guidance

Solution fits within Planning Assistance to States/Tribes Program Refer to Table E for Study Guidance

Refer to Table C

for New Start Guidance

NORMAL Fed Budget

Cycle, District works with

Sponsor to Request a

New Start

(Earliest Fed Funding is 2 years out)

Larger

Projects

Smaller

Projects

District Evaluates

the Problem and

Determines

Appropriate

Program

Refer to Tables A & B for Continuing Authorities Program Guidance

District Requests funds

NOW from the Corps

Annual Appropriations

(Project can lead to Construction /

Implementation)