Statement of Work

NCI-Mouse Models of Human Cancers Consortium

Steering Committee Meeting

Boston, MA

June, 2007

Background

The NCI-Mouse Models of Human Cancers Consortium (NCI-MMHCC), Division of Cancer Biology, NCI plans a 2.5-day meeting and Symposium to be held June 11-13, 2007.  The meeting will take place at the Colonnade Hotel, 120 Huntington Avenue, Boston MA 02116, and the Symposium on June 12th at the Conference Center at Harvard Medical, 77 Avenue Louis Pasteur, Boston, MA 02115.  There will be approximately 20 invited speakers (domestic) for the Symposium, 110 meeting participants at the hotel, and about 300 Symposium attendees.  The invited speakers will be reimbursed for their hotel accommodations, airfare, per diem and ground transportation as per Federal Travel Regulations (FTRs).  The meeting participants will pay for their hotel and travel expenses (no reimbursements).

The hours for the meeting at the Colonnade Hotel are 4:30-7:30 PM on June 11th, 7:00-9:00 AM and 4:30-7:30 PM on June 12th, and 7:00 AM – 3:00 PM on June 13th.

STATEMENT OF WORK

Funding for this Task Order will be obligated in 3 segments:  July 2006, December 2006, and March 2007.

PRE-MEETING:

Hotel

- Pay the (est.) $5,000 hotel deposit for the meeting site and administer the contract with the hotel.

- The contract includes a room block that consists of 80 sleeping rooms for travelers for 2 nights (June 11th and 12th), 3 sleeping rooms for June 10th, and 5 sleeping rooms for June 13th.

- The main meeting room for 2.5 days is sufficiently large to accommodate 110-120 participants in classroom seating arranged chevron style, with a panel table for six, a lectern, and a projection screen facing the participants.

- Arrange and provide light refreshments during registration from 4:30-7:30 PM on June 11th for 110 attendees.

- Arrange and provide 2 continental breakfasts (June 12th and June 13th) and 1 working lunch (June 13th) for 110 attendees; collect lunch cost from all participants and speakers.

- Arrange and provide 1 morning (June 13th) and 1 afternoon break (June 12th) for 110 attendees.

- Coffee/tea/soft drinks/bottled water to be available throughout the 2.5 days.

Symposium site

- Coordinate with The Conference Center at Harvard Medical (Contact: Maureen Ridings, Director of Sales & Marketing, The Conference Center at Harvard Medical, 77 Avenue Louis Pasteur, Boston, MA 02115, Direct Line: (617) 432-8992, FAX: (617) 432-8991, maureen_ridings@hms.harvard.edu, (http://www.theconfcenter.hms.harvard.edu) for use of the Harvard Medical School Conference Center Auditorium for a Symposium from 9AM to 3:30 PM on June 12th.

- Pay the necessary deposit (est. $4,000) for use of the Conference Auditorium and a separate room for the luncheon.

- Ensure that the Conference Center receives appropriate Federal tax-free documentation.

- Arrange for round-trip bus transportation between the Colonnade Hotel and Harvard for 100 people.

- Arrange with a caterer to provide a morning snack break (light refreshments) for an estimated 300 attendees at the Symposium

- Arrange with a caterer to provide lunch for 100-120 (NCI-MMHCC members and invited speakers) from 12:00 PM to 1:00PM in a suitable room in the conference center.

Logistics

- Make direct telephone contact with speakers and their travel coordinators to ensure that they understand all travel arrangements and the extent of reimbursement.

- Solicit travel information from speakers, and develop detailed travel itineraries.

- Provide speakers with prepaid tickets, by courier or postal services, in advance of travel, if possible.

- Provide easy access to registration (e.g., online website, email or fax); registration should be available at least six weeks prior to the meeting.

- Coordinate all pre-meeting mailings (email and/or postal service) and provide logistical and informational support for the meeting participants.

- Prepare pre-meeting and meeting packages for participants, to include an agenda, participant list, and other materials as defined by NCI-MMHCC staff; send to participants (email and/or postal service) and provide during the meeting (see below)

- Mail meeting notices and updates to participants (both email and/or postal service)

- Prepare name tags, name tents and meeting folders including agenda, participant list, and other duplicated materials as defined by NCI-MMHCC staff, no later than June 07, 2007.

- Prepare any necessary paperwork related to the meeting as stipulated by NCI-MMHCC staff.

MEETING:

- Provide microphones for every three-four participants seated at the at the classroom style tables.

- Provide a lavaliere microphone for lectern presentations.

- Provide all necessary audio-visual (AV) equipment for the meeting room (LCD projector, laptop computer, laser pointers, overhead projector).

- Provide an Internet connection in the meeting room for 2 days.

- Provide with task order contract funds one (1) AV technician.  This must be a knowledgeable audio-visual (AV) technician to be available during the 2.5 day meeting to set up and run PowerPoint presentations using an LCD projector and laptop (PC- and MAC-compatible) computer system.  The Government’s preference is:  Mr. Carey Anthony Brown from C.A. Brown Enterprises, Inc.  His telephone number is (954) 501-4086; email is redsscam@aol.com.  This is provided for information purposes only and is not considered restrictive for proposal purposes.

- Determine and pay costs for appropriate support services during the 2.5 day meeting, including 1 person at the registration desk to assist participants and register attendees.

POST-MEETING:

- Reimburse speakers for ground transportation and other travel-related expenses as permitted under Government FTRs and Government policies.

- Provide post-meeting services to include contacting all speakers to ensure that all travel and per diem costs are submitted and reimbursed; these services should extend for 3 months after the conclusion of the meeting.

- Provide meeting materials packets or information (via e-mail and/or mail) to those meeting participants who request them, but were unable to attend the meeting.

- Provide NCI-MMHCC staff with a Word document list of all participants at the meeting and their contact information based on final registration.

- Return all unused meeting materials.

Deliverables

- Logistical information that is prepared and mailed/emailed to the participants.

- Participant name tags, name tents, meeting folders, etc., to be prepared no less than 4 days prior to the meeting.

- Participant packages, final participant list, agenda, etc., to be prepared no less than 4 days prior to the meeting.

- Professional Service Contract (PSC) equivalents to be provided to the invited speakers at the end of the meeting.