SECTION F

DELIVERIES OR PERFORMANCE

F.1	LISTING OF CLAUSES INCORPORATED BY REFERENCE

NOTICE:  The following contract clauses pertinent to this section are hereby incorporated by reference:

I.  FEDERAL ACQUISITION REGULATION (48 CFR CHAPTER 1)

CLAUSE

NUMBER	DATE	TITLE

52.242-15	AUG 1989	STOP-WORK ORDER

52.247-34	NOV 1991	F.O.B. DESTINATION

II.  NASA FEDERAL ACQUISITION REGULATION SUPPLEMENT (48 CFR CHAPTER 18)

CLAUSE

NUMBER	DATE	TITLE

No NASA By reference clauses in Section D.

(End of Clause)

F.2	COMPLETION OF WORK (JSC 52.212-95) (SEP 1988)

All work required under this contract, including submission of all reports, shall be completed on or before December 31, 2003.  In the event an option mission is ordered pursuant to Article F.6 with a launch date in late calendar year 2003, for which the post-flight destow process would not be completed by December 31, 2003, Article F.2, Completion of Work shall be modified to reflect the option mission's Return + 1 month (R + 1) date.

(End of Clause)

F.3	OPTION TO EXTEND COMPLETION OF WORK

The Government may require the Contractor to continue to perform services under this contract.  The Contracting Officer may exercise each option by issuance of a unilateral contract modification no later than 15 months prior to the launch opportunity date.  These options will be exercised prior to the end of the completion of work set forth in Article F.3.  Should an option be exercised, the resultant contract will include all terms and conditions of the basic contract as it exists immediately prior to the exercise of the option, except for the following changes:

OPTION 1

Add a fourth mission to the contract.  STS-107 will be replaced by a logistics double module at 95% NASA allocation and the research double module at 82% NASA allocation will be moved to another flight.

F-1

- Article B.2 entitled, "Firm-Fixed-Price" shall be modified to reflect the addition of $15,800,000 to the contract value.  Article B.2 shall be deleted in its entirety and replaced with the following:

“B.2	FIRM-FIXED PRICE (NASA 1852.216-78) (DEC 1988)

The total firm-fixed price of this contract is $58,660,000.

(End of clause)”

- Article B.3 entitled, “Milestone Schedule,” item 3 shall be modified to reflect the logistics double module and item 4 shall be added to the contract:

Delivery		Firm-Fixed

Item Number	Services				  Date		    Price

3	Lease of Logistics Double Module and

related integration services

on STS-107 (95% NASA Allocation)

3a	Baseline MRAD, submit CIP Addendum		L-12 mo.	$  2,962,500

3b	Delivery of Finite Element structural

models, thermal models, and Mission

Training Plan					L-9 mo.		$  2,962,500

3c	Submittal of Phase III Safety Data

Packages (Flight & Ground)			L-5 mo.		$  3,950,000

3d	All Interface Control Agreements

(core ICD’s, SIA’s, PTA’s)

baselined					L-3 mo	.	$  1,975,000

3e	Analytical Engineering Analyses

(Structural, Thermal, EMI/EMC and

Acoustics) delivered to SSP			L-2 mo.		$     987,500

3f	Delivery of flight-ready SPACEHAB

double module in accordance with the

SOW to KSC					L-1 mo.		$     987,500

3g	Post-flight destow process complete		R+1 mo.	$  1,975,000

SUBTOTAL STS-107							$15,800,000

4	Lease of Research Double Module

and related integration services

on STS-TBD (82 % NASA Allocation)

4a	Baseline MRAD, submit CIP Addendum		L-12 mo.	$  3,712,500

4b	Delivery of Finite Element structural

models, thermal models, and Mission

Training Plan					L-9 mo.		$ 3,712,500

4c	Submittal of Phase III Safety Data

Packages (Flight & Ground) 			L-5 mo.		$  4,950,000

4d	All Interface Control Agreements

(core ICD’s, SIA’s, PTA’s) baselined		L-3 mo.		$  2,475,000

4e	Analytical Engineering Analyses

(Structural, Thermal, EMI/EMC and

Acoustics) delivered to SSP			L-2 mo.		$  1,237,500

4f	Delivery of flight-ready SPACEHAB

module in accordance with the

SOW to KSC					L-1 mo.		$  1,237,500

F-2

Delivery 	Firm-Fixed

Item Number	Services				  Date		    Price

4g	Post-flight destow process complete		R+1 mo.	$  2,475,000

SUBTOTAL STS-TBD							$19,800,000

TOTAL PAYMENTS								$58,660,000

- Section C, Statement of Work will be modified as follows

Section 2.3  SUMMARY OF SPACEHAB MODULE RESOURCES, table in paragraph five is deleted in its entirety and replaced with the following:

| Mission | Config. | Mass Capability | NASA Allocation %, (lbm), [kg] | Contractor Allocation %, (lbm), [kg] |
| --- | --- | --- | --- | --- |
| STS-95 | SM | 4,800 lbm | 55, (2,640), [1197] | 45, (2,160), [980] |
| STS-96 | LDM | 9,000 lbm | 100, (9,000), [4082] | 0 |
| STS-107 | LDM | 9,000 lbm | 95, (8,550), [3878] | 5, (450), [204] |
| STS-TBD | RDM | 9,000 lbm | 82, (7,380), [3347] | 18, (1,620), [735] |

- F.2 entitled "Completion of Work" shall be modified to extend the ending date of the contract to R + 45 days of the selected mission.

OPTION 2

Add a fourth mission to the contract.  STS-107 will be replaced by a logistics double module at 100% NASA allocation and the research double module at 82% NASA allocation will be moved to another flight.

- Article B.2 entitled, "Firm-Fixed-Price" shall be modified to reflect the addition of $17,860,000 to the contract value.  Article B.2 shall be deleted in its entirety and replaced with the following:

“B.2	FIRM-FIXED PRICE (NASA 1852.216-78) (DEC 1988)

The total firm-fixed price of this contract is $60,720,000.

(End of clause)”

- Article B.3 entitled, “Milestone Schedule,” shall be modified by the addition of the following milestones:

Delivery		Firm-Fixed

Item Number	Services				  Date		   Price

3	Lease of Logistics Double Module and

related integration services

on STS-107 (100% NASA Allocation)

3a	Baseline MRAD, submit CIP Addendum		L-12 mo.	$  3,348,750

3b	Delivery of Finite Element structural

models, thermal models, and Mission

Training Plan					L-9 mo.      	$  3,348,750

3c	Submittal of Phase III Safety Data

Packages (Flight & Ground)			L-5 mo.	$	$  4,465,000

3d	All Interface Control Agreements

(core ICD’s, SIA’s, PTA’s)

F-3

Delivery		Firm-Fixed

Item Number	Services				  Date		    Price

baselined					L-3 mo.		$  2,232,500

3e	Analytical Engineering Analyses

(Structural, Thermal, EMI/EMC and

Acoustics) delivered to SSP			L-2 mo.		$  1,116,250

3f	Delivery of flight-ready SPACEHAB

double module in accordance with the

SOW to KSC					L-1 mo.		$  1,116,250

3g	Post-flight destow process complete		R+1 mo.	$  2,232,500

SUBTOTAL STS-TBD							$17,860,000

4	Lease of Research Double Module

and related integration services

on STS-TBD (82 % NASA Allocation)

4a	Baseline MRAD, submit CIP Addendum		L-12 mo.	$  3,712,500

4b	Delivery of Finite Element structural

models, thermal models, and Mission

Training Plan					L-9 mo.		$  3,712,500

4c	Submittal of Phase III Safety Data

Packages (Flight & Ground) 			L-5 mo.		$  4,950,000

4d	All Interface Control Agreements

(core ICD’s, SIA’s, PTA’s) baselined		L-3 mo.		$  2,475,000

4e	Analytical Engineering Analyses

(Structural, Thermal, EMI/EMC and

Acoustics) delivered to SSP			L-2 mo.		$  1,237,500

4f	Delivery of flight-ready SPACEHAB

module in accordance with the

SOW to KSC					L-1 mo.		$  1,237,500	4g	Post-flight destow process complete		R+1 mo.	$  2,475,000

SUBTOTAL STS-TBD							$19,800,000

TOTAL PAYMENTS								$60,720,000

- Section C, Statement of Work will be modified as follows:

Section 2.3  SUMMARY OF SPACEHAB MODULE RESOURCES, table in paragraph five is deleted in its entirety and replaced with the following:

| Mission | Config. | Mass Capability | NASA Allocation %, (lbm), [kg] | Contractor Allocation %, (lbm), [kg] |
| --- | --- | --- | --- | --- |
| STS-95 | RSM | 4,800 lbm | 55, (2,640), [1197] | 45, (2,160), [980] |
| STS-96 | LDM | 9,000 lbm | 100, (9,000), [4082] | 0 |
| STS-107 | LDM | 9,000 lbm | 100, (9,000), [4082] | 0 |
| STS-TBD | RDM | 9,000 lbm | 82, (7,380), [3347] | 18, (1,620), [735] |

- F.2 entitled "Completion of Work" shall be modified to extend the ending date of the contract to R + 45 days of the selected mission.

OPTION 3

Add a fourth mission for a logistics double module at 95% NASA allocation to the contract.

F-4

- Article B.2 entitled, "Firm-Fixed-Price" shall be modified to reflect the addition of $15,800,000 to the contract value.  Article B.2 shall be deleted in its entirety and replaced with the following:

“B.2	FIRM-FIXED PRICE (NASA 1852.216-78) (DEC 1988)

The total firm-fixed price of this contract is $58,660,000.

(End of clause)”

- Article B.3 entitled, “Milestone Schedule” shall be modified to add the following milestones established as follows:

Delivery		Firm-Fixed

Item Number	Services				  Date		     Price

4	Lease of Logistics Double Module and

related integration services

on STS-TBD (95% NASA Allocation)

4a	Baseline MRAD, submit CIP Addendum		L-12 mo.	$  2,962,500

4b	Delivery of Finite Element structural

models, thermal models, and Mission

Training Plan					L-9 mo.      	$  2,962,500

4c	Submittal of Phase III Safety Data

Packages (Flight & Ground)			L-5 mo.		$  3,950,000

4d	All Interface Control Agreements

(core ICD’s, SIA’s, PTA’s)

baselined					L-3 mo.		$  1,975,000

4e	Analytical Engineering Analyses

(Structural, Thermal, EMI/EMC and

Acoustics) delivered to SSP			L-2 mo.		$     987,500

4f	Delivery of flight-ready SPACEHAB

double module in accordance with the

SOW to KSC					L-1 mo.		$     987,500

4g	Post-flight destow process complete		R+1 mo.	$  1,975,000

TOTAL PAYMENTS-STS-TBD							$15,800,000

TOTAL PAYMENTS								$58,660,000

- Section C, Statement of Work will be modified as follows:

Section 2.3  SUMMARY OF SPACEHAB MODULE RESOURCES, table in paragraph five.  Revise the table in the paragraph as follows:

| Mission | Config. | Mass Capability | NASA Allocation %, (lbm), [kg] | Contractor Allocation %, (lbm), [kg] |
| --- | --- | --- | --- | --- |
| STS-95 | RSM | 4,800 lbm | 55, (2,640), [1197] | 45, (2,160), [980] |
| STS-96 | LDM | 9,000 lbm | 100, (9,000), [4082] | 0 |
| STS-107 | LDM | 9,000 lbm | 82, (7,380), [3347] | 18, (1,620) [735] |
| STS-TBD | RDM | 9,000 lbm | 95, (8,550), [3878] | 5, (450), [204] |

- F.2 entitled "Completion of Work" shall be modified to extend the ending date of the contract to R + 45 days of the selected mission.

OPTION 4

F-5

Add a fourth mission for a logistics double module at 100% NASA allocation to the contract.

- Article B.2 entitled, "Firm-Fixed-Price" shall be modified to reflect the addition of $17,860,000 to the contract value.  Article B.2 shall be deleted in its entirety and replaced with the following:

“B.2	FIRM-FIXED PRICE (NASA 1852.216-78) (DEC 1988)

The total firm-fixed price of this contract is $60,720,000.

(End of clause)”

- Article B.3 entitled, “Milestone Schedule” shall be modified to add the following milestones established as follows:

Delivery	Firm-Fixed

Item Number	Services				  Date		    Price

4	Lease of Logistics Double Module and

related integration services

on STS-TBD (100% NASA Allocation)

4a	Baseline MRAD, submit CIP Addendum		L-12 mo.	$  3,348,750

4b	Delivery of Finite Element structural

models, thermal models, and Mission

Training Plan					L-9 mo.		$  3,348,750

4c	Submittal of Phase III Safety Data

Packages (Flight & Ground)			L-5 mo.	$	$  4,465,000

4d	All Interface Control Agreements

(core ICD’s, SIA’s, PTA’s)

baselined					L-3 mo.		$  2,232,500

4e	Analytical Engineering Analyses

(Structural, Thermal, EMI/EMC and

Acoustics) delivered to SSP			L-2 mo.		$  1,116,250

4f	Delivery of flight-ready SPACEHAB

double module in accordance with the

SOW to KSC					L-1 mo.		$  1,116,250

4g	Post-flight destow process complete		R+1 mo.	$  2,232,500

SUBTOTAL STS-TBD							$17,860,000

TOTAL PAYMENTS								$60,720,000

- Section C, Statement of Work will be modified as follows:

Section 2.3  SUMMARY OF SPACEHAB MODULE RESOURCES, table in paragraph five is deleted in its entirety and replaced with the following:

| Mission | Config. | Mass Capability | NASA Allocation %, (lbm), [kg] | Contractor Allocation %, (lbm), [kg] |
| --- | --- | --- | --- | --- |
| STS-95 | RSM | 4,800 lbm | 55, (2,640), [1197] | 45, (2,160), [980] |
| STS-96 | LDM | 9,000 lbm | 100, (9,000), [4082] | 0 |
| STS-107 | RDM | 9,000 lbm | 82, (7,380), [3347] | 18, (1,620), [735] |
| STS-TBD | LDM | 9,000 lbm | 100, (9,000), [4082] | 0 |

F-6

- F.2 entitled "Completion of Work" shall be modified to extend the ending date of the contract to R + 45 days of the selected mission.

(End of Clause)

F.4  AGREEMENT CONCERNING DELAYS IN SHUTTLE LAUNCH DATES AS SET FORTH IN THE CONTRACT AND RELATED EQUITABLE ADJUSTMENTS

Since flight schedule changes are likely to occur, launch schedule variations shall not be subject to the Changes clause so long as:

- The launch schedule variation does not increase the period of performance of this contract.

- The launch  date  for  any  Option  Mission  ordered pursuant to Article F.5 is not delayed more

than 60 days from NASA’s official Shuttle launch date in effect at the time the Contractor is directed to begin integration.

- For consecutive missions, the change allows the Contractor at least 45 working days to process hardware in the SPPF between consecutive Logistics missions, 60 working days between consecutive Research missions, or 60 working days between consecutive Research and Logistics missions, or vice versa.

(End of Provision)

F.5  OPTION MISSIONS

The Government may require the Contractor to continue to perform services under this contract.  The Contracting Officer may exercise each option by issuance of a unilateral contract modification no later than 15 months prior to the launch opportunity date by identifying the module type, NASA Allocation, and price from the matrix below.  The price shall be selected from the year noted in the matrix which corresponds with the scheduled launch date at the time the option is exercised.

(Numbers below are in millions)

| MODULE TYPE | NASA ALLOCATION | 1999 | 2000 | 2001 | 2002 | 2003 |
| --- | --- | --- | --- | --- | --- | --- |
| Logistics Double | 100% | $17.600 | $17.800 | $18.000 | $18.200 | $18.500 |
| Logistics Double | 95% | $16.700 | $16.900 | $17.100 | $17.300 | $17.500 |
| Logistics Double | 90% | $15.800 | $16.000 | $16.200 | $16.400 | $16.600 |
| Research Double | 90% | $30.400 | $30.800 | $31.200 | $31.600 | $32.300 |
| Research Double | 85% | $27.400 | $27.700 | $28.100 | $28.400 | $29.100 |
| ICC | 100% | $ 3.450 | $ 3.450 | $ 3.450 | $ 3.450 | $ 3.450 |
| SHOSS | 100% | $ .395 | $ .395 | $ .395 | $ .395 | $ .395 |

Should an option be exercised, the resultant contract will include all terms and conditions of the basic contract as it exists immediately prior to the exercise of the option, except for the following changes:

- Article B.2, Firm-Fixed-Price, shall be modified to reflect the addition of the value noted in the matrix above to the total contract value for the option chosen.  The year/price shall correspond to the scheduled launch dates at the time the option is exercised.  For Logistics Double Modules only, the prices in the matrix shall be adjusted to accommodate transportation costs.  For module capacity commercially sold by the Contractor in excess of the 100% NASA allocation/9,000 pound module capability requirement, the matrix price shall be reduced by $3,000 for every pound

F-7

sold.  For capacity commercially sold by the Contractor at the 95% and 90% allocations, transportation costs shall be negotiated as a credit to be applied against the matrix price, after the option has been exercised.  The credit amount shall be determined based upon the individual circumstances of the instant mission, but in no case shall the transportation cost credit exceed $3,000 per pound of gross payload weight.

- Article B.3, Milestone Schedule, item TBD, shall be added to the contract for an Option Mission of any allocation, any year, with appropriate substitution for the item number, the module type or ICC/SHOSS, the STS number, the allocation, the resultant milestone price, total price, and new total contract value, as follows:

| Item Number | Services | Delivery date | Firm-Fixed Price |
| --- | --- | --- | --- |
| TBD | Lease of TBD Double Module and Related integration services on STS-TBD (TBD Allocation) |  |  |
| TBD a | Baseline MRAD, submit CIP addendum | L-12 mo. | 18.75% of matrix price |
| TBD b | Delivery of Finite elment structural models, thermal models, and Mission Training Plan | L-9mo. | 18.75% of matrix price |
| TBD c | Submittal of Phase II Safety Data Packages (Flight and Ground) | L-5 mo. | 25.00% of matrix price |
| TBD d | All Interface Control Agreements (core ICDs, SIAs, PTAs) baselined | L-3 mo. | 12.50% of matrix price |
| TBD e | Analytical Engineering Analyses (Structural, Thermal, EMI/EMC and Acoustics) delivered to SSP | L-2 mo. | 6.25% of matrix price |
| TBD f | Delivery of flight-ready SPACEHAB module in accordance with the SOW to KSC | L-1 mo. | 6.25% of matrix price |
| TBD g | Post-flight destow process complete | R+1 mo. | 12.5% of matrix price |
| SUBTOTAL STS-TBD |  |  | 100% OF MATRIX OPTION PRICE |
| TOTAL PAYMENTS |  |  | CURRENT CONTRACT VALUE + 100% OF MATRIX OPTION PRICE |

MATRIX CONTINUED ON THE NEXT PAGE

F-8

| or |  |  |  |
| --- | --- | --- | --- |
| Item Number | Services | Delivery date | Firm-Fixed Price |
| TBD | Lease of Integrated Cargo Carrier (ICC) and/or SHOSS enclosure {SPECIFY EITHER OR BOTH} with Level IV I&O services on STS-TBD (100% NASA Allocation) {SPECIFY ICC OR SHOSS AND TAILOR SERVICES AS APPROPRIATE ON TBD a THROUGH TBD h} |  |  |
| TBD a | Assess ICC/SHOSS Payload Complement; Deliver preliminary ICC/SHOSS MRAD; Submit ICC CIP Addendum and initial ICD-A inputs | L-12 mo. | 18.75% of matrix price |
| TBD b | Submit ICC/SHOSS Mission Training Plan; Deliver ICC/SHOSS Structural & Thermal Models to SSP | L-9 mo. | 18.75% of matrix price |
| TBD c | Ready for ICC/SHOSS Payload Training; Deliver ICC/SHOSS mockups to NBL for EVA Training; Submit initial stowage and labeling data to ISS; Baseline ICC ICD-A | L-6 mo. | 18.75% of matrix price |
| TBD d | Submit ICC/SHOSS Phase III Flight & Ground Safety Data Packages to SSP | L-5 mo. | 6.25% of matrix price |
| TBD e | Baseline ICC/SHOSS MRAD; All ICC/SHOSS Interface Control Agreements (core ICD’s, SIA’s and PTA’s) baselined | L-3 mo. | 12.5% of matrix price |
| TBD f | ICC/SHOSS Analytical Engineering Analyses delivered to SSP | L-2 mo. | 6.25% of matrix price |
| TBD g | Delivery of flight ready ICC/SHOSS to KSC for ground processing for flight | L-1 mo. | 6.25% of matrix price |
| TBD h | Post-Flight Destow process complete | R+1 mo. | 12.5% of matrix price |
| SUBTOTAL STS-TBD |  |  | 100% OF MATRIX OPTION PRICE |
| TOTAL PAYMENTS |  |  | CURRENT CONTRACT VALUE + 100% OF MATRIX OPTION PRICE |

In accordance with Paragraph A, the matrix price shall be adjusted to accommodate transportation costs on Logistics missions.  Transportation cost consideration is already included in the matrix price for Research missions.

- Section C, Statement of Work, Section 2.3, SUMMARY OF SPACEHAB MODULE RESOURCES, table in paragraph five shall be revised to add the following for each option exercised, with appropriate substitutions for the TBD’s based upon the configuration and allocation ordered:

F-9

| Mission | Config. | Mass Capability | NASA Allocation %, (lbm), [kg] | Contractor Allocation %, (lbm), [kg] |
| --- | --- | --- | --- | --- |
| STS-TBD | TBD | 9000 lbm | TBD, (TBD), [TBD] | TBD, (TBD), [TBD] |

- Section C, Statement of Work, Section 2.4, SUMMARY OF SPACEHAB INTEGRATED CARGO CARRIER RESOURCES, table in paragraph five shall be revised to add the following for each option exercised, with appropriate substitutions for the TBD’s based upon the configuration and allocation ordered:

| Mission | Config. | Mass Capacity | NASA Allocation %, (lbm), [kg] | Contractor Allocation %, (lbm), [kg] |
| --- | --- | --- | --- | --- |
| STS-TBD | ICC | 6000lbm | TBD, (TBD), [TBD] | TBD, (TBD), [TBD] |

(End of Clause)

F.6  SHIPMENT BY GOVERNMENT BILLS OF LADING (NASA 1852.247-73) (MAR 1997)

- The Contractor shall ship U.S. Government payloads returned from flight, if the transportation cost per shipment exceeds $100, by Government bills of lading (GBLs).  At least 15 days before shipment, the Contractor shall request in writing GBLs from:

NASA - Lyndon B. Johnson Space Center

Attn:  Todd Pryor, JSC Transportation Office, Mail Code JB7

2101 NASA Road One

Houston, TX  77058

If time is limited, requests may be by telephone:  281-483-6512.  Requests for GBLs shall include the following information:

(1) Item identification/ description.

(2) Origin and destination.

(3) Individual and total weights.

(4) Dimensions and total cubic footage.

(5) Total number of pieces.

(6) Total dollar value.

(7) Other pertinent data.

- The Contractor shall prepay transportation charges of $100 or less per shipment.  The Government shall reimburse the contractor for these charges if they are added to the invoice as a separate line item supported by the paid freight receipts.  If paid receipts in support of the invoice are not obtainable, a statement as described below must be completed, signed by an authorized company representative, and attached to the invoice.

F-10

"I certify that the shipments identified below have been made, transportation charges have been paid by (company name), and paid freight or comparable receipts are not obtainable.

Contract or Order Number:

Destination:                "

(End of clause)

[END OF SECTION]

F-11