## Blank 533Q
2. REPORT FOR QUARTER BEGINNING
NATIONAL AERONAUTICS AND SPACE ADMINISTRATION | [6 empty] | Form Approved
QUARTERLY CONTRACTOR FINANCIAL MANAGEMENT REPORT | [6 empty] | O.M.B. No. 2700-0003
TO: |  |  |  | FROM: | [10 empty] | 3. CONTRACT VALUE
[15 empty] | a. COST |  | b. FEE
| a. TYPE |  |  | b. CONTRACT NO. AND LATEST DEFINITIZED MODIFICATION NO. | [10 empty] | 4. FUND LIMITATION
1. DESCRIPTION
OF
CONTRACT | c. SCOPE OF WORK |  |  | d. AUTHORIZED CONTRACTOR REPRESENTATIVE (Signature) | [9 empty] | DATE | 5. BILLING
[15 empty] | a. INVOICE AMTS. BILLED |  | b. TOTAL PYTS. REC'D
|  | 7. COST INCURRED/HOURS WORKED |  |  |  | 8. ESTIMATED COST/HOURS TO COMPLETE | [8 empty] | 9. ESTIMATED FINAL |  |  | 11. UN-
|  | CUM ACT |  |  | MONTH | MONTH | MONTH | QUARTER | QUARTER | QUARTER | BALANCE | NEXT |  |  | COST/HOURS |  | 10. EST | FILLED
| 6. REPORTING CATEGORY | THROUGH | CURRENT | CUM | [6 empty] | OF FY | FY | BAL | TOTAL TO | CONTRACTOR | CONTRACT | COMPL | ORDERS
|  | PRIOR | MONTH | EST | [8 empty] | OF | COMPLETE | ESTIMATE | VALUE | DATE | OUT-
|  | MONTH | EST | TO DATE | [8 empty] | CONTR |  |  |  |  | STANDING
|  | a. | b. | c. | a. | b. | c. | d. | e. | f. | g. | h. | i. | j. | a. | b.
Baseline Plan Identification (Col 7b & 7d): Revision No. ____________________________________ , Dated _______________
NASA FORM 533Q AUG96 PREVIOUS EDITIONS ARE OBSOLETE. | [17 empty] | RCS 10PUB00417

## Sample 533Q with data
2. REPORT FOR QUARTER BEGINNING
NATIONAL AERONAUTICS AND SPACE ADMINISTRATION | [7 empty] | Form Approved
QUARTERLY CONTRACTOR FINANCIAL MANAGEMENT REPORT | [7 empty] | O.M.B. No. 2700-0003 | [7 empty] | 1991-07-01
TO: | Jet Propulsion Laboratory |  |  |  | FROM: | Acme Aerospace Co | [9 empty] | 3. CONTRACT VALUE
| 4800 Oak Grove Drive |  |  |  |  | 2020 Electronics Way | [9 empty] | a. COST |  | b. FEE
| Pasadena, CA 91109 c/o I. Buythings, Contract Negotiator |  |  |  |  | South Bay, CA 90200 | [9 empty] | 10500 |  | 840
| a. TYPE |  |  |  | b. CONTRACT NO. AND LATEST DEFINITIZED MODIFICATION NO. | [10 empty] | 4. FUND LIMITATION
1. DESCRIPTION |  | Cost Plus Fixed Fee |  |  |  | 959000 Mod 5 | [9 empty] | 6300
OF | [15 empty] | (Mod 5)
CONTRACT | c. SCOPE OF WORK |  |  |  | d. AUTHORIZED CONTRACTOR REPRESENTATIVE (Signature) | [9 empty] | DATE | 5. BILLING
[16 empty] | a. INVOICE AMTS. BILLED |  | b. TOTAL PYTS. REC'D
|  | Spacecraft Subsystem | [12 empty] | 1991-06-13 | 4953 |  | 4289
[16 empty] | Inv. No. 82335 |  | (5/20/91)
|  |  | 7. COST INCURRED/HOURS WORKED |  |  |  | 8. ESTIMATED COST/HOURS TO COMPLETE | [8 empty] | 9. ESTIMATED FINAL |  |  | 11. UN-
|  |  | CUM ACT |  |  | MONTH | MONTH | MONTH | QUARTER | QUARTER | QUARTER | BALANCE | NEXT |  |  | COST/HOURS |  | 10. EST | FILLED
| 6. REPORTING CATEGORY |  | THROUGH | CURRENT | CUM | [6 empty] | OF FY | FY | BAL | TOTAL TO | CONTRACTOR | CONTRACT | COMPL | ORDERS
|  |  | PRIOR | MONTH | EST | JUL | AUG | SEP | O-N-D | J-F-M | A-M-J | J-A-S |  | OF | COMPLETE | ESTIMATE | VALUE | DATE | OUT-
|  |  | MONTH | EST | TO DATE | 1991 | 1991 | 1991 | 1991 | 1992 | 1992 | 1992 | 1993 | CONTR |  |  |  |  | STANDING
|  |  | a. | b. | c. | a. | b. | c. | d. | e. | f. | g. | h. | i. | j. | a. | b.
ENGINEERING DIRECT LABOR HOURS |  |  | 61.6 | 7.5 | 69.1 | 7.2 | 8 | 7.8 | 21 | 12.3 |  |  |  |  | 56.3 | 125.4 | 125.4
MANUFACTURING DIRECT LABOR HOURS |  |  | 1.9 | 0.8 | 2.7 | 1.2 | 3.2 | 3.8 | 9.1 | [5 empty] | 17.3 | 20 | 20
TOTAL DIRECT LABOR HOURS |  |  | 63.5 | 8.3 | 71.8 | 8.4 | 11.2 | 11.6 | 30.1 | 12.3 |  |  |  |  | 73.6 | 145.4 | 145.4
ENGINEERING DIRECT LABOR DOLLARS |  |  | 1417 | 173 | 1590 | 166 | 184 | 179 | 483 | 283 |  |  |  |  | 1295 | 2885 | 2748
MANUFACTURING DIRECT LABOR DOLLARS |  |  | 25 | 11 | 36 | 16 | 42 | 50 | 120 | [5 empty] | 228 | 264 | 276
TOTAL DIRECT LABOR DOLLARS |  |  | 1442 | 184 | 1626 | 182 | 226 | 229 | 603 | 283 |  |  |  |  | 1523 | 3149 | 3024
ENGINEERING OVERHEAD |  |  | 1715 | 209 | 1924 | 201 | 223 | 217 | 584 | 342 |  |  |  |  | 1567 | 3491 | 3300
MANUFACTURING OVERHEAD |  |  | 89 | 39 | 128 | 57 | 150 | 178 | 427 | [5 empty] | 812 | 940 | 976
TOTAL OVERHEAD |  |  | 1804 | 248 | 2052 | 258 | 373 | 395 | 1011 | 342 |  |  |  |  | 2379 | 4431 | 4276
MATERIALS |  |  | 759 | 123 | 882 | 90 | 131 | 120 | [6 empty] | 341 | 1223 | 843 |  | 322
SUBCONTRACTS |  |  | a.: 400; b.: 100; c.: 500; a.: 100; j.: 100; a.: 600; b.: 600 |  | 100
OTHER DIRECT COSTS |  |  | 225 | 20 | 245 | 20 | 30 | 30 | 90 | 63 |  |  |  |  | 233 | 478 | 387
TOTAL PRODUCTION COSTS |  |  | 4630 | 675 | 5305 | 650 | 760 | 774 | 1704 | 688 |  |  |  |  | 4576 | 9881 | 9130
G&A |  |  | 694 | 101 | 795 | 97 | 114 | 116 | 255 | 103 |  |  |  |  | 685 | 1480 | 1370
TOTAL COST |  |  | 5324 | 776 | 6100 | 747 | 874 | 890 | 1959 | 791 |  |  |  |  | 5261 | 11361 | 10500 | 2/28/92
FEE |  |  | 426 | 53 | 479 | 51 | 60 | 61 | 135 | 54 |  |  |  |  | 361 | 840 | 840
TOTAL COST PLUS FEE |  |  | 5750 | 829 | 6579 | 798 | 934 | 951 | 2094 | 845 |  |  |  |  | 5622 | 12201 | 11340
Baseline Plan Identification (Col 7b & 7d): Revision No. ___1__________________________________ , Dated ____2/15/91_____________
NASA FORM 533Q AUG96 PREVIOUS EDITIONS ARE OBSOLETE. |  |  | b.: Dollars in Thousands
Hours in Thousands

## Instructions
INSTRUCTIONS FOR COMPLETING NASA FORM 533Q
General - Paragraph references below are to the current edition of NPR 9501.2, which includes additional instructions for completing NASA Form 533 reports. Copies of the NPR are available from the NASA Contracting Officer or the Superintendent of Documents, Government Printing Office, Washington, DC 20401. All data entered shall be as of the report date, unless stated otherwise below. | 6. Reporting Category - Enter the captions of the reporting categories specified in the contract (par. 2.4).
Forms - Forms will be obtained from the NASA Contracting Officer. When directed or approved by the NASA Contracting Officer, electronic data interchange may be used for transmitting the data. | 7. Cost Incurred/Hours Worked: a. Enter the cumulative actual cost incurred/hours worked through the prior month. Where the cumulative data reported in this column is only for the current "schedule" or option, the report summary shall show the total cumulative cost for each of all previous "schedules" or options and the total cumulative contract cost from inception to date. b. Enter an estimate for the month in which the report is due (see "Submission" above). c. Enter the sum of columns 7a and b.
Security Classification - If the information in the report is classified, appropriate security classification shall be given the report (par. 1.7).
Submission - The NASA Form 533Q is due on a quarterly frequency not later than the 15th day of the month preceding the quarter being projected based upon the Government's fiscal year in columns 8a, b and c (see par. 3.4). For initial reports and other related items of significance, see par. 3.2 and the contract. The addressees and number of copies to be submitted will be specified by the contract or administrative instruction. | 8. Estimated Cost/Hours to Complete (columns 8a through i) - Enter the appropriate month, quarter and fiscal year designations in the column headings. Enter the current estimates for performing authorized work included in the most recently executed contract modification plus additional authorized work (directions to proceed) for which execution of modifications is pending. These estimates will be for planning purposes only and will not be binding on either the contractor or NASA. The sum of columns 8a through i will be entered in column 8j. If the totals reported in column 8i, "Balance of Contract," exceed more than one fiscal year, each fiscal year shall be identified and reported separately.
Amounts - Report whole dollars and hours (may be rounded to the nearest hundred or thousand dollars or tenths of thousands of hours, as directed by the NASA Contracting Officer, e.g., $32,600 as $33 or 462 hours as .5).
Form Headings - Complete as follows: 1. To - Enter the full name and address of the NASA Center and NASA Contracting Officer or other designated recipient. 2. From - Enter the full name and address of the contractor and, if applicable, the division performing the contract. | 9. Estimated Final Cost/Hours: a. Contractor Estimate - Enter the total estimated cost/hours for completion of the contracted effort for each reporting category. This should equal the sum of columns 7c and 8j. b. Contract Value - Enter the distribution of the Contract Value to the reporting categories. The total of this column shall agree with item 3, above. Significant differences between columns 9a and 9b shall be explained in the "Contractor Narrative Remarks."
Preparation:
1. Description of Contract: a. Type - Cost-Plus-Fixed-Fee, Cost-Plus-Incentive-Fee, etc. b. Contract No. and Latest Definitized Modification No. - Enter complete letter or contract symbol, number, and number of latest definitized modification. c. Scope of Work - Enter a brief description of the contract effort. Identify the service, project, system or subsystem and, where hardware is concerned, the quantity being procured or pro posed for the contract. d. Authorized Contractor Representative (Signature) and Date - The authorized contractor representative shall sign and date the summary page to reflect approval. | 10. Estimated Completion Date - As directed by the NASA Contracting Officer, enter the estimated completion date for each subdivision of work. The entry shall not serve as a notice to NASA of late delivery or acquiescence in such late delivery by NASA.
11. Unfilled Orders Outstanding - As directed by the NASA Contracting Officer, enter the total of unfilled orders outstanding as of the report date (par. 3.3.2.4(2)).
12. Contractor Narrative Remarks - The narrative comments submitted with the quarterly cost projection report shall normally be limited to those items materially affecting projected cost or performance which have not been addressed in the preceding monthly narrative reports (par. 3.6). a. Explain any significant items affecting cost; e.g., technical and schedule problems, changes in plans, over/under runs incurred, etc. b. Include a reconciliation from the original to the present contract value as reported in Item 3. A sample format is set forth in par. 3.6 and Figure A below. c. The NASA Contracting Officer may require that changes authorized but not finalized be further subdivided as follows: (1) Changes negotiated but not definitized. (2) Changes pending negotiation. (3) Changes pending estimation. d. Identify effects of new change orders as set forth in par. 3.6 and Figure B below.
2. Report for Quarter Beginning - Enter the beginning date of the quarter being projected in columns 8a, b and c and the number of working days in the quarter.
3. Contract Value - Enter the total definitized cost (a) and fee (b) of all currently authorized work to be performed under the contract. Include dollar amounts through the latest definitized modification as noted in 1b above. For all incentive contracts, enter the negotiated target cost and fee.
4. Fund Limitation - Enter the total funds obligated and latest corresponding contract modification number.
5 . Billing: a. Invoice Amounts Billed - Enter the total amount of invoices billed against the contract and latest invoice number. b. Total Payments Received - Enter the total amount of payments received for the contract.