Office of the U.S. Global AIDS Coordinator

Task Order Request (TOR)

Task Name:  Provide logistical support to S/GAC in planning and implementing the 2007 President’s Emergency Plan for AIDS Relief (PEPFAR) Annual Meeting and the 2007 HIV/AIDS Implementers’ Meeting (approximately 1,500 attendees total) to be held in Africa in May/June 2007.

Proposed Contractor:

Project Officer:  William Dilday, S/GAC Executive Director, (202) 663-2571

Task Objectives/Requirements:

Please see the attached SOW for task objectives and requirements

Deliverables:

Please see attached SOW for full list of deliverables

- Project plan/timeline

- Weekly status reports (progress, budget, etc)

- Conference center contract

- Hotel contracts

- Secure other vendors as needed

- Design and develop meeting website

- Design registration and abstract submission forms

- Facilitation of online abstract review process

- Provide on-site coordination and logistical support

- Prepare post conference summary

- Develop post conference website

Time and Period of Performance:   October 30, 2006 – September 30, 2007.

# Acceptance Criteria:

- Past Performance

- Corporate Experience

- Price

Cost Estimate:

A contract with a minimum of $1,000,000 and a maximum of $1,500,000.

STATEMENT OF WORK

The PEPFAR Annual Meeting and the 2007 HIV/AIDS Implementers’ Meetings

Background:

On May 27, 2003, The President signed Public Law 108-25, The US Leadership Against HIV/AIDS, Tuberculosis and Malaria Act of 2003.  While providing $15 billion over five years to fight HIV/AIDS abroad, Section 101 of this legislation also imposed a requirement for the Administration to develop The President’s Emergency Plan for AIDS Relief.  As a result, the Office of the US Global AIDS Coordinator (S/GAC or OGAC) was established in the Department of State to lead an integrated US Government (USG) global HIV/AIDS effort; to provide a rallying point for private sector, Faith-Based Organization and Non-Government Organization (NGO) efforts; and to ensure that policies are harmonious, programs synergistic and operations efficient and effective.  The Emergency Plan operates in over 100 nations worldwide, including a special focus on 15 countries – the African nations of Botswana, Cote d’Ivoire, Ethiopia, Kenya, Mozambique, Namibia, Nigeria, Rwanda, South Africa, Tanzania, Uganda and Zambia; the Caribbean nations of Guyana and Haiti; and Viet Nam – in its efforts to combat HIV/AIDS and to promote an integrated prevention, treatment and care program.  In the Emergency Plan’s focus countries, the USG will support treatment of 2 million HIV-infected people; prevent 7 million new HIV infections; and support care for 10 million people infected and affected by HIV/AIDS, including orphans and vulnerable children.  The US Global AIDS Coordinator reports directly to the Secretary of State and oversees and directs all USG international HIV/AIDS activities in all departments and all agencies of the Federal Government.  S/GAC through proactive liaising also coordinates with non-USG stakeholders – host-country governments and multi-lateral institutions such as the World Bank, World Health Organization, Joint United Nations Program on HIV/AIDS (UNAIDS), etc. – in order to develop a coordinated global effort to fight the global HIV/AIDS pandemic.

Introduction:

The 2007 President’s Emergency Plan for AIDS Relief Annual Meeting and the 2007 HIV/IADS Implementers’ Meeting are critical for the implementation of the President’s Emergency Plan for AIDS Relief (PEPFAR) because the PEPFAR meeting serves as the core meeting time for PEPFAR teams in the field to interact with each other and the staff in US-based offices.  The HIV/AIDS Implementers’ meeting is the only conference that brings together HIV/AIDS implementers to widely disseminate in real time lessons learned during the implementation of multi-sectoral HIV/AIDS programs with an emphasis on:

  - Scale-up of prevention, treatment, and care programs,

  - Building local capacity,

  - Quality, and

  - Coordination among partners.

The Implementers’ meeting is also essential in catalyzing an open dialogue about future directions of HIV/AIDS programs with a strong emphasis on implementation.  It also gives participants and presenters the opportunity to directly impact HIV/AIDS program implementation in the upcoming year through the diffusion of best practices.

# Objectives:

The contract objectives are to provide S/GAC with conference facilitation in planning and implementing both meetings  (1,500 participants, six days total – Sunday to Friday) to be held in Africa in May/June 2007 while liaising with S/GAC throughout the decision making and conference implementation process.

# Requirements and Responsibilities – Summary:

The contractor will be responsible for an array of roles in planning for the meetings – please see below for the full list of requirements.  In addition to the below items, the contractor must show experience with USG sponsored conferences, conferences of a similar size (1,500 attendees), conferences that are scientifically driven (including electronic abstract collection and review), and conferences held in developing country settings.  The contractor must also have headquarter locations in the Washington, DC metro area.

Time and Period of Performance:   October 30, 2006 – September 30, 2007.

Specific Requirements:

The contractor shall furnish all necessary personnel, materials, services, facilities and otherwise do all things necessary for or incident to the work described below.

Following are expectations of the contractor:

A.	Project Management Team

The contractor will provide an organization chart and a staffing plan highlighting the background and key responsibilities of staff supporting the project. This plan will include, the Officer in Charge, Project Director and project managers and assistants, meeting planners, travel coordinator accounting staff and editors.

The contractor will provide evidence of the availability, qualifications, and demonstrated experience of key management personnel, including the Project Director, Project Manager and Lead Meeting Planner.  The contractor will also provide evidence of the Project Director’s expertise in managing projects with similar requirements.

- Planning Group and Communication

The contractor will participate in a kick-off meeting and planning team meetings. The frequency of the meetings will be determined by the Project Officer (PO); however, the contractor should anticipate weekly, bi-weekly or monthly meetings with the Project Officer and other key project staff.

- Deliverable Schedule and Timeline

The contractor will prepare a deliverable schedule and outline a timeline based on the statement of work.

- Reporting Requirements

A monthly progress report is required for all tasks. This report should include a description of the work performed during the month and any outstanding issues and/or challenges.

- Web site Development and Management

The contractor will develop a meeting Web site with guidance from the Project Officer. The Web site will serve as a comprehensive one-stop shop for information to potential meeting participants. All communication must be clear and concise. Meeting participants will access the Web site to learn the objectives of the meeting, submit abstracts, register for the meeting, access information about conference hotels and make hotel arrangements, as well as obtain general information about the meeting location.  The contractor will serve as Web master and perform on-going site maintenance necessary to eliminate or minimize downtime.

- Web Based Tools

The contract will provide Web-based reporting tools for the PO to monitor meeting progress (e.g., abstract monitoring, registration reporting, application monitoring, etc.).

- Site Search, Recommendations and Negotiations

The contractor will perform a site search in a region of Africa specified by the Project Officer. The search will take into consideration the number of participants and meeting space requirements as specified by the Project Officer (see attachment I). The contractor will prepare a chart of site search recommendations for review by the PO.

Upon receiving approval from the Project Officer, the contractor will conduct negotiations with the selected meeting site. The contractor will outline a plan and discuss efforts to eliminate or minimize attrition and penalties to S/GAC.

- Housing

The contractor will perform a site search in an effort to secure adequate and appropriate housing for meeting participants. The search will take into consideration the length of the meeting and the number of participants (see attachment I). The contractor will prepare a chart of housing recommendations for review by the PO. Information on the available housing will be posted on the meeting Web site.

Upon receiving approval from the Project Officer, the contractor will conduct negotiations to secure adequate housing for meeting participants. The contractor will develop a plan to allow participants to confirm housing arrangements and eliminate or minimize attrition and penalties to S/GAC.

- Letters and Correspondence

The contractor will draft, finalize and disseminate meeting related letters and correspondence with guidance and approval from S/GAC. These will include but are not limited to invitation letters, speaker letters, confirmation letters, and abstract notifications.

- Meeting Registration

Meeting participants will be expected to register online. Contractor will draft a meeting registration form with guidance from the PO. Participants will be allowed to register in pre-determined categories, e.g., USG, Non-USG, etc. The registration form should take into consideration that potential participants will also be allowed to register for a 2-day USG meeting, a 4-day Implementers’ Meeting or both.  The contractor will facilitate the process for participants who encounter problems or have difficulty with online registration.

- Application Process

Applications for the open registration process will be made available online for a limited period of time.  The contractor will draft an application form with guidance from the PO.  Once applications are submitted they will need to be disseminated to the appropriate approval board with an online acceptance or rejection function.  Applicants who are rejected and accepted should be notified by automatic E-mail. Accepted applicants should be registered in an efficient manner.

- Registrar Training

The Project Officer will identify persons (Registrars) who will assist with in-country registrations. The contractor shall develop a training module that will allow Registrars to understand how to navigate the meeting Web site; assist in-country delegates with the registration process; and manage and monitor registration numbers for in-country delegates. The training should be a Web-based training accompanied by a teleconference. The contractor should anticipate that the training will be delivered to up to 30 in-country Registrars.

- Abstracts and Abstract Management

The contractor will provide online based abstract submission form(s).  They will also manage the online abstract review process including: disseminating abstracts to the appropriate reviewers (provided by S/GAC), collecting online their feedback and ratings and tabulate scores and report back to PO on ranking of abstracts and comments.

- Management and Support of VIPs

The contractor will be expected to work with high level officials including but not limited to US Ambassadors, foreign government officials and other high level speakers. The contractor will provide support to identified VIPs. Support will include confirming that identified VIPs have registered and made hotel arrangements for the meeting, as well as forward any other pertinent documentation to the VIPs. The contractor will also provide onsite assistance identified VIPs.

- Speaker Management

The contractor will provide support to speakers identified by the Project Officer. Support for speakers will include travel, lodging and reimbursement of approved expenses for identified speakers from the African region. In addition, limited support (e.g. disseminating confirmation letters, collecting contact information, presentations and biographies and on-site registration support and management) will be provided to oral and poster presenters and moderators. The contractor will prepare a Speaker Tracking Sheet to be submitted monthly, bi-monthly and weekly as the meeting date approaches. The tracking sheet should include contact information, correspondence log, confirmation dates, speaking times, travel, lodging and reimbursement information with supporting backup documentation.

- Posters and Oral Presentations

The contractor will be responsible for managing the logistics for the poster session including but not limited to notifying poster presenters of acceptance, securing poster boards (approximately 100 posters daily) and adequate space for poster session and providing appropriate instructions to poster presenters.

The contractor will also be responsible for formatting the meeting agenda with the appropriate presenters and presentations times. They will organize logistics for presentations and provide speaker support during sessions. The contractor will also seek speakers’ permission prior to the meeting and collect an electronic copy of final presentations for each presenter. Presentations will be posted to the post-conference Web site (see speaker management for additional required support to the poster and oral presenters).

- Cyber Café and Resource Market Place

The contractor will plan for an area (Cyber Café) where meeting participants will have high speed internet access to at least 30 computers.  In addition, a resource market place should also be available. This will be an area where tables will be available for participants to place materials which would be of interest to the general meeting population. The contractor should expect to staff both locations for the duration of the meeting. The contractor will work with the PO to determine the number of tables needed for these activities.

- Meeting Evaluations

Meeting evaluations will be developed by USG staff; however, the contractor will be required to assemble, duplicate and distribute daily evaluations onsite.

- Subcontract and Vendor Management

The contractor will secure the best value for services rendered and manage delivery of all deliverables. Award of any subcontract is subject to the written approval of the Contract Officer upon review of the supporting documentation as required by FAR Clause 52.215-12, Subcontractor Cost or Pricing Data, of the General Clauses incorporated into the contract.  A copy of the signed subcontract shall be provided to the Contract Officer.

- Materials Development and Production

The contractor will outline a materials development and production timeline. The contractor should anticipate reproduction and preparation of the following materials: Meeting Program and Agenda, Agenda at a Glance, Abstract Book, participant lists, name badges and conference signs.

- Shipping

The contractor will develop a shipping scheduled based on the country, date of the meeting and expected time of delivery. The contractor will inventory all materials prior to shipment and confirm delivery of all materials.

- Site Visit and Onsite Support

The contract will be expected to travel with S/GAC staff to the meeting site (in Africa) for a full site visit prior to the meeting date. The site visit will last approximately 4 days (on the ground).

The contractor will be required to provide onsite support for the duration of the meeting. The contractor should expect to be onsite approximately two weeks prior to the start of the meeting.

The contractor will determine onsite manpower needs and develop an onsite staffing plan to properly support all meeting activities. The contractor will present the staffing plan to the PO for approval.

- Communication

The contractor will be expected to communicate with participants and vendor, many of whom will be international. There may also be a need for the contractor to courier deliverables to S/GAC.

- General Conference Supplies

The contractor will be expected to purchase supplies specific to conference attendees, for example pens, pads, conference folders, badges and lanyards, poster session supplies, etc.

- Shuttle Service

The contractor will secure a vendor to provide shuttle service to participants for travel from respective hotels to and from the conference center. This service will be required daily, i.e, the contractor should anticipate the need for morning shuttles and evening shuttles to accommodate the agenda.

Shuttle service will also be required for a one-day site visit to a local program for up to 30 senior staff members; as well as car service for VIPS (i.e., two cars with drivers will be reserved for the duration of the meeting).

- Budget Monitoring and Management

The contractor will manage tasks to the approved budget and individual line items. Approval must be received in writing from the PO before exceeding limits on any budget line item. The contractor will provide cost reports at pre-determined times to the PO.

- Post Conference Materials

The contractor will develop a post-conference Web site with guidance from S/GAC. Conference presentations, select biographies, final meeting agenda and abstracts will be among the documents housed on the site. The Web site will serve as a resource to meeting attendees and the general public. The post-conference Web site must be 508 compliant. Any graphic presentations must also be formatted in HTML to meet this requirement.

- Post Conference Activities

At the conclusion of the meeting the contractor will ensure that all vendors are paid and all speaker reimbursements are processed in a timely manner. The contractor will prepare in draft a meeting and financial summary for review and approval by the PO. Upon approval the contractor will submit final summaries to the PO. The contractor will also participant in a meeting debrief with select staff from S/GAC.

Attachment 1:

| The President's Emergency Plan for AIDS Relief Annual Meeting |
| --- |
| The 2007 HIV/AIDS Implementers' Meeting |  |
| May/June 2007 |  |
| Day 1 |  |
| Room Purpose | Number of Delegates | Room Name/Location | Time | Setup | Other |  |
| USG Plenary | 500 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| Breakaway 1 | 100 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| Breakaway 2 | 100 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| Breakaway 3 | 100 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| Breakaway 4 | 100 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| Breakaway 5 | 150 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| USG Awards Dinner | 500 |  | 7:30pm - 10:00 pm | Banquet | Also need stage for entertainment, microphone and podium for award presentation |  |
| Registration | Varies |  | 6:00am - 7:00 pm | Registration Flow | Set for week: Tables/chairs to accommodate 1,500 delegates |  |
| Professional Conference Organizers Office (Secretariat) | Varies |  | 24hr access |  | Allow for: Computers, fax machine, copier, telephones, storage space for materials |  |
| USG Office | 30 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Embassy Control Office | 50 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Speakers Registration and Lounge Area | Varies (flow) |  | 6:00am - 7:00 pm |  | Tables/chairs to accommodate approximately,500 speakers |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| Ambassador's Office | 5 |  | 6:00am - 7:00 pm | Conference |  |  |
| Cyber Café | varies |  | 6:00am - 7:00 pm | Computer stations | space for up to 30 computers (tables/chairs). Space could also be used for business center: copier, fax, printers |  |
| Respite Area | varies |  | 6:00am - 7:00 pm | TBD | setup to be confirmed |  |
| VIP Lunch | 50 |  | 11:00am - 2:30 pm | Rounds | setup to be confirmed |  |
| Day 2 |  |
| Room Purpose | Number of Delegates | Room Name/Location | Time | Setup | Other |  |
| USG Plenary | 500 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| Breakaway 1 | 100 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| Breakaway 2 | 100 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| Breakaway 3 | 100 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| Breakaway 4 | 100 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| Breakaway 5 | 150 |  | 7:00am - 7:00pm | Schoolroom |  |  |
| Registration |  |  | 6:00am - 7:00 pm | Registration Flow | Tables/chairs to accommodate 1,500 delegates |  |
| Secretariat Office | Varies |  | 24hr access |  | see day 1 setup |  |
| USG Office | 30 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Embassy Control Office | 50 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Speakers Registration and Lounge Area | Varies (flow) |  | 6:00am - 7:00 pm |  | see day 1 setup |  |
| VIP Room | 15 |  | 7:00am - 7:00pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 7:00pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 7:00pm | Lounge |  |  |
| Ambassador's Office | 5 |  | 6:00am - 7:00 pm | Conference |  |  |
| Cyber Café | varies |  | 6:00am - 7:00 pm |  | see day 1 setup |  |
| Press Filing Center | varies |  | 6:00am - 7:00 pm |  | audio visual and media equipment |  |
| Respite Area | varies |  | 6:00am - 7:00 pm |  | scattered seating (setup TBD) |  |
| Day 3 |  |
| Room Purpose | Number of Delegates | Room Name/Location | Time | Setup | Other |  |
| Plenary | 1500 |  | 7:00am - 6:00 pm | Theater |  |  |
| Poster Hall | 200 |  | 7:00am - 7:00 pm | Poster Boards | Poster Session - number of poster TBD |  |
| Resource Room |  |  | 7:00am - 5:00 pm | Tables for materials | May be able to use part of poster session area (Room 3) |  |
| Breakaway 1 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 2 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 3 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 4 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 5 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 6 | 250 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 7 | 250 |  | 7:00am - 7:00 pm | Theater |  |  |
| Opening Reception | 1500 |  | 7:30pm - 10:00pm | Banquet |  |  |
| Registration | Flow |  | 6:00am - 7:00 pm | Registration Flow | Tables/chairs to accommodate 1,500 delegates |  |
| Secretariat Office | Varies |  | 24hr access |  | see day 1 setup |  |
| USG Office | 30 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Embassy Control Office | 50 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Speakers Registration and Lounge Area | Varies (flow) |  | 6:00am - 7:00 pm |  | see day 1 setup |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| Ambassador's Office | 5 |  | 6:00am - 7:00 pm | Conference |  |  |
| Cyber Café | varies |  | 6:00am - 7:00 pm |  | see day 1 setup |  |
| Press Filing Center | varies |  | 6:00am - 7:00 pm |  | set up evening of day 2 |  |
| Respite Area | varies |  | 6:00am - 7:00 pm |  | scattered seating (setup TBD) |  |
| Day 4 |  |
| Room Purpose | Number of Delegates | Room Name/Location | Time | Setup | Other |  |
| Plenary | 1500 |  | 7:00am - 6:00 pm | Theater |  |  |
| Poster Hall | 200 |  | 7:00am - 7:00 pm | Poster Boards | Poster Session - number of poster TBD |  |
| Resource Room |  |  | 7:00am - 5:00 pm |  | Tables for materials |  |
| Breakaway 1 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 2 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 3 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 4 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 5 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 6 | 250 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 7 | 250 |  | 7:00am - 7:00 pm | Theater |  |  |
| Registration | Flow |  | 6:00am - 7:00 pm | Registration Flow | Tables/chairs to accommodate 1,500 delegates |  |
| Secretariat Office | Varies |  | 24hr access |  | see day 1 setup |  |
| USG Office | 30 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Embassy Control Office | 50 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Speakers Registration and Lounge Area | Varies (flow) |  | 6:00am - 7:00 pm |  | see day 1 setup |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| Ambassador's Office | 5 |  | 6:00am - 7:00 pm | Conference |  |  |
| Cyber Café | varies |  | 6:00am - 7:00 pm |  | see day 1 setup |  |
| Press Filing Center | varies |  | 6:00am - 7:00 pm |  |  |  |
| Respite Area | varies |  | 6:00am - 7:00 pm |  | scattered seating (setup TBD) |  |
| Day 5 |  |
| Room Purpose | Number of Delegates | Room Name/Location | Time | Setup | Other |  |
| Plenary | 1500 |  | 7:00am - 6:00 pm | Theater |  |  |
| Poster Hall | 200 |  | 7:00am - 7:00 pm | Poster Boards | Poster Session - number of poster TBD |  |
| Resource Room |  |  | 7:00am - 5:00 pm |  | Tables for materials |  |
| Breakaway 1 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 2 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 3 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 4 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 5 | 200 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 6 | 250 |  | 7:00am - 7:00 pm | Theater |  |  |
| Breakaway 7 | 250 |  | 7:00am - 7:00 pm | Theater |  |  |
| Registration | Flow |  | 6:00am - 7:00 pm | Registration Flow | Tables/chairs to accommodate 1,500 delegates |  |
| Secretariat Office | Varies |  | 24hr access |  | see day 1 setup |  |
| USG Office | 30 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Embassy Control Office | 50 |  | 6:00am - 7:00 pm | Conference | include scattered seating |  |
| Speakers Registration and Lounge Area | Varies (flow) |  | 6:00am - 7:00 pm |  | see day 1 setup |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| Ambassador's Office | 5 |  | 6:00am - 7:00 pm | Conference |  |  |
| Cyber Café | varies |  | 6:00am - 7:00 pm |  | see day 1 setup |  |
| Press Filing Center | varies |  | 6:00am - 7:00 pm |  | see day 1 setup |  |
| Respite Area | varies |  | 6:00am - 7:00 pm |  | scattered seating (setup TBD) |  |
| Day 6 (BREAKDOWN DAY) |  |
| Room Purpose | Number of Delegates | Room Name/Location | Time | Setup | Other |  |
| Plenary | 1500 |  | 7:00am - 5:00 pm | Theater |  |  |
| Poster Hall | 200 |  | 7:00am - 5:00 pm | Poster Boards | Poster Session - number of poster TBD |  |
| Resource Room |  |  | 7:00am - 5:00 pm |  | Tables for materials |  |
| Breakaway 1 | 200 |  | 7:00am - 5:00 pm | Theater |  |  |
| Breakaway 2 | 200 |  | 7:00am - 5:00 pm | Theater |  |  |
| Breakaway 3 | 200 |  | 7:00am - 5:00 pm | Theater |  |  |
| Breakaway 4 | 200 |  | 7:00am - 5:00 pm | Theater |  |  |
| Breakaway 5 | 200 |  | 7:00am - 5:00 pm | Theater |  |  |
| Breakaway 6 | 250 |  | 7:00am - 5:00 pm | Theater |  |  |
| Breakaway 7 | 250 |  | 7:00am - 5:00 pm | Theater |  |  |
| Registration | Flow |  | 7:00am - 5:00 pm | Registration Flow | Tables/chairs to accommodate 1,500 delegates |  |
| Secretariat Office | Varies |  | 7:00am - 5:00 pm |  | see day 1 setup |  |
| USG Office | 30 |  | 7:00am - 5:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 7:00am - 5:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 7:00am - 5:00 pm | Conference | include scattered seating |  |
| Co-Sponsors Office | 50-100 |  | 7:00am - 5:00 pm | Conference | include scattered seating |  |
| Embassy Control Office | 50 |  | 7:00am - 5:00 pm | Conference | include scattered seating |  |
| Speakers Registration and Lounge Area | 500 |  | 7:00am - 5:00 pm |  | see day 1 setup |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| VIP Room | 15 |  | 7:00am - 5:00 pm | Lounge |  |  |
| Ambassador's Office | 5 |  | 7:00am - 5:00 pm | Conference |  |  |
| Cyber Café | varies |  | 7:00am - 5:00 pm |  | see day 1 setup |  |
| Press Filing Center | varies |  | 7:00am - 5:00 pm |  | see day 1 setup |  |
| Respite Area | varies |  | 7:00am - 5:00 pm |  | scattered seating (setup TBD) |  |