F. TASK DESCRIPTION:

LOGISTICAL SUPPORT FOR THE NATIONAL EYE INSTITUTE’S NATIONAL EYE HEALTH EDUCATION PROGRAM MEETINGS

Background

Historically, the National Eye Health Education Program, supported by the National Eye Institute (NEI), has worked to educate our citizens about the importance of eye health. NEI is committed to achieving the eye health objectives set in Healthy People 2010. In support of the Program, meetings are held for the NEHEP Planning Committee and various subcommittees and work groups.  In addition, a biannual conference is held.  The goal of these meetings is to strengthen the Program and provide opportunities for outside organizations to provide insight and feedback for new and existing programs.

Statement of Work

The purpose of this task is to provide logistical support for meetings that are held to support the National Eye Health Education Program.  Approximately 6-8 one-day meetings will be held per year.  A 3-day biannual conference will be held in 2008.  The following is a description of the tasks the contractor will perform in support of this conference.

1. Select and coordinate with meeting sites.  The contractor will propose and help select a meeting site and coordinate the arrangements with the facility for each meeting.

2. Plan and manage breaks, meals, and receptions. In consultation with the NEI task initiator, the contractor will plan and manage meal functions as required

3. Prepare invitational letters and packets. The contractor will prepare and distribute letters of invitation and any attachments, such as agendas and registration materials as required.   The contractor will research, as requested, proper titles, affiliations, and addresses.

4. Provide graphic artist. The contractor will provide a graphic artist to create any designs that may be needed for meeting materials.

5. Create registration website and manage registration. As required, the contractor will provide an informational and registration website, which will track conference attendees.  The contractor will manage all preregistration information, including receiving inquiries, dissemination information packets, and accepting registration fees. The contractor’s database will track all pertinent registrant information on attendees.

6. Arrange lodging and transportation. The contractor will arrange lodging and transportation for approximately 25-30 participants for each meeting,

7. Provide out-of-pocket expense reimbursement. The contractor will provide all travel and per diem reimbursements for up to 30 participants as allowed by the Government travel regulations. Invoices for such expenses will be reviewed and approved by the NEI task initiator before approval by the contractor conference manager and subsequent payment to the participants.

8. Prepare pre-meeting materials. The contractor will prepare, reproduce, and distribute to all attendees by mail prior to the meeting, and/or at the meeting, all necessary advance materials, including itineraries, appropriate travel guide materials, and background materials.

9. Provide meeting facilitator/manager. The contractor will assist the NEI task initiator prior to and during the conference, and recommend sufficient staff for meeting functions such as planning, clerical support, messenger service, registration, information desk, audiovisual equipment, recording, transcription, and other meeting support as needed. As required, the contractor will provide one additional staff person for onsite support, as well as an audiovisual technician during the meeting.

10. Provide audiovisual equipment and support and meeting supplies. The contractor will work with the facility to provide necessary amplification systems, blackboards and chalk, pointers, projectors, video equipment, screens, easels, and recording equipment as needed. The contractor will also provide meeting supplies such as name badges, signage, tent cards, and other identifiers, note pads and pencils, etc.

11. Prepare post-conference materials. The contractor will prepare, reproduce, and distribute post-conference materials to attendees as required.

12. Prepare evaluation form. As required, the contractor will design, distribute, and collect an evaluation form to identify future requirements and/or improvements regarding the agenda and logistical arrangements for the meeting. The contractor will tabulate results prepare a final meeting report for submission to the NEI task initiator.

13. Submit monthly progress reports. The contractor conference manager will prepare and submit monthly progress reports on the meeting activities to the NEI task initiator.

14. Track task expenses and prepare monthly financial reports. The contractor will prepare monthly invoices, showing current costs for the month as well as cumulative costs for the task with backup. The contractor’s project manager also will prepare a monthly report on the task, indicating number of hours incurred, hours remaining, costs to date, and funds remaining. In addition, the contractor will maintain copies of all vendor invoices and participant reimbursement information in her meeting notebook for reference. Any items over or under budget shall be discussed with the NEI Project Officer.

15. Prepare final report. The contractor’s project manager and conference manager will prepare a final task report within 10 days following the end of the contract.  The report will include the meeting title, dates, place, description of the meeting substance, copies of the program materials, list of speakers and participants, and a description of all services provided as well as problems experienced.

Specific task deliverables:

• Work plan and schedule

• Logistical arrangements, i.e., audiovisual equipment, food functions, lodging and travel arrangements for specified invitees.

• Provision and processing of lodging and per diem expenses.

• Onsite logistical support, including meeting packets, meeting management, audiovisual support, and transcription.

• Preparation and assembly of preregistration, meeting materials, agendas, name badges, registration packets, and others.

• Monthly progress reports, monthly financial reports, and a final report.

H. EVALUATION FACTORS

• RELATED EXPERIENCE:  Contractor must show directly related experience with the National Eye Health Education Program, its Partnership, and NEI.

• STAFFING/CORPORATE EXPERIENCE: Qualifications of personnel and their ability to perform the work will be evaluated.

• COST: While price is not the most important evaluation factor, proposed prices will be considered when selecting the firm that represents the best value to the Government.