# Construction Schedule

# Examples

4R Examples

The significant restrictions imposed on this project are: No major ground disturbing activities from November 1 thru April 31 and all clearing must be performed during the non-nesting season which is August 1 to January 31. These restrictions will have the most impact on the construction contract time. The key activity driving the duration of construction is wall construction. It was assumed that there would be 2 wall crews working. This assumption was chosen to be conservative.

The biggest restriction imposed on this project is weather conditions. It is possible that this project may have to shut down due to snow from the beginning of November to the end of March. The key activity during construction will be wall construction. It is anticipated that this project will need three construction seasons to complete the 1.5 mile section. The time to complete the project will be reduced with the length of the project actually being construction. The current estimate for the construction schedule has the project starting on April 21, 2008 and ending on November 3, 2010. Please see the attached CPM for more detailed information.

The anticipated start of construction is May 13, 2005 and the completion date is September 30, 2005. No interim dates are necessary. The critical path method (CPM) was used to generate the schedule. The completion date can be extended by 15 days, if necessary. Completion of temperature critical work becomes an issue if construction occurs beyond October 30.

3R Examples

The anticipated start of construction is May 13, 2005 and the completion date is September 30, 2005. No interim dates are necessary. The critical path method (CPM) was used to generate the schedule. The completion date can be extended by 15 days, if necessary. Completion of temperature critical work becomes an issue if construction occurs beyond October 30.

Due to the higher elevations and mountainous location of the project, the construction season would be limited to May through October.

This construction package is planned for advertisement on January 15, 2006. Subsequently, the bid opening and notice to proceed will be February 15th and March 15th respectively. Final completion of the project is expected by September 1, 2006. Originally, the National Park Service goal was to have the construction completed by the Fourth of July weekend. This is generally one of the two biggest weekends for visitation at the park. At 70% design a preliminary construction schedule using the critical path method (CPM) was put together to estimate if this goal could be accomplished. The opening of the local batch plants was and still is the critical path for paving and ultimately the completion of the project. The 70% schedule had NTP on January 1st and paving operations beginning in mid-March. The parks’ goal was reachable with the project completion shown on May 19th. Due to the shelving of the Halls Crossing project, the construction schedule had to be reviewed once again. The Glen Canyon NRA inquired if the project, or at least the paving operations, could be completed before the Memorial Day Holiday weekend. In taking another look at the paving operations and long haul required for this remote site, it was determined that paving operations would take significantly longer than first estimated. Additionally, the first schedule done at 70% was overly optimistic when paving could begin. Even if the local batch plant opens early, daytime temperatures would not become warm enough until later in the year, especially with a possible 3-hour haul to the project site. Pulverization and paving is estimated to take 5 and 7 weeks respectively. Both the parks’ goals of being completed by Memorial Day and Fourth of July weekend are not unattainable.