## Sources
Source | Receipt | Inversion | Test Insert & Review | Insertion | Editing | Release Date | Workdays Receipt to Release | Release Version
NCI Thesaurus
NCI2007_01D | 2007-02-02 | 2007-02-09 | 2007-02-26 | 2007-02-27 | 2007-03-16 | 2007-04-12 | 50 | Meta2007_01D
NCI2007_02C | 2007-03-06 | 2007-03-08 | skip test insertion | 2007-03-28 | 2007-04-06 | 2007-04-18 | 32 | Meta2007_02C
NCI2007_03D | 2007-04-09 | 2007-04-10 | skip test insertion | 2007-04-30 | 2007-05-31 | 2007-06-15 | 50 | Meta2007_03D
NCI2007_04E | 2007-05-11 | 2007-05-16 | skip test insertion | 2007-06-08 | 2007-07-23 | n/a | 0 | n/a
NCI2007_05E | 2007-06-04 | 2007-06-07 | skip test insertion | 2007-07-20 | 2007-07-26 | 2007-08-12 | 50 | Meta2007_05E
NCI2007_06D | 2007-07-10 | 2007-08-08 | 2007-08-21 | 2007-08-22 | 2007-08-31 | 2007-09-12 | 47 | Meta2007_06D
NCI2007_07C | 2007-08-20 | 2007-08-22 | skip test insertion | 2007-09-19 | 2007-10-01 | 2007-10-12 | 40 | Meta2007_07C
NCI2007_08D | 2007-09-25 | 2007-08-26 | skip test insertion | 2007-10-03 | 2007-10-15 | n/a |  | n/a
NCI2007_09D | 2007-10-18 | 2007-10-24 | skip test insertion | 2007-11-15 | 2007-11-19 | 2007-12-17 | 43 | Meta2007_09D
NCI2007_10D | 2007-11-12 | 2007-11-13 | skip test insertion | 2007-12-05 | 2007-12-19 | 2008-01-31 | 57 | Meta2007_10D
NCI2007_12A | 2007-12-11 | 2007-12-13 | skip test insertion | 2007-12-24 | 2008-01-14 | n/a |  | n/a
NCI2007_12E | 2008-01-07 | 2008-01-08 | skip test insertion | 2008-03-13 | 2008-03-27 | 2008-04-14 | 69 | Meta2007_12E
NCI2008_01D | 2008-02-06 | 2008-02-08 | skip test insertion | 2008-03-27 | 2008-04-04 | n/a |  | n/a
NCI2008_02D | 2008-03-04 | 2008-03-11 | skip test insertion | 2008-04-02 | 2008-04-15 | in progress
NCI2008_03D | 2008-04-07 | 2008-04-08 | skip test insertion | in progress
NCI Local Sources
CBO2005_06 | 2005-06-20 | 2005-08-26 | 2005-09-01 | 2005-10-31 | 2005-11-15 | 2006-02-08 | 168 | Meta2005_09
MDBCAC2005_12 | 2005-12-27 | 2006-01-10 | 2006-01-22 | 2006-01-23 | 2006-01-26 | 2006-02-16 | 38 | Meta2005_10E
CBO2006_03 | 2006-04-11 | 2006-04-24 | 2006-06-12 | 2006-06-19 | 2006-07-17 | 2006-08-07 | 85 | Meta2006_05D
MDR90 | 2006-05-22 | 2006-05-24 | 7/17/1006 | 2006-07-24 | 2006-09-29 | completed | 0 | Meta2006_06E
MDRSPA90 | 2006-05-24 | 2006-05-25 | 2006-07-17 | 2006-08-02 | 2006-09-29 | n/a | 0 | n/a
ICDO3 | 2006-09-05 | 2006-09-19 | n/a | 2006-09-24 | 2006-09-29 | completed | 0 | Meta2006_06E
PDQ2006_12 | 2006-12-04 | 2006-12-07 | 2006-12-28 | 2006-12-29 | 2007-01-17 | 2007-02-07 | 48 | Meta2006_11D
PMA2007 | 2006-10-18 | 2006-11-26 | 2006-11-28 | 2006-11-29 | 2006-12-04 | 2006-12-29 | 53 | Meta2006_10D
MGED2006_11_08 | 2006-12-06 | 2007-03-02 | 2007-03-12 | 2007-03-22 | 2007-04-06 | 2007-04-18 | 96 | Meta2007_02C
PDQ2007_05 | 2007-05-08 | 2007-05-16 | 2007-06-20 | 2007-07-30 | 2007-08-31 | 2007-09-12 | 92 | Meta2007_06D
CBO2007_06 | 2007-07-17 | 2007-08-20 | 2007-08-27 | 2007-09-05 | 2007-10-01 | 2007-10-12 | 64 | Meta2007_07C
PDQ2007_11 | 2007-11-12 | 2007-11-15 | 2007-12-10 | 2007-12-12 | 2007-12-20 | 2008-01-31 | 57 | Meta2007_10D
RADLEX2.0 | 2007-12-05 | 2008-01-30 | 2008-04-18 | in progress
0
UMLS Metathesaurus | [6 empty] | 0
UMLS 2005AC | 2005-12-19 | 2006-01-13 | 2006-03-22 | 2006-04-03 | 2006-06-12 | 2006-07-24 | 156 | Meta2006_03D
UMLS2006AA | 2006-06-22 | 2006-07-09 | 2006-08-14 | 2006-08-24 | 2006-09-29 | completed | 0 | Meta2006_06E
UMLS2006AB | 2006-09-18 | 2006-12-05 | 2007-02-12 | 2007-02-26 | 2007-03-16 | 2007-04-12 | 149 | Meta2007_01D
MTH2006AC | 2007-01-08 | 2007-02-23 | 2007-04-03 | 2007-04-18 | 2007-05-31 | 2007-06-15 | 115 | Meta2007_03D
MTH2006AD | 2007-04-16 | 2007-04-30 | 2007-05-25 | 2007-06-18 | 2007-07-23 | 2007-08-13 | 86 | Meta2007_05E
MTH2007AA | 2007-05-07 | 2007-06-01 | 2007-10-15 | 2007-10-21 | 2007-11-13 | 2007-12-17 | 161 | Meta2007_09D
MTH2007AB | 2007-07-10 | 2007-11-26 | 2008-01-08 | 2008-01-22 | 2008-03-27 | 2008-04-14 | 197 | Meta2007_12E
MTH2007AC | 2007-07-10: 2007-11-28; 2007-11-26: 2008-02-19; 2008-01-08: in progress
META RELEASE | EXPORT | BUILD | LOAD | FTP |  |  | Workdays EXPORT to FTP
Meta2005_09 | 2006-01-24 | 2006-02-07 | 2006-02-07 | 2006-02-08 |  |  | 12
Meta2005_10E | 2006-02-13 | 2006-02-15 | 2006-02-16 | 2006-02-16 |  |  | 4
Meta2005_12F | 2006-03-13 | 2006-03-14 | 2006-03-14 | 2006-03-14 |  | 0 | 2
Meta2006_01C | 2006-04-03 | 2006-04-05 | 2006-04-05 | 2006-04-05 |  |  | 3
Meta2006_02D | skip export | n/a | n/a | n/a |  |  | 0
Meta2006_03D | 2006-06-26 | 2006-07-24 | 2006-07-24 | 2006-07-24 |  |  | 21
Meta2006_05D | 2006-08-02 | 2006-08-07 | 2006-08-07 | 2006-08-07 |  |  | 4
Meta2006_06E | 2006-10-09 | completed | completed | completed |  |  | 0
Meta2006_09D | 2006-11-10 | 2006-12-08 | 2006-12-08 | 2006-12-08 |  |  | 21
Meta2006_10D | 2006-12-21 | 2006-12-29 | 2006-12-29 | 2006-12-29 |  |  | 7
Meta2006_11D | 2007-01-25 | 2007-02-07 | 2007-02-07 | 2007-02-07 |  |  | 10
Meta2007_12D | skip export | n/a | na/ | n/a |  |  | 0
Meta2007_01D | 2007-03-26 | 2007-04-12 | 2007-04-12 | 2007-04-12 |  |  | 14
Meta2007_02C | 2007-04-13 | 2007-04-18 | 2007-04-18 | 2007-04-18 |  |  | 4
Meta2007_03D | 2007-06-11 | 2007-06-15 | 2007-06-15 | 2007-06-15 |  |  | 5
Meta2007_05E | 2007-08-03 | 2007-08-13 | 2007-08-13 | 2007-08-13 |  |  | 7
Meta2007_06D | 2007-09-07 | 2007-09-12 | 2007-09-12 | 2007-09-12 |  |  | 4
Meta2007_07C | 2007-10-09 | 2007-10-12 | 2007-10-12 | 2007-10-12 |  |  | 4
Meta2007_08D | skip export | n/a | n/a | na
Meta2007_09D | 2007-12-12 | 2007-12-17 | 2007-12-17 | 2007-12-17 |  |  | 4
Meta2007_10D | 2008-01-28 | 2008-01-31 | 2008-01-31 | 2008-01-31 |  |  | 4
Meta2007_12E | 2008-03-31 | 2008-04-14 | 2008-04-14 | 2008-04-14 |  |  | 11
Meta2008_02D | 2007-07-10: in progress
Formulas:
Workdays Receipt to Release = IF(ISERROR(NETWORKDAYS([Receipt],[Release Date],Holidays!$A4:A23)),0,IF(NETWORKDAYS([Receipt],[Release Date],Holidays!$A4:A23)>0,NETWORKDAYS([Receipt],[Release Date],Holidays!$A4:A23),0))
Workdays Receipt to Release = IF(ISERROR(NETWORKDAYS([Receipt],[Insertion],Holidays!$A4:A23)),0,IF(NETWORKDAYS([Receipt],[Insertion],Holidays!$A4:A23)>0,NETWORKDAYS([Receipt],[Insertion],Holidays!$A4:A23),0))
Note on D4: squan: 3/5/07 Carol C. running ExportRels.
Note on D17: quans: 4/7 Original data received on 4/4 but the value of the source and termtype fields switched. Corrected data received today.
Note on D26: squan: Questions about data format. Seeing end of line characters within records. Asked NCI about it. 12/4 We are going to go ahead with the inversion and try to fix the data ourselves since we haven't heard back re: the data format problems yet.
Note on D29: quans: 4/10/07 Received April data. 5/8/07 Decided to use May data instead. Changed SAB to PDQ2007_05.
Note on D45: Waited until PDQ2005_12 editing was complete before beginning export.
Note on D46: File being collected 1/31/06. 2/9/06 Export essentially complete. Need to copy back files to Apelon for the build and create the history and mapping files.
Note on D50: Apelon: Export is a little behind schedule because of some tricky issues related to the way the MTH update works and because the parallel operations with the MEMEDB cleanup are making the machine quite slow.
Note on D52: Apelon: Export started 10/6/2006
Note on D57: squan: 3/9/07 start export 3/12/07 editing continues; start export at end of week 3/19/07 db ready for export
Note on D58: squan: 4/6/07 DB ready for export. 4/8/07 Export started.
Note on D59: quans: 5/31/07 Editing complete. Db ready for export. 6/4/07 Export running.
Note on D60: quans: 7/24/07 DB ready to begin export. 7/24/07 DB still has some concepts that require editing. (These did not show up due to bug in EMS). DB returned. 7/26/07 Editing complete. 7/27/07 Export beginning.
Note on D65: quans: 12/19 db ready for export. 1/24 Export still in progress.
Note on D66: quans: 3/31 RRF files currently being built.
Note on D67: quans: 4/7 Export to start next week.4/18 Export in progress.
Note on E8: quans: 7/12 Questions about new subsources and ATNs that have been omitted from the configuration file. NCI checking into this. 8/6/07 Waiting for a citation for subsource ICH.
Note on E16: quans: 3/4 Data problem with source and termtype values switched. Sent file of affected records to NCI. 3/6 Received fixed file. Inversion started.
Note on E20: Time includes waiting for new relationship files, sty assignments, finalizing source inversion proposal, etc.
Note on E22: 4/12 sent NCI and Cerner proposal and source information for review. 4/21 Data error in cbo_terms.csv file. Manually corrected file and re-ran scripts.
Note on E25: Apelon: 9/8 Inversion complete. 9/18 Found that SAIDs were overlapping due to an error in a previous source. 9/19 Re-inverted source with new SAIDs.
Note on E27: MSD: There were many problems with the encoding of the data. Had to translate an Excel file to cp1252 then to utf8. Needed to remove bullets and other control characters resulting from the Excel format, needed to translate unicode characters to ascii.
Note on E29: squan: 4/11/07 sent PDQ2007_04 source inversion proposal to NCI. Waiting for feedback. 5/7/07 SLQ will start inversion this week. 5/8/07 Decided to use May data rather than April's. Changed SAB to PDQ2007_05.
Note on E30: quans: 7/19/07 Before continuing with inversion , NCI will decide if they want to update this source. 8/13/07 Begin inversion process.
Note on E31: quans: 11/12/07 Will start inversion after NCI2007_10D complete.
Note on E32: quans: 1/24 Conference call with Sherri to discuss data and source inversion proposal.
Note on E38: squan: 2/23 re-run of MTH2006AC for NCI with SCTSPA moved from part3 to part2
Note on E42: quans: 2/4 Sherri will check to see if any feedback received on replacing MDR90 with MDR10. 2/15 Sherri checking with Frank re: any feedback. 2/19 Inversion complete using MDR10.
Note on E45: Ran out of space on 1/26/06. Build has to be re-started. Build finished 1/27. Sharon out. Build checked 1/30 and files being sent. Being put in test database 1/30. Problem discovered with hierarchy 1/31/. MRCXT and MRREL corrected and build rerun on 2/2. 2/2-2/3/06 - Problem with 'no record locks'. 2/6/06 - Still working on record lock problem. Meeting with Sherri today. Resolved problem in the pm. Scripts ran overnight. 2/7/06 Created concept.out files.
Note on E50: Apelon: 7/5 encountered core dump and out of memory error messages.7/9 build completed over the weekend; files being zipped. 7/11 context.dat file to large to zip. Need to split files. 7/13 Split successfully done but found context.dat not correct. Nels edited script to split MRCXT which is used in creating context.dat. New context.dat created. Also going to try processing files on cbioapp513 since it has more memory/space than Apollo. 7/14 -7/21 Encountered additional problems of extra end of line characters, UMLS SAB contained a "." (period) which is not allowed in Metaphrase. Some scripts need to be re-written. 7/24 Scripts completed. Portion of build run over the weekend. Building mphdata files.
Note on E53: squan: 12/4 Waiting for atlas to be setup so that the concept.out files can be created.
Note on E57: squan: 3/27/07 migration of data to cbioatlas /d1 directory not complete yet. Should be ready by next week and then can start build. 4/3/07 /d1 and /d2 directories now ready.
Note on F3: squan: 2/12/2007 NCI will be test inserted after UMLS2006AB Part III has been inserted. 2/23/2007 Had a db available so test inserted. 2/25/07 test insertion completed.
Note on F4: squan: 3/12/07 Carol to check w/Laura whether it should be inserted at the same time as MGED or inserted later on. 3/26/07 ready to start test insertion. 3/27/07 Skip test insertion. Start with real insertion.
Note on F8: quans: 8/20/07 Test insertion complete and review underway.
Note on F22: Apelon: 5/22 Currently being reviewed. Real insertion will take place after editing of UMLS2005AC is complete.
Note on F23: Apelon: 6/19 test insert MDR again. 6/26 test insertion complete. 7/9 under review.
Note on F24: Apelon: Test insertion complete on 6/1.
Note on F29: quans: 5/14/07 Can be test inserted after the db has been turned over to Brian. 6/8/ Test insertion complete. Under review. 6/18/07 Reviewing test insertion.
Note on F32: quans: 1/24 Will fill in sources.src with temp. data for test insertion. Will update with official data when received. 2/4 Two files sent: one of data issues and one a list of attributes with their values/domains. Being reviewed by NCI. 2/6 Meeting with Daniel R. to discuss data issues. Working on identifying every RADLEX record affected for each data issue found. 2/12 Sent file of all affected records to Daniel and Sherri. 2/13 Daniel asks to wait until they fix data before test inserting. 3/10 Unknow when corrections will be made. May test insert next week after demotions have gone down. 3/17 After 12E export, will copy db and test insert. Corrections not received yet. 4/2 Test insertion completed. 4/7 Under review. 4/10 2nd test insertion started. 4/14 AS termtype causing inappropriate merging. Will exclude AS from merging. Re-running test insertion. 4/16 Radlex test insertion completed.
Note on F35: 2/3/06 - Test insertion of 2005AC continues. We had to temporarily stop it due to the large volume of activity during the insertion which was slowing down preparations for the export and NCI2005_12F insertion. 2/14/06 the disk configuration on cbioapp513 is not optimal for Oracle; the inversion files had left off a field from classes_atoms.src file that is needed for the CUI assignment which is very important for the UMLS update; we have refreshed the DB, re-inverted the classes file and will proceed with the test insertion (again). 3/6 2005AC inversion is being redone to include "suppressible" atoms from the UMLS. The algorithm used to remove certain term types when generating the UMLS subset for the NCI update caused all suppressible atoms including RXNORM/OCD,OBD to be left out. This involves starting with UMLS files and generating the relevant subset and re-inverting the files. 3/9 UMLS_CUI attributes for the existing UMLS data were inserted. This will assist in handling the UMLS 2005AC update properly.
Note on F37: squan: 1/8 part I of test insertion (MSH) complete; beginning part II (SNOMEDCT) begins 1/9. 1/12 test insertion complete. Review in progress. 1/23 Test insertion for part III. 1/25 Bug found in scripts for part III. Test insertion re-started. 1/28 Part III under review. Part I real insertion this weekend.
Note on F38: squan: 3/19/07 part I test insertion complete. 3/20/07 part I test insertion review complete. 3/26/07 Start part II test insertion this week 3/30/07 Part II test insertion and review completed. 3/30/07 Start Part III test insertion. 4/2/07 Part III test insertion complete. 4/3/07 Part III review complete.
Note on F39: quans: 5/9/07 Part I test insertion complete. 5/17/07 Part II test insertion complete. 5/18/07 Part III test insertion complete. 5/23/07 Review in progress.
Note on F40: quans: 9/17 To be test inserted this week. 9/25/ Test insertion complete.
Note on F41: quans: 12/13/07 test insertion started. 12/17/07 Part I complete. Part II in progress. 12/21/07 Part II in progress. 12/27/07 Test insertion complete. Under review.
Note on F42: quans: 3/31 AC test insertion can be done after the RADLEX test insertion. 4/14 Test insertion after the 200802 export.
Note on F45: 1/30 CBO codes too long for code field in Oracle table. Corrected and rebuilt mphdata.zip file. Data loaded into test database. Created concept.out reports but found problem with the relationships of the higher level concepts. No hierarchical tree displaying. 1/31 Will correct the relationship files and rebuild. 2/6/06 - Second attempt at load on hold until 'lock' problem resolved. Lock problem resolved. 2/7/2006 Data loaded into test db.
Note on G3: squan: 2/27/07 Insertion completed.
Note on G6: quans: 5/14/07 Insertion done after export.
Note on G7: quans: 6/18/07 NCI will let us know when they are ready for us to insert. 7/19/07 Begin insertion tonight after 5pm.
Note on G9: quans: 9/17 To be inserted either Tues or Wed.
Note on G11: quans: 10/29/07 Wait for editing counts to decrease before inserting. 11/5/07 insert possibly Mon or Tues (11/12-13) before next export 11/14/07 Insertion started.
Note on G13: quans: 12/21 insertion started
Note on G15: quans: 3/24 To be inserted at the end of this week once editing is completed.
Note on G22: Apelon: 6/19 problems found with insertion. Corrections made.
Note on G23: Apelon: 7/17 source will be inserted after the export of Meta2006_05D.
Note on G24: Apelon: 7/17 source will be inserted after the export of Meta2006_05D.
Note on G29: quans: 6/20/07 Wait to hear from NCI before inserting. 7/9/07 Per Sherri, we'll export the db again before inserting PDQ.
Note on G30: quans: 8/27 Wait until editing cycle is complete before inserting CBO.
Note on G35: 4/10 MTH attributes inserted and SNOMED concepts assembled
Note on G37: squan: 2/3 Real insertion of Part I started. 2/5 Part I complete. 2/8 Real insertion of Part II started.l 2/12 Part II complete. Part III will be inserted when editing of Part II is finished. 2/16 Part III real insertion started. 2/21 Part III insertion complete and review underway.
Note on G38: squan: 4/9/07 will insert all 3 parts before returning db. Est. completion is Wed., 4/11. 4/12/07 Part I insertion and review complete. 4/14/07 Part II insertion complete and Part III in progress 4/16/07 Part III complete and under review.
Note on G39: quans: 5/25/07 Wait until after export to do real insertion. 6/11/07 Part I insertion complete. 6/13/07 Part II insertion completed. 6/18/07 Part III insertion completed.
Note on G41: quans: 1/10/08 Part I complete. 1/14/08 Part II complete. 1/17/08 Insertion complete but there are count discrepencies with what was in the test insertion.
Note on G45: 2/9/06 Noticed no NCI definitions included in build. Apelon buillt new condef.dat file and ftp'd to NCI so they could update their files.
Note on H3: squan: 3/5/07 editing should be completed by this Friday.
Note on H15: quans: 3/31 Editing should be complete by the end of the week.
Note on H16: quans: 4/7 Editing still in progress. Expect to be finished next week. 4/14 Editing should be complete by tomorrow.
Note on H22: Apelon: 6/26 Difficulty in editing b/c there is nothing to indicate which Sys are connected to which PTs. To resolve, Apelon will recreate a classes_atoms.src file and insert scui and saui codes. 6/27 scui and saui codes updated.
Note on H23: Apelon: 8/14 being edited.
Note on H24: Apelon: 8/14 being edited.
Note on H41: quans: 1/28 Expect editing to be completed in 2-3 weeks.
Note on I24: squan: Spanish terms are not currently being included because of a problem Metaphrase has handling foreign language terms.

## MEME
| Priority | Completion Date | Progress Notes
Maintenance Work
Export preparations and DB cleanup | High | 2008-04-16 | Preparations for 200802 export.
MID Validation & Monster QA | High | 2008-04-21 | Next weekly run, completed for 4/14/2008
Documentation |  |  |  | 0
Work on Wiki | Med | 2008-04-17 | Updated wiki sections on code update and export processes
to more accurately capture dependencies and steps involved.
Editing Support |  |  | Using to train JFW on process.
Miscellaneous
Update to latest NLM code | Med | 2008-04-17 | Code updated to NLM revision 1009 (code changes as of 04/17/2008)
Note on E3: Brian Carlsen: Estimated
Note on E4: Brian Carlsen: Estimated

## Meta Releases
| META2007_12E | META2007_10D | META2007_09D | META2007_07C | META2007_06D | META2007_05E | META2007_03D | META2007_02C | META2007_01D
UMLS Meta base | MTH2007AB | MTH2007AA | MTH2007AA | MTH2006AD | MTH2006AD | MTH2006AD | MTH2006AC | MTH2006AB | MTH2006AB
NCI Thesaurus version | NCI2007_12E | NCI2007_10D | NCI2007_09D | NCI2007_07C | NCI2007_06D | NCI2007_05E | NCI2007_03D | NCI2007_02C | NCI2007_01D
Local Sources* | BioC_0712E | BioC_0710D | BioC_0709D | BioC_0707C | BioC_0706D | BioC_0705E | BioC_0703D | BioC_0702C | BioC_0701D
| CBO2007_06 | CBO2007_06 | CBO2007_06 | CBO2007_06 | CBO2006_03 | CBO2006_03 | CBO2006_03 | CBO2006_03 | CBO2006_03
| CDC_0712E | CDC_0710D | CDC_0709D | CDC_0707C | CDC_0706D | CDC_0705E | CDC_0703D | CDC_0702C | CDC_0701D
| CDISC_0712E | CDISC_0710D | CDISC_0709D | CDISC_0707C | CDISC_0706D | CDISC_0705E | CDISC_0703D | CDISC_0702C | CDISC_0701D
| COH_0712E | COH_0710D | CRCH_0709D | CRCH_0707C | CRCH_0706D | CTCAE_0705E | CTCAE_0703D | CTCAE_0702C | CTCAE_0701D
| CRCH_0712E | CRCH_0710D | CTCAE_0709D | CTCAE_0707C | CTCAE_0706D | CTEP04 | CTEP04 | CTEP04 | CTEP04
| CTCAE_0712E | CTCAE_0710D | CTEP04 | CTEP04 | CTEP04 | DCP_0705E | DCP_0703D | DCP_0702C | DCP_0701D
| CTEP04 | CTEP04 | DCP_0709D | DCP_0707C | DCP_0706D | DTP_0705E | DTP_0703D | DTP_0702C | DTP_0701D
| DCP_0712E | DCP_0710D | DICOM_0709D | DTP_0707C | DTP_0706D | ELC2001 | ELC2001 | ELC2001 | ELC2001
| DICOM_0712E | DICOM_0710D | DTP_0709D | ELC2001 | ELC2001 | FDA_0705E | FDA_0703D | FDA_0702C | FDA_0701D
| DTP_0712E | DTP_07010D | ELC2001 | FDA_0707C | FDA_0706D | ICDO3 | ICDO3 | ICDO3 | ICDO3
| ELC2001 | ELC2001 | FDA_0709D | ICDO3 | ICDO3 | JAX_0705E | JAX_0703D | JAX_0702C | JAX_0701D
| FDA_0712E | FDA_0710D | ICDO3 | ICH_0707C | ICH_0706D | KEGG_0705E | KEGG_0703D | KEGG_0702C | KEGG_0701D
| ICDO3 | ICDO3 | ICH_0709D | JAX_0707C | JAX_0706D | MDBCAC2005_12 | MDBCAC2005_12 | MDBCAC2005_12 | MDBCAC2005_12
| ICH_0712E | ICH_0710D | JAX_0709D | KEGG_0707C | KEGG_0706D | MDR90 | MDR90 | MDR90
| JAX_0712E | JAX_0710D | KEGG_0709D | MDBCAC2005_12 | MDBCAC2005_12 | MGED131 | MGED131 | MGED131 | MDR90
| KEGG_0712E | KEGG_0710D | MDBCAC2005_12 | MDR90 | MDR90 | NCI-CTCAEv3 (SRC atoms only) | NCI-CTCAEv3 (SRC atoms only) | NCI-CTCAEv3 (SRC atoms only) | NCI-CTCAEv3 (SRC atoms only)
| MDBCAC2005_12 | MDBCAC2005_12 | MDR90 | MGED131 | MGED131 | NCI-GLOSS_0705E | NCI-GLOSS_0703D | NCI-GLOSS_0702C | NCI-GLOSS_0701D
| MDR90 | MDR90 | MGED131 | NCI-CTCAEv3 (SRC atoms only) | NCI-CTCAEv3 (SRC atoms only) | NCI2007_05E | NCI2007_03D | NCI2007_02C | NCI2007_01D
| MGED131 | MGED131 | NCI-CTCAEv3 (SRC atoms only) | NCI-GLOSS_0707C | NCI-GLOSS_0706D | PDQ2006_12 | PDQ2006_12 | PDQ2006_12 | PDQ2006_12
| NCI-CTCAEv3 (SRC atoms only) | NCI-CTCAEv3 (SRC atoms only) | NCI-GLOSS_0709D | NCI-HL7_0707C | NCI-HL7_0706D | PMA2007 | PMA2007 | PMA2007 | PMA2007
| NCI-GLOSS_0712E | NCI-GLOSS_0710D | NCI-HL7_0709D | NCI2007_07C | NCI2007_06D | RENI_0705E | RENI_0703D | RENI_0702C | RENI_0701D
| NCI-HL7_0712E | NCI-HL7_0710D | NCI2007_09D | PDQ2007_05 | PDQ2007_05
| NCI2007_12E | NCI2007_10D | PDQ2007_05 | PMA2007 | PMA2007
| PDQ2007_11 | PDQ2007_11 | PMA2007 | RENI_0707C | RENI_0706D
| PMA2007 | PMA2007 | RENI_0709D | UCUM_0707C | UCUM_0706D
| RENI_0712E | RENI_0710D | UCUM_0709D
| UCUM_0712E | UCUM_0710D
Special Comments
*new/updated sources highlighted

## Holidays
Federal Holidays
2008
2008-01-01 | LM holiday
2008-01-21
2008-02-18
2008-05-26 | LM holiday
2008-07-04 | LM holiday
2008-09-01 | LM holiday
2008-10-12
2008-11-11
2008-11-27 | LM holiday
2008-11-28 | LM holiday
2008-12-25 | LM holiday