Ministry of Regional Development Authorities

COAST DEVELOPMENT AUTHORITY

P.O. BOX 1322

MOMBASA

Contact Person: The Managing Director

Tel. +254 41 224406, Fax +254 41 224411

Email address:

cda@africaonline.co.ke (Main Office)

cmscsec@africaonline.co.ke (KCMP Office)

Kenya Coastal Management Program (KCMP)

Year 1 Performance Report

2003-04 F/Y Annual Work-Plan

Covering 01Sept 2003 – 30 June 2004

Prepared for the United States Agency for International Development (USAID) Mission to Kenya under Contract / Grant Number 615-005

FIRST DRAFT

The KCMP is a partnership between USAID/Kenya and the

Coast Development Authority (CDA- Kenya)

September 2004

PREFACE

The Kenya Coastal Management Program (KCMP) is a partnership between the Coast Development Authority (CDA) and the United States Agency for International Development (USAID/Kenya). The goal of KCMP is to improve natural coastal resources management in targeted bio-diverse areas by and for the stakeholders in line with the USAID’s Strategic Objective 5 (SO5) and the vision and mission of CDA. The main performance indicators are Land use change in target areas (ha) and the number of stakeholders benefiting from involvement in improved Integrated Coastal Management (ICM).

In Year 1 of KCMP activities, KCMP worked with community members from Jomo Kenyatta Public Beach (JKPB), Diani Chale Management Area (DCMA) and Shimoni-Vanga Area. The initiatives undertaken include promotion of Rain-water Harvesting (RWH) technology, improving access to the beach and other marine resources and empowering the local communities to improve conservation and management of the natural resources while increasing benefits to communities through establishment of Shimoni –Vanga Locally Managed Marine Area (LMMA).

The above KCMP activities contributed to the Program’s Intermediate Results (IRs) corresponding to SO5 IR5.1; 5.1.1; 5.1.2; 5.1.3; 5.1.4; 5.1.5; 5.4; 5.4.1 and 5.4.2. A Program Management Team (PMT) consisting of technical officers representing the respective institutions was responsible for the key operation of the program and for attaining the desired results. This was done against some critical assumptions, successes and challenges and demonstrates how the ICM approach can improve natural coastal resources management in targeted biodiverse areas by and for stakeholders to combat poverty and create wealth.

CDA worked with all institutional members or partners who have either a comparative advantage on particular issues or the legal mandate to perform the same. Institutional members of the ICAM secretariat listed in Appendix B were directly involved. Pact-Kenya, an NGO, was contracted to provide Capacity building (Organizational Development and Enterprise Development) to the CBOs working with CDA.

| Name of the Program Leader: | Wainaina Mburu | Date Submitted: | October 2004 |
| --- | --- | --- | --- |
| Role in Program: | Program Officer/Coordinator |  |  |
| Name of Grantee: | Coast Development Authority | KCMP Work-plan: | 2003/04 |

LIST OF ACCRONYMS

| CB | Community Based |
| --- | --- |
| CBNRM | Community Based Natural Resource Management |
| CBO | Community Based Organization |
| CDA | Coast Development Authority |
| CORE | Conservation of Resources through Enterprise |
| CRC | Coastal Resources Centre |
| DCMA | Diani-Chale Management Area |
| DCMC | Diani-Chale Management Committee |
| DCMT | Diani-Chale Management Trust |
| DDC | District Development Committee |
| EEZ | Exclusive Economic Zone |
| EIA | Environmental Impact Assessment |
| FAO | Food and Agriculture Organization |
| FiD FD | Fisheries Department Forestry Department |
| FORREMS | Forest Rangeland Rehabilitation Environment & Management Strengthening |
| GIS | Geographical Information System |
| ICAM | Integrated Coastal Area Management |
| ICM | Integrated Coastal Management |
| INRM | Integrated Natural Resource Management |
| IR | Intermediate Result |
| IUCN | World Conservation Union |
| IWRM | Integrated Water Resources Management |
| JKPB | Jomo Kenyatta Public Beach |
| JKPBSHG | Jomo Kenyatta Public Beach Self Help Group |
| KAHC | Kenya Association of Hotel-keepers and Caterers |
| KCMI | Kenya Coastal Management Initiative |
| KCMP KEFRI | Kenya Coastal Management Program Kenya Forestry Research Institute |
| KMF | Kenya Marine Forum |
| KMFRI | Kenya Marine and Fisheries Research Institute |
| KWS | Kenya Wildlife Service |
| LMMA | Locally Managed Marine Areas |
| LUP | Land Use Planning |
| M & E | Monitoring and Evaluation |
| MCM | Municipal Council of Mombasa |
| MoU NBS | Memorandum of Understanding Nyali-Bamburi-Shanzu |
| NEMA | National Environment Management Authority |
| NGO | Non-Governmental Organisation |
| NMK | National Museums of Kenya |
| NRM | Natural Resources Management |
| OCA | Organizational Capacity Assessment |
| PMP | Performance Monitoring Plan |
| PRA | Participatory Rural Appraisal |
| SO5 SVA | Strategic Objective 5 Shimoni-Vanga area |
| TD | Tourism Department |
| TOR | Terms of Reference |
| TTF | Tourism Trust Fund |
| UNDP | United Nations Development Program |
| UNEP | United Nations Environment Program |
| URI | University of Rhode Island |
| USAID | United States Agency for International Development |
| WRM | Water Resources Management |
| WSS | Water Supply and Sanitation |

TABLE OF CONTENTS

1.0	INTRODUCTION	1

1.1	Background Information	1

1.2	Site-Specific Areas	1

1.3	Institutions involved in the implementation of KCMP	2

1.4	Anticipated Project Results	3

1.5	Program Monitoring	3

2.0	PERFORMANCE RESULTS SUMMARY	4

2.1	Key Results/Achievement	4

2.2	Challenges	4

2.3	Opportunities/prospects	5

3.0	DETAILED PERFORMANCE INDICATORS AND DATA REPORT	7

3.1	Indicator # 1: Land use change in target areas (ha)	7

3.2	Indicator # 2: Number of Stakeholders benefiting from involvement in Improved ICM	7

3.3	Indicator Number 3: Number of ICM initiatives successfully implemented in target areas	8

3.4	Indicator Number 4: Number of Conservation Tools/Technologies in use by targeted stakeholders	9

3.5	Indicator Number 5: Number of integrated ICM plans implemented	11

3.6	Indicator Number 6: Number of local decision made based on monitoring and analysis	11

3.7	Indicator Number 7:  Financial benefits to communities from nature – focused business	12

3.8	Indicator Number 8: Number of Stakeholders aware of incentives for ICM	13

3.9	Indicator Number 12: Capacity of constituency groups in advocacy (index)	14

3.10	Indicator Number 13: Organizational Capacity of targeted constituency groups (index)	14

4.0	RESULTS BY FOCAL AREA	16

4.1	Jomo Kenyatta Public Beach (JKPB)	16

4.2	Diani-Chale Management Area (DCMA)	16

4.3	Shimoni / Vanga Area (in collaboration with CORE program)	17

4.4	Water quality monitoring in Diani-Shanzu area	17

4.5	Integrated Water Resources Management (IWRM)	17

4.6	Progress Towards IR5.1 and IR5.4	17

APPENDIX A: KENYA COASTAL MANAGEMENT PROGRAM (KCMP) ORGANIZATIONAL CHART	23

APPENDIX B: INTEGRATED COASTAL AREA MANAGEMENT (ICAM) INSTITUTIONAL MEMBERS	24

Figure 1: Site Specific ICAM activities along the Kenya coast	2

Table 1: KCMP Year 1 Performance Monitoring Indicators, Targets and Output	6

Table 2: Hectarage of Land Use in Target Areas	7

Table 3: Number of stakeholders benefiting from involvement in improved ICM	8

Table 4: Employment and Income data for JKPB	13

Table 5: Number of stakeholders aware of incentives for ICM	13

Table 6: KCMP Year 1 Summary of Progress in Achieving Intermediate Results (IRs)	18

INTRODUCTION

Background Information

Kenya Coastal Management Program (KCMP) is a partnership between CDA and USAID/Kenya. The Partnership is founded on an assessment of CDA’s Integrated Coastal Area Management (ICAM) activities by USAID conducted in Year 2003 that determined that these activities contribute to the overall objectives of USAID’s Improved Natural Resources Management Program. The KCMP goal of “improving natural coastal resources management in targeted bio-diverse areas by and for stakeholders” clearly supports CDA’s core functions and strategic development objectives and is in line with the USAID’s Strategic Objective 5 that seeks to improve natural resources management in targeted biodiverse areas by and for stakeholders. The Program seeks to:

- Consolidate and strengthen local ICM programs outside of marine protected areas so that tangible community benefits of ICM are demonstrated

- Expand stakeholder capacity and participation in ICM processes, and

- Contribute experience, information and a strong constituency to support and catalyze the on-going national environmental dialogue in Kenya

The primary indicators of these results are: Land use change in target areas (ha), and the Number of stakeholders benefiting from involvement in improved ICM.

Major program activities are issue driven. Issues are identified through a consensus building process where the majority of the stakeholders participate. Short and long term actions and plans are similarly developed to address the issues

Site-Specific Areas

KCMP was focussed on three site-specific areas: Jomo Kenyatta Public Beach, Diani-Chale, and Shimoni/Vanga Area (in collaboration with CORE program).

The Nyali-Bamburi-Shanzu Area (NBSA) was identified in 1994 and started as the pilot site for the ICAM Program, with the main demonstration activities being at the Jomo Kenyatta Public Beach (JKPB). Both long term and short-term demonstration activities have been done at the public beach so as to act as a “model” for other areas.

The Diani-Chale Management Area (DCMA) is the second coastal site to benefit from the ICAM Program. Stakeholders in the area were involved in a participatory manner through consultative workshops in the identification of key issues as fisheries, tourism and Kaya forests related issues. Out of this the Diani-Chale Management Committee (DCMC) was constituted and Pact Kenya has been working with the committee to develop a vision and mission and acquire skills in undertaking their roles and responsibilities as leaders for the Diani-Chale area.

Shimoni/Vanga area (SVA) is an important cultural and marine resource located in the southern most point of Kenya. The area is adjacent Kisite-Mpunguti Marine Park and Reserve, and is both a tourist attraction and contains a diversity of marine species, extensive mangrove areas, sea-grass beds and coral reefs.

In addition, some other activities were undertaken to demonstrate tangible community benefits of ICM. These are Capacity Development (Organizational and Enterprise Development), Water quality monitoring of Diani-Shanzu coastal waters, Coastal Shoreline changes Monitoring and Control, and Integrated Water Resource Management (IWRM).

Figure 1: Site Specific ICAM activities along the Kenya coast

Institutions involved in the implementation of KCMP

KCMP is being implemented by a multi-sectoral Integrated Coastal Management (ICM) Secretariat, which is based at the CDA. The members of the secretariat include representatives from the Kenya Marine and Fisheries Research Institute (KMFRI), Fisheries Department (FiD), Kenya Wildlife Services (KWS), Municipal Council of Mombasa (MCM), Tourism Department (TD), the Kenya Association of Hotel-keepers and Caterers (KAHC), Kenya Forestry Research Institute (KEFRI), Kenya Ports Authority (KPA), Forest Department (FD), Department of Water (WD), National Museums of Kenya (NMK), National Environmental Management Authority (NEMA). Plans are underway to increase institutional membership of the Secretariat so as to include Non Governmental Organisations (NGOs), other research institutions and the private sector.

Anticipated Project Results

- Physical improvement of infrastructure for integrated beach management aimed at making JKPB a ‘model public beach’

- Development of business fishing enterprises of artisanal fishermen (JKPB and DCMA) through improved fish catches, handling, storage and marketing while encouraging sustainable utilisation of the coastal and marine resources.

- Improved access to the beach and other marine resources through securing of fish landing sites and opening up of beach access routes.

- Minimised conflicts between hoteliers and beach operators (JKPB) and improved business opportunities of beach operators through establishment of a centralised market centre.

- Enhanced capacity of local institutions for advocacy of a national ICM policy

- Establishment of a functional coastal and marine information database (coastal processes, water quality, fisheries etc).

- Action strategy for key coastal management issues (e.g. IWRM) developed

- Capacity of coastal managers and local communities on ICM enhanced

- An appropriate Performance Monitoring Plan to monitor, evaluate and report the impacts of the various coastal activities established.

Program Monitoring

A three-tier Program management structure has been set up. It consists of a Program Steering Committee, Program Management Team, and a Program Implementation Team.

The Program Steering Committee (PSC) is made up of Institutions/Departments Directors and its role is to provide overall guidance and leadership. The Program Management Team (PMT) is the organ responsible for the key operation of the program while the Program Implementation Team (PIT) is the team responsible for the direct implementation of the program. A  small Monitoring and Evaluation subcommittee is in place to carry out regular  M & E.

PERFORMANCE RESULTS SUMMARY

Key Results/Achievement

During the 2003/2004 financial period, KCMP worked with community members from Jomo Kenyatta Public Beach (JKPB), Diani Chale Management Area (DCMA) and Shimoni-Vanga Area. The initiatives undertaken include promotion of Rain Water Harvesting (RWH) technology, improving access to the beach and other marine resources and empowering the local communities to improve conservation and management of the natural resources while increasing benefits to communities through establishment of Shimoni –Vanga Locally Managed Marine Area (LMMA).

Inaccessibility to the beach and other marine resources has hampered efforts by the community members that are geared towards addressing the socio-economic and conservation issues directly targeting use of marine and coastal resources in the area.  In an effort to improve the situation along the Kenyan coastline, KCMP has enabled the fishing community and the public at large to access the beach with ease by opening up the beach access leading to JKPB and Mwaepe fish landing site (DCMA) and initiating the process of acquiring land documentation.

In order to promote an integrated approach to address the various water and sanitation related issues, an Integrated Water Resource Management (IWRM) Working Group was initiated to provide a coordinated approach in the management of water and sanitation sector. Under the coordination of the group, roof catchment has been demonstrated as one method of Rain Water Harvesting (RWH) in selected sites. Nine (9) new RWH tanks (130,000 lts) were constructed from various local materials in addition to the 23 tanks (267,000 lts) constructed earlier, 20 masons trained on RWH skills and technology, 40 masons given on-the-job training and awareness created among the beneficiaries on RWH.

KCMP worked in Shimoni-Vanga in collaboration with Pact CORE. Zonal projects steering committees were established for 9 Locally Managed Marine Areas (LMMA) zones and Projects capital estimates and action plans completed for those zones. GIS resource maps were developed for the LMMA zones and linkages for technical support for the identified LMMA project were established with stakeholders (GoK agencies, NGOs and Privates sector). The Shimoni – Vanga  LMMA NRM Plan was finalized.

Challenges

In the implementation of the program in the three project sites, the following challenges were faced:

- Finding an appropriate entry level for artisanal fishermen into commercial fishing enterprise given that majority of the artisanal fishermen are aged and illiterate.

- Finding the appropriate technology level for the artisanal fishermen as they graduate to commercial fishing. The artisanal fishermen are used to their traditional ways of fishing and therefore need to be upgraded to the next level of fishing gradually.

- The frequent changes in the political and management office at Mombasa Municipal Council has adversely affected the formation of a responsible Management Trust and  implementation of the JKPB development plan therefore making it difficult to maintain the Private sector commitment and investment.

- Development of JKPB has attracted interests from various interest groups making it quite challenging to satisfactorily accommodate them.

- Engaging the hoteliers in maintaining acceptable sewage and waste water management practices based on the water quality assessment results.

- Meeting increasing demand for RWH tanks as more community members now appreciate the use of RWH technology.

- The long legal process of repossessing land from the illegal occupants and obtaining legal land documentation.

- The demands of the Program, that requires extra commitment for timely implementation, has put pressure on the implementing officers as they are also expected to implement their individual work plans in their respective institutions. This, coupled with lack of incentives in the Program, has resulted in low team morale as the officers give priority to other programs that offer incentives.

- Delay in disbursement of activity funds resulting to time constraints and some activities left pending

Opportunities/prospects

In the program sites, there is an opportunity for:

- The mangrove taskforce formed during the workshop coming up with a draft National Policy for mangroves.

- New business enterprises from the developments at JKPB and Mwaepe.

- Improving the income earnings of the artisanal fishermen though provision of appropriate fishing gears/fishing crafts.

- Conducting on-job training of the artisanal fishermen on gear technology and craft handling using the new boats.

- Expanding the RWH activity to cover a wider area to help alleviate the water shortage problem.

- Using the RWH activity to sensitize communities on HIV/AIDs and health issues.

Learning from experiences of our neighboring coastal stakeholders which have policies on mangroves and ICM e.g Tanzania.

Table 1: KCMP Year 1 Performance Monitoring Indicators, Targets and Output

| SO5 Statement: Improved natural resources management in targeted biodiverse areas by and for stakeholders | KCMP Goal: Improving natural coastal resources management in targeted biodiverse areas by and for stakeholders | Performance Monitoring Targets |
| --- | --- | --- |
| SO5 Intermediate Results (IR) | KCMP Intermediate Results (IR) | Year | Target | Output |
| Indicator#1: Land use change in target areas (ha) | Indicator #1: Land use change in target areas (ha) | 2004 | 10 ha | 3.7 +Pact |
| Indicator #2: Number of stakeholders benefiting from involvement in improved NRM | Indicator #2 : Number of stakeholders benefiting from involvement in improved ICM | 2004 | 1,600 / 140,000 | 5775/ 14,2540 |
| IR5.1 – Site Specific Initiatives For NRM Implemented Outside Protected Areas Indicator #3: Number of NRM initiatives successfully implemented in target areas | KCMP IR5.1 –Models for Integrated Coastal Resource Management in Partnership with Public & Private Stakeholders Implemented Indicator #3: Number of ICM initiatives successfully implemented in target areas | 2004 | 5 | 4 |
| IR5.1.1 – Appropriate NRM Tools and Technologies Adopted Indicator #4: Number of conservation tools/technologies in use by targeted stakeholders | KCMP IR5.1.1 – Appropriate tools and technology for ICM adopted by Public & private stakeholders Indicator #4: Number of conservation tools/technologies in use by targeted stakeholders | 2004 | 8 | 14 |
| IR5.1.2 – Integrated Community NRM Plans Established Indicator #5: Number of integrated NRM plans implemented | KCMP IR5.1.2 – Integrated development plans for 3 ICM sites implemented Indicator #5: Number of ICM plans implemented | 2004 | 3 | 3 |
| IR5.1.3 – Improved Local Decision-Making Based on Monitoring and Analysis Indicator #6: Functionality of databases available to targeted local decision-makers | KCMP IR5.1.3 – Improved Coastal Management decision-making based on improved disseminated information Indicator #6: Number of local decisions made based on monitoring and analysis | 2004 | 3 | 0 |
| IR5.1.4 – Nature-Focused Business Practices Improved Indicator #7: Financial benefits to communities from nature-focused businesses | KCMP IR5.1.4 – Small and micro nature-focused business practices improved Indicator #7: Financial benefits to communities from nature-focused businesses | 2004 | Ksh. 0.5 Million | Ksh. 0.3 Million |
| IR5.1.5 – Awareness of Incentives For NRM Increased Indicator #8: Stakeholder awareness of incentives for NRM | KCMP IR5.1.5 – Awareness of incentives for ICM increased Indicator #8: Number of stakeholder aware of incentives for ICM | 2004 | 1,600 | 1,855 |
| IR5.4 – Environmental policy and legislative reform advanced Indicator #12: Selected environmental policies and legislations advanced | KCMP IR5.4 – Advocacy for Integrated Coastal Management Policy Advanced Indicator #12: Integrated Coastal Management Policy advocacy advanced | 2004 | 1.5 | 3.0 |
| IR5.4.2 – Constituencies to support improved NRM strengthened Indicator #13: Organizational development index of targeted CBOs | KCMP IR5.4.2 – Constituencies for ICM Advocacy established Indicator #13: Organizational Capacity of targeted constituency groups | 2004 | 1.5 | 3.0 |

DETAILED PERFORMANCE INDICATORS AND DATA REPORT

Indicator # 1: Land use change in target areas (ha)

Definition: Land which is purposefully dedicated to improved ICM or open space placed under site-specific ICM programs or ICM plans through accepted integrated development plans.

During the financial year 2003/4, KCMP focused its activities on 3 specific ICM sites namely: Jomo Kenyatta Public Beach (JKPB) in the north coast, Diani-Chale Management Area (Mwaepe fish landing site) and Shimoni-Vanga area in the south coast.

Table 2: Hectarage of Land Use in Target Areas

| ICM Site | Size (ha) |
| --- | --- |
| Jomo Kenyatta Public Beach | 3.4 |
| Mwaepe fish landing site | 0.3 |
| Shimoni-Vanga area | 155 (Reported under CORE) |
| Total | 158.7 |

Two (2) JKPB stakeholders’ consultative workshops were conducted whereby the JKPB ICM Development Plan was unanimously endorsed for implementation. Mwaepe fish landing site is one of the 12 fish landing sites that were identified for repossession in the south coast. As a result, KCMP through Fisheries Department and DCMT managed to secure it for implementing ICM activities. The landing site currently encompasses a slipway, model fish depot, fishermen meeting banda and improved sanitation system.

The Shimoni – Vanga  LMMA NRM Plan was finalized and GIS resource maps were developed for the 9 LMMA zones covering a total area of 155 hectares.

Indicator # 2: Number of Stakeholders benefiting from involvement in Improved ICM

During the reporting period, KCMP received adequate representation from government institutions and private sector in planning of ICM activities. The ultimate goal of KCMP is to involve as many stakeholders as possible in the ICM process. The stakeholders who benefited from involvement in the ICM were:

Table 3: Number of stakeholders benefiting from involvement in improved ICM

| Stakeholder | Direct benefit | Indirect benefit |
| --- | --- | --- |
| DCMT | 30 (24M, 6F) | _ |
| JKPB Groups | 65 (54M, 11F) | _ |
| ICAM Secretariat | 32 (22M, 10F) | _ |
| Water activity beneficiaries | 5,643 | 8,590 |
| Students | 5 (4M, 1F) | 150 |
| JKPB | _ | 133,800 |
| Total | 5,775 | 142,540 |

- Direct Benefit from Involvement in ICM

A total of 5,775 individuals (5,028 women and 747 men) directly benefited from involvement in ICM through training, field visits, and workshops participation. These individuals were mainly from local community groups (DCMT, JKPB and RWH beneficiaries), members of the ICAM Secretariat, and university students on attachment.

- Indirect Benefit from Involvement in ICM

A total of 142,540 individuals indirectly benefited from involvement in ICM.  These were stakeholders mainly from beneficiaries of the water activity and JKPB. The high number of JKPB stakeholders was attributed to the many visitors at the Public Beach especially during busy days and public holidays, due to improved  beach infrastructure. On the other hand, the water activity targeted public institutions such as schools, colleges, clinics, and households. Trainees of RWH systems continue to disseminate knowledge to the rest of the community members as demonstrated by the large number of enquiries for RWH tanks being received at CDA

Indicator Number 3: Number of ICM initiatives successfully implemented in target areas

A total of 4 ICM initiatives have been successfully implemented in the site specific areas as explained under the key results and achievements:

- Promotion of Rainwater Harvesting (Roof Catchment, formation of IWRM working group). A total of 32 rainwater roof catchment tanks (397,000 lts) distributed in 26 sites in public institutions, government institutions, private homes, women groups, and fish landing sites have been successfully completed. Over 5643 people have access to clean and safe water and another 8,590 are aware of the benefits of RWH. There is now an opportunity of using the RWH activity to sensitize communities on HIV/AIDs and other health issues.

- Provision of improved access to the beach resource (JKPB and Mwaepe). A number of beach access roads were identified both in the north coast and south coast. Most of these access roads were blocked and grabbed by private developers thereby hindering free access to the beach resource especially by fishermen. Through KCMP JKPB access road and Mwaepe fish landing site access road which provide access not only for the fishermen but also to the rest of the public were repossessed and opened for public use.

- Securing of Fish Landing sites (Mwaepe, JKPB): Most fish landing sites both in the north and south coast have been grabbed by private developers. This has affected the activities of the artisanal fishermen as they have to walk long distances to get access to the marine resources. Most of these private developers are hotel owners and beach resorts. KCMP through Fisheries Department organized consultative meetings with hoteliers and the local communities and identified a number of fish landing sites along the coast to be secured and repossessed by the local communities. As a result, 2 fish landing sites (JKPB and Mwaepe fish landing site) were secured.

- Setting up of locally managed marine areas (Shimoni –Vanga): Pact Kenya and the Fisheries Department have been working with community members to develop a locally managed marine area (LMMA) that would empower local communities to improve conservation and management of marine and land based natural resources while increasing benefits to communities from tourism and diverse NRM activities.

Indicator Number 4: Number of Conservation Tools/Technologies in use by targeted stakeholders

- Training

Various trainings were conducted as a conservation tool/technology to be used by the target stakeholders. These were trainings on Roof Catchment Systems Management, appropriate rainwater harvesting technologies, fish handling and processing techniques, Conflict Management with a committee in place, participatory natural resource monitoring with a monitoring committee in place i.e Diani-Chale Research and Monitoring Team, Business Planning, and a Strategic Planning for DCMT.

- Exchange Field visits

Two exchange field visits were conducted by the target stakeholders i.e DCMT and the Nyali-Bamburi-Utange fishermen group. Twenty four (24) Members of DCMT had an exchange visit to Amboseli at Kimana and Imbirikani community managed wildlife sanctuaries where they learnt community natural resource management. Thirty (30) artisanal fishers from Nyali-Bamburi-Utange visited Trans-Africa Fish Processing Plant in Mombasa where they learnt sea food handling and processing techniques.

- Business Plans

Through Pact Kenya, KCMP saw the completion of 4 business plans for JKPB stakeholders and 3 business plans for DCMT members. The 4 business plans for JKPB are business plans for fishermen, boat operators, tube renters, and beach hawkers. The business plans for DCMT are for Kaya Kinondo Ecotourism, Kaya Diani Ecotourism, and Mwaepe fishing project. These business plans are currently used by the stakeholders to source for funding.

- Management Trusts

This is an effective tool used in management of the natural resources by the stakeholders. KCMP saw the formation, registration and functioning of the Diani-Chale Management Trust (DCMT) through Pact Kenya. DCMT is fully in-charge of the management of the Diani-Chale marine and coastal resources. JKPB Management and Conservation Trust is also at a high level of being completed.

- Development of Model Fish Depots

Two (2) model fish depots have been completed i.e Mwaepe fish depot in the south coast, and JKPB fish depot in the north coast. These facilities have greatly improved fish handling by the fishermen.

- Rapid Response ICM Planning

This is a tool imparted to the Shimoni-Vanga stakeholders. This has been used by stakeholders to identify and map out their own marine resources and as a result the Shimoni – Vanga LMMA – NRM Plan was produced.

- Awareness campaigns

This has been done through support of annual marine events i.e Marine Environment Day (MED), International Coastal Cleanup (ICC), World Environment Day (WED) and World Wetlands Day (WWD). These have been used to create awareness and sensitize public on ICM issues.

- Strategic Planning

This has been imparted to stakeholders for proper planning of projects and as a result DCMT Strategic Plan was produced.

- Rainwater Harvesting and Management

This has been imparted to all beneficiaries of the water activity through formation of the IWRM group. The result is use of roof catchment system, and various types of storage systems by these beneficiaries.

- Improved Sanitation Systems

This has been imparted to the stakeholders through introduction of ecosan and septic tanks technologies at JKPB and Mwaepe respectively.

- Organizational Capacity Development (OCD) Tools and skills (DCMT and JKPB)

These have been imparted to members of DCMT and JKPB stakeholders. As a result, they are now organized into registered groups with functioning offices and secretariats.

- Surveillance and Monitoring

Through Fisheries Department, surveillance and monitoring of reef fishery was done for Tudor Creek–Nyali stretch in the north coast, and Shimoni-Majoreni stretch in the south coast. This resulted in the removal of 34 damaging fishing gears thereby reducing the number of undersize fish caught and contributing to conservation of the ecosystem.

- GIS Resource Mapping

GIS technology was used in the production of Shimoni-Vanga LMMA GIS maps. These are being used by the stakeholders to know their own marine resources and to plan for their sustainable utilization.

- Forum/network creation

A full functioning Kenya Marine Forum (KMF) is now in place registered as community trust and responsible for advocacy on marine environment issues all along the Kenyan coast. A Board of Trustees and an Executive Director are responsible for effective operation of the Forum.

Indicator Number 5: Number of integrated ICM plans implemented

In the year 2003/4 KCMP implemented key components of the following ICM plans:

- JKPB Development Plan

- Site plan for Mwaepe

- Shimoni-Vanga area

Indicator Number 6: Number of local decision made based on monitoring and analysis

Diani-Shanzu area lies within the KCMP ICM sites with the highest level of tourism activities. While tourism creates jobs and contributes to national economy, it also poses a risk to the environment through pollution from land based sources. To ensure clean beaches and marine waters for recreational purposes, KCMP through KMFRI monitored the water quality along Bamburi-Shanzu stretch. The preliminary results indicate that there is minimal pollution at the moment occurring in the area implying that the marine waters are suitable for recreational activities. The challenge to KCMP is to engage the hoteliers in maintaining acceptable sewage and waste water management practices based on the water quality assessment results.

Indicator Number 7:  Financial benefits to communities from nature – focused business

During 2004, KCMP provided business support to help communities initiate and strengthen conservation-based enterprises in two key areas:

- Training in business planning and management skills, and

- Leveraging investment and operational funds

- Business Planning and Management Skills

In 2004, KCMP conducted training for DCMT members in business planning and management skills to enable commercialization of the artisanal fishing and establish beyond the reef ring net fishing, establish a traditional and cultural exhibition center at Kaya Kinondo, and enhance Kaya Diani eco-tourism project. Consequently, three business plans were developed by the DCMT using participatory approach with the technical support from Pact Kenya. During the same period, the business plan for the Nyali-Bamburi-Utange group was revised to reflect financial changes for required fishing gears and the boat.

- Leveraging investment and operational funds

Pact Kenya sought financial support from the Tourism Trust Fund (TTF) for legitimization of the estimated 2000 beach operators along the Nyali Bamburi Shanzu, establish a market center for the operators and provide investment fund for the business plans. Among the business plans to be supported are (a) Mombasa Boat Owners Association -- to link Jomo Kenyatta Public Beach with other community based eco-tourism hot-spots such as Wasini Island, Mwaluganje Elephant Sanctuary and local Kayas; (b) Hawkers Self Help Group to enhance Jomo Kenyatta Public Beach attractions through establishment of children playing games and fun fare, and (c) support the tube renters to secure a pedal boat and life saving gears. Through the ICAM process, Pact Kenya is in intensive consultations with TTF and MoTW to provide legal and regulatory policy framework to ensure a sustainable legitimization process of the beach operators.

- Employment and Incomes

Among the four groups that KCMP was working with in 2004, there were 240 jobs sustained in fishing, boat operations, ticketing and vending tourist products at Jomo Kenyatta Public Beach. This represented 140 paid up members as at October 2004. The combined earnings for the various group enterprise activities supported were US $ 330, 600.

Table 4: Employment and Income data for JKPB

| Group | # Members | # Jobs | Annual Income (US$) in "000" |
| --- | --- | --- | --- |
|  | 2003 | 2004 | 2003 | 2004 | 2003 | 2004 |
| Jomo Kenyatta Fishing Group | 25 | 25 | 53 | 53 | 57.9 | 58.3 |
| Jomo Kenyatta Hawkers | 43 | 43 | 99 | 100 | 127.3 | 149.3 |
| Jomo Kenyatta Tube Renters | 20 | 22 | 40 | 45 | 29.6 | 46.7 |
| Jomo Kenyatta Boat Operators | 78 | 50 | 38 | 42 | 61.0 | 76.3 |
| Totals | 166 | 140 | 230 | 240 | 275.8 | 330.6 |

** Note: Employment and Income data are best estimates based on groups’ reports.

Indicator Number 8: Number of Stakeholders aware of incentives for ICM

In the year 2003/4, KCMP documented a total of 1,855 stakeholders aware of incentives for ICM as summarized in the table.

Table 5: Number of stakeholders aware of incentives for ICM

| Stakeholder | Number |
| --- | --- |
| Kenya Marine Forum | 60 |
| Annual Marine events participants | 800 |
| Beneficiaries of Rainwater Harvesting | 250 |
| Tsunza Community | 50 |
| Pwani Development Group | 20 |
| Wasini Women Group | 25 |
| Diani – Chale Community | 350 |
| JKPB Stakeholders | 300 |
| Total | 1,855 |

Indicator Number 12: Capacity of constituency groups in advocacy (index)

- Kenya Marine Forum

KMF membership reached 290 member organizations representing over 15,000 covering the entire coast line. In addition, it finalized the recruitment and setting up of a functional secretariat and embarked on community mobilization to collation of issues of concern to the community. KMF also initiated a mangrove policy advocacy process with a tour to Tanzania and also held a mangrove policy workshop and is providing leadership in Integrated Coast Area Management policy. In the year, KMF conducted the second OCA with the findings indicating that there is an improvement from 1 to 3 in the overall score placing it in the emerging stage of organizational development. In fundraising, KMF made substantial gains and has made contact with a number of donors such as UNEP, CIDA, UNDP/GEF-SGP, JICA and DANNIDA and has been incorporated into the National Committee of Eastern Africa Marine Eco-Region (EAME/WWF Programme). Problems of leadership led to internal conflicts that will likely result in a change of leadership for the group. On the positive side however the conflicts did not get out of control and did not interrupt the work of the executive director.

Indicator Number 13: Organizational Capacity of targeted constituency groups (index)

In the 2004 reporting year, KCMP supported two organizations in organizational development. These were the Jomo Kenyatta Public Beach Self Help Group (JKPBSHG) and Diani-Chale Management Trust (DCMT). JKPBSHG is made up of four business associations while the DCMT emerged from a committee mandated by stakeholders to support the management of the Diani-Chale area. It is made up of business groups (at least three businesses groups are currently receiving support), women groups, and general community members. DCMT baseline OCA score was 1.5 while JKPBSHG second OCA was 2.5 indicating an improvement from the baseline of 1.0.

- Governance, Management & operating systems

The two CBOs made significant progress in developing systems. JKPBSHG reached a consensus to elevate from a self help group to a management Trust able to mobilize resources and manage the public beach. The CBO further agreed to broaden the Trust to incorporate the wider stakeholders. To achieve this, a committee was constituted to look into the formation of the Trust. Through the committee, a draft deed is in place and Board of Trustee selection is in progress. The four member business groups have successfully conducted elections with new leadership working closely with the outgoing members. This brought a fresh impetus to the groups in terms active participation by membership in the groups activities, decision making and in demanding accountability. DCMT set up a secretariat which involved renovation of an office block, purchase of basic office furniture and hired a Program Intern from the area to assist in the administration of the secretariat and activities follow up. DCMT further enhanced participation and representation of community in the area through a membership out reach program in which the Board of Trustees organized and facilitated 10 village Barazas. The DCMT also registered fully as a Trust.

- Conflict Management

KCMP facilitated training sessions in conflict management for JKPBSHG and DCMT. The key challenge in JKPBSHG has been to inculcating democratic practice in the leadership and membership involvement in decision making process. The trainings in conflict management has enabled the CBOs members apply different strategies in addressing conflicts like mediation, arbitration and negotiation. In DCMT, the areas of conflict have been both internal and external to the group. Internal conflicts are on representation of the community in DCMT. External conflicts are largely on access and ownership of resources by the community and between institutions eg KWS on the ownership and management of the Diani Marine Reserve, some of the hoteliers on access to beach where hotel property block beach access roads and water sports operators. The DCMT developed an action plan that they will use to address conflict. One key outcome from the training is DCMT’s the willingness to negotiate with KWS to co-manage the Diani Marine Reserve.

- Natural Resources Management

DCMT finalized the resource mapping process where the six businesses were prioritized for support under KCMP. The CBO also received training in resource monitoring to ensure that the community is able to monitor the trend and those activities implemented do not adversely affect the resource base. JKPBSHG continued their weekly beach clean up program through out the year, an indication of the group’s commitment in the beach management. In partnership with the CORE program, the Shimoni/Vanga Locally Managed Marine Area (LMMA) received support to finalize the planning process and prepare budgets for interventions. These interventions include the rice and fish farming, bee keeping, extension of the board walk at the Wasini Island, crab farming, nature trails and a diving area. The BCP/CDTF has provided funds for the mangrove board walk extension at the Wasini Island, crab farming and bee keeping in Wasini, Bati and Mukwiro.

- Sustainability

DCMT developed a five year strategic plan to provide focus for the Trust in achieving its set goals. In Jomo Kenyatta Beach the long term plan for beach improvement includes facilities such as rest rooms, parking and recreation areas which once in place will provide revenue for maintenance of the beach which will be managed by the Jomo Kenyatta Public Beach Conservation and Management Trust.

RESULTS BY FOCAL AREA

Jomo Kenyatta Public Beach (JKPB)

JKPB is located to the north of Mombasa Town in the Nyali-Bamburi-Shanzu. Being a Public Beach with a multi-stakeholder interest to the marine and coastal resources, short term and long term demonstration activities have been implemented so as to act as a “model” for other areas. Through KCMP significant results have been achieved which include:

- Section of the beach access road opened up.

- JKPB Development Plan adopted by Stakeholders.

- JKPB Development Committee formed.

- JKPB Trust & Management Committee formed.

- JKPB Landscaping Committee formed.

- Acceptance by key Private-Public Tourism stakeholders to legitimize and mainstream beach activities through the Market Centre (TD and KTDC)

- The 4 member CBOs of JKPB reached a consensus for development of Trust under the name Jomo Kenyatta Public Beach Management & Conservation Trust

- A Draft Trust deed was developed and trustees proposed from Public and Private sector

- A concept to legitimize beach operators for Jomo Kenyatta beach has been developed and forwarded to TTT for funding considerations.

Diani-Chale Management Area (DCMA)

The Diani-Chale area in Msambweni Division of Kwale District is an area of great beauty, blessed with many economically valuable natural resources and numerous attractions. Mwaepe fish landing site in Diani was selected by the local community as a site specific initiative to demonstrate the ICAM process in the area using the Jomo Kenyatta Public Beach as a ‘model’. The following has been achieved:

- Rehabilitation and expansion of Mwaepe Fish Depot. A fishermen rest banda, a slip way and a toilet block (consisting of 2 toilets and 2 showers) were constructed

- Improvement of beach access road

- DCMT members trained on conflict management and a conflict resolution mechanism put in place.

- A strategic plan for DCMT was developed

- Membership outreach meetings conducted

- Completion of DCMT office

- DCMT trained in business management skills

- Three (3) business plans for Kaya Kinondo, Kaya Diani, and Mwaepe fishing project developed

Shimoni / Vanga Area (in collaboration with CORE program)

Shimoni/Vanga area is an important cultural and marine resource located in the southern most point of Kenya. The area is adjacent to Kisite-Mpunguti Marine Park and Reserve, and is both a tourist attraction and contains a diversity of marine species i.e. extensive mangrove ecosystems, sea-grass beds and coral reefs. Results achieved include:

- Zonal projects steering committees established for the 9 LMMA zones

- Finalization of  the Shimoni – Vanga  LMMA NRM Plan

- Completion of the GIS resource maps development for the Shimoni – Vanga LMMA zones

- Projects capital estimates and action plans completed for the 9 LMMA zones

- Established  linkages for technical support for the identified LMMA project with stakeholders (GoK agencies,  NGOs and Privates sector)

Water quality monitoring in Diani-Shanzu area

- Diani-Chale and Nyali Shanzu areas are among the most popular recreational areas that are frequently visited by both local and foreign tourists. Marine water and sandy beaches offer recreationists with the much needed direct contact activities such as swimming, snorkeling, diving, wind surfing and other water related sports. To assess the water quality of coastal marine water and its suitability for both direct and indirect recreational activities, a water quality monitoring program is in place. The preliminary results indicate that there is minimal pollution at the moment occurring in the area implying that the marine waters are suitable for recreational activities.

Integrated Water Resources Management (IWRM)

In order to promote an integrated approach to address the various water and sanitation related issues, the following results were achieved:

- An Integrated Water Resource Management (IWRM) Working Group was formed.

- 20 masons trained on construction of various RWH systems.

- 40 masons practically trained on site.

- Nine (9) RWH tanks (130,000 lts) constructed.

- Awareness created among the beneficiaries on RWH.

## Progress Towards IR5.1 and IR5.4

The Progress towards Intermediate Results (IR) 5.1 and 5.4 is summarized in Table 6 below.

Table 6: KCMP Year 1 Summary of Progress in Achieving Intermediate Results (IRs)

| KCMP Goal: Improving natural coastal resources management in targeted biodiverse areas by and for stakeholders |
| --- |
| Indicator #1: Land use change in target areas (ha). Indicator #2 : Number of stakeholders benefiting from involvement in improved ICM |
| KCMP Intermediate Results (IR) | Activities | Target output | Progress made | Way Forward |
| KCMP IR5.1 –Models for Integrated Coastal Resource Management in Partnership with Public & Private Stakeholders Implemented Indicator: Number of ICM initiatives successfully implemented in target areas | Jomo Kenyatta Public Beach (JKPB) Landscaping of the site Improved beach access road and parking lot | Selected priority components of the landscape plan implemented | 1 meeting with Bamburi Cement Ltd held in January 2004 and commitment obtained on murraming and grading of beach access road Relocation of 8 KWS unipots that were obstacles on a section of the beach access road Landscaping Committee established JKPB stakeholders’ consultative workshop held on 21st April 2004 2 JKPB Working Committees established i.e. JKPB Development Committee, and JKPB Management & Conservation Trust Committee and regular weekly meetings were held from May to July 2004 | Activity to be continued next phase |
|  | Establishment of a market centre (vendor kiosks) | Establishment of a market centre initiated | Several site meetings were held to discuss the market centre plan. KTDC and TTF have shown interest to develop the market centre. 3 preliminary market designs developed | Activity to be continued next phase |
|  | Improved provision of water and sanitation facilities | Improved provision and management of water and sanitation facilities | 2 additional RWH tanks constructed (36,000 lts) 3 Ecosan demonstration toilets constructed | Activity to be continued next phases |
|  | Power supply installation | 3 users connected to power supply | JKPB Self Help Groups initiated application process for power connection ( fishermen and boat operators) | Activity to be continued next phases |
|  | Establishment of an information centre | Detailed architectural plans in place Tender awarded | No progress made | Activity to commence next phase |
|  | Empowerment of artisanal fishermen to develop commercial fishing enterprise | 1 motorized boat 1 set of fishing gear Number of trainings conducted 1 study tour conducted | Tendering process for motorized boat completed 30 artisanal fishers trained on fish handling, processing techniques and marketing | Activity to be continued next phases |

| KCMP Intermediate Results (IR) | Activities | Target output | Progress made | Way Forward |
| --- | --- | --- | --- | --- |
| KCMP IR5.1 continued… | Diani-Chale Management Area (DCMA) Securing Mwaepe fish landing site/others | Certificate of lease issued for Mwaepe | Follow ups made with the Director of Fisheries and Commissioner of Lands office, letter of allotment issued. | Activity to be continued in year 2 |
|  | Development of Mwaepe fish depot | Additional 15m2 provided, Slipway in place, 1 sanitation facility constructed, Power connected to the depot, Well/tap water provided. | Open shade constructed (40m2), Slip way constructed, 1 toilet block, 1 septic tank and 2 soak pits constructed, application for power made. 1 RWH tank (10 m3) constructed | Complete power and fresh water supply to site. |
|  | Empowerment of artisanal fishermen to develop commercial fishing enterprise | 1 motorized boat, 1 set of fishing gear, Number of trainings conducted, 1 cold storage, 1 study tour conducted. | Specifications for fishing boats done Quotations floated | Activity to be continued in year 2 |
|  | Water quality monitoring of Diani coastal waters | Data on water quality (marine water and ground water) for Diani-Shanzu area available. 2 institutions strengthened | Sampling and analysis of ground and marine water along the Diani-Chale waters ongoing | To continue in Year 2 |
|  | Other KCMP Activities |  |  |  |
|  | Shimoni-Vanga Area (SVA) Establishing gaps in baseline information for Simoni-Vanga area | A report on gaps in baseline information | Study not accomplished | Activity to be done in year 2 |
|  | Finalization of Locally Managed Marine Areas (LMMAs) planning process | 9 action plans and budgets DDC approval | Action plans and budgets developed Stakeholders workshop held in preparation for the DDC Presentation to the sub-DDC | DDC approval process to continue in year 2 |
|  | Implementation of the LMMA plan | Funding for interventions (2 per zone) and linkages with 4 Gok departments | Funding not provided Linkages with KEFRI and agriculture achieved | Implementation of 2 pilot projects to start in year 2 Establishment of linkages to continue in year 2 |
|  | Fundraising for NRM interventions and nature based enterprise under the LMMA | 2 proposals, TTF and UNDP | Proposals submitted to UDNP-GEF/SGP, USAID/APS and WWF/EAME No response received yet | Intensive fundraising to continue in year 2 |
|  | Water quality monitoring of Diani coastal waters | Data on water quality (marine water) for Diani-Shanzu area available. Data on water quality (groundwater) for Kisauni available. 2 institutions strengthened | Sampling and analysis of ground and marine water along the Diani-Chale waters is ongoing | To continue in Year 2 |

| KCMP Intermediate Results (IR) | Activities | Target output | Progress made | Way Forward |
| --- | --- | --- | --- | --- |
| KCMP IR5.1 continued… | Monitoring of shoreline erosion | Monitoring mechanism in place Key area covered. | 9 areas showing critical shoreline changes were identified as monitoring points Garmin eTrex Summit GPS and its accessories) acquired to assist in data collection | To continue in Year 2 |
|  | Support of annual marine events and programs | 2 annual events. 4 programs. | 2 annual events supported (World Environment Day and Marine Environment Day) | To continue in Year 2 |
|  | Support to communities that have adopted the ICM process | 2 initial joint meetings held. Strengthen the ICM process within the target communities. | 2 initial meetings held with Tsunza Community Development Program and Pwani Community Development Organization | To continue in Year 2 |
|  | Involvement in transboundary issues | 2 meetings held Mechanism for conflict resolution in place | Not done | To continue in Year 2 |
|  | Integrated Water Resources Management | IWRM working group functioning. IWRM strategy in place. IWRM information disseminated. 8 skilled groups trained on RWH. 5 awareness meetings held. 10 RWH systems in place. 24 people trained on health aspects, management and maintenance. 2 demonstration systems in place (JKPB & Mwaepe)] | An IWRM Working Group Initiated to provide a coordinated approach in the management of water and sanitation sector. 3 seminars held for communities where 62 stakeholders were sensitized on RWH and management of the RWH systems 20 Artisans trained on appropriate RWH Technologies 40 masons trained on site Construction of nine (9) RWH storage systems of various types and sizes completed and providing communities with alternative source of clean and safe drinking water. | To continue in Year 2 |
| KCMP IR5.1.1 – Appropriate tools and technology for ICM adopted by Public & private stakeholders Indicator: Number of conservation tools/technologies in use by targeted stakeholders | Jomo Kenyatta Public Beach (JKPB) |  |  |  |
|  | Improved water and sanitation facilities Market centre Information centre Commercial fishing ventures Organisational Capacity Assessment Training (OCAT) Conflict management Advocacy Cost recovery mechanism Protocol for conflict management Integrated water resources management | Improved provision and management of water and sanitation facilities Market centre in place Information centre in place Commercial fishing ventures started OCA score Conflict management skills Advocacy strategy Cost recovery mechanism for the parking and rest rooms Conflict management mechanism IWRMG in place | 2 additional RWH tanks and 2 Ecosan toilets constructed. Not done Not done Not done OCA not done Conflict management training conducted for DCMT and JKPBSHG Advocacy activities not accomplished Not accomplished, pegged on MCM approval of the request submitted Conflict management training conducted | Continue in year 2 |

| KCMP Intermediate Results (IR) | Activities | Target output | Progress made | Way Forward |
| --- | --- | --- | --- | --- |
| KCMP IR5.1.1 continued… | Diani-Chale Management Area (DCMA) |  |  |  |
|  | Improved water and sanitation Commercial fishing Rapid response to NRM Planning | 1 sanitation facility constructed, Well/tap water provided Commercial fishing ventures started 1 Rapid Response NRM plan | 1 toilet block, 1 septic tank, 2 soak pits and 1 RWH tank constructed Not done Resource mapping accomplished, priority project selected and 3 business plans developed | Activity to be continued in year 2 To do in year 2 GIS mapping to continue in year 2 Mentoring Resource monitoring to continue in |
|  | Other LMMA GIS maps Coastal erosion data ICAM resource centre Kenya Marine Forum | 1 LMMA plan GIS mapping for the LMMA Baseline data available Functional resource centre in place 1 CBO in place | Participatory planning complete, budget and action plans in place awaiting DDC approval Process complete and GIS maps in place Data collection initiated 1 computer and multimedia projector purchased See section on KMF below | DDC approval to continue being sought in year 2 Continue in year 2 Networking of computers to be done in year 2 Support to KMF to continue in year 2 |
| KCMP IR5.1.2 – Integrated development plans for 3 ICM sites implemented Indicator: Number of ICM plans implemented | Jomo Kenyatta Public Beach Diani-Chale Community NRM Plans LMMA – Shimoni | ‘Model’ public beach ‘Model’ fish landing site 1 NRM plan (DCMA Rapid Response NRM plan) 1 plan | Various activities ongoing Construction of fish landing site completed Resource mapping accomplished, priority project selected and business plans developed Plan complete, awaiting DDC approval and implementation | Complete in year 2 Complete in year 2 GIS mapping to continue in year 2 DDC approval to continue being sought and Implementation to continue in year 2 |

| KCMP Intermediate Results (IR) | Activities | Target output | Progress made | Way Forward |
| --- | --- | --- | --- | --- |
| KCMP IR5.1.3 – Improved Coastal Management decision-making based on improved disseminated information Indicator: Number of local decisions made based on monitoring and analysis | JKPB Surveillance and monitoring of reef fishery Water quality monitoring Integrated water resources management Monitoring of coastal shoreline erosion Diani Water quality monitoring Integrated water resources management Monitoring of coastal shoreline erosion | 3 ICM decisions made based on improved disseminated information | 9 sets of damaging gears, including fish nets and traditional fish traps, were removed. Activities are ongoing | Continue in year 2 |
| KCMP IR5.1.4 – Small and micro nature-focused business practices improved Indicator: Financial benefits to communities from nature-focused businesses | JKPB Water sport, Boat operation, Boating, Business promotion, Fisheries activities, Capacity building Diani Nature practice, Business promotion, Fisheries activities, Capacity building | 4 businesses with improved income (25%) 6 businesses plans developed 3 business deals established 3 businesses effectively implementing their plan | Business plans for fishermen, boat operators, vendors and tube renter developed Mentoring for fishermen and boat operators in implementation initiated 6 businesses identified and 3 prioritized 3 Business plans developed 1 deal under negotiation for village tours Training and mentoring ongoing | Investment fund and implementation to be done in year 2 Enterprise capacity development to continue in year 2 Business plans for other 3 to continue in year 2 Business partnership to be promoted in year 2 |
| KCMP IR5.1.5 – Awareness of incentives for ICM increased Indicator: Number of stakeholder aware of incentives for ICM | JKPB and Diani Chale activities | 1600 people aware of the ICM incentives | Awareness campaigns on ICM done during annual events (Marine Environment Day, World Environment Day) | Activities to continue year 2 and survey to be conducted to establish |
| KCMP IR5.4 – Advocacy for Integrated Coastal Management Policy Strengthened Indicator: Capacity of constituency groups in advocacy (index) | Enhance the capacity of KMF and integrate its activities in the ICM process Liasing with NEMA to ensure issues are addressed at National level Conferences/seminars on National coastal issues | Integration of KMF in ICM process 2 policy issue meetings. Consensus on coastal policy issues reached 1 National workshop held | 1 Consultative workshop on mangrove policy held. Task force on mangrove formed Forest Bill and Policy mainstreamed to reflect mangrove issues | Prioritized in year 2 |
| KCMP IR5.4.1 – Constituencies for ICM Advocacy established Indicator: Organizational Capacity of targeted constituency groups | Jomo Kenyatta Public Beach Self Help Group (JKPBSHG) Diani-Chale Management Trust (DCMT) KMF | Skills in advocacy | Training not conducted for both JKPB and DCMT Training and mentoring on going under the CORE program Assessment of grassroots issues complete Participation in the national Kenya Wildlife Working Group on going | Prioritized in year 2 Support to KMF in developing ICM advocacy strategy prioritized in year 2 |

## APPENDIX A: KENYA COASTAL MANAGEMENT PROGRAM (KCMP) ORGANIZATIONAL CHART

## APPENDIX B: INTEGRATED COASTAL AREA MANAGEMENT (ICAM) INSTITUTIONAL MEMBERS

| Kenya Forestry Research Institute P.O. Box 20412 00200 Nairobi Tel: 066-32891/2/3 Fax: 066-32844 Director of Water Development P.O. Box 30521 Nairobi. Tel: 020-2716103 Fax: 020-2727622 Kenya Marine Fisheries & Research Institute P.O. Box 81651 Mombasa Tel:041-475151/475152/4 Fax: 475157 Fisheries Department P.O. Box 58187-00200 Nairobi Tel: 020-3742320/749936 Fax: 020-3744530 Kenya Wildlife Service P.O. Box 40241 Nairobi Tel: 020600800/602345 Fax: 020-501752/500276 Municipal Council of Mombasa P.O. Box 90440 Mombasa. Kenya Association of Hotelkeepers P.O. Box 83378 Mombasa Or Fax: 041-5485652/405 Tel:041-5485926/7/8/9 National Museums of Kenya Museum Hill Rd. Westlands P.O. Box 40658 Nairobi Tel: 020-220058/222425 Fax: 020-3741424 | Kenya Ports Authority P.O. Box 95009 Mombasa Tel: 040-312211/221211 Fax: 0410311867 National Environment Management Authority P.O. Box 47146 Nairobi Tel: 020-609013/27 Fax: 020-608997 Forestry Department Chief Conservator of Forests P.O. Box 30521 Nairobi Tel: 020-3754904/5/6 Fax: 020-3764249 Coast Development Authority P. O. Box 1322, Mombasa Tel. 041 224406/225774 Fax. 041 224411 Department of Tourism Ministry of Information & Tourism P. O. Box 30027 Nairobi Tel: 020-313010 Tel: 041-223465 PARTNERS PactKenya P.O. Box 76390 - 00508 Nairobi Tel: 020-578271/3/4 Fax: 020-570775 |
| --- | --- |

# Text boxes

Shimoni-Vanga Area

Diani-Chale Management Area

Jomo Kenyatta Public Beach

KCMP

ICAM

Secretariat

Community Activities

Program Steering

Committee (PSC)

Program Implementation Team (PIT)

Program Management Team (PMT)

USAID

/Kenya

Managing

Director (CDA)