Statement of Work

NCI-Mouse Models of Human Cancers Consortium

Steering Committee Meeting

Bethesda, MD

January 7 – 9, 2008

Background

The NCI-Mouse Models of Human Cancers Consortium (NCI-MMHCC), Division of Cancer Biology, NCI plans a 2.5-day meeting for January 7 – 9, 2008.  The meeting will take place at the Hyatt Regency-Bethesda, 1 Bethesda Metro Center, Bethesda, MD  20814.  There will be approximately 20 invited speakers and guests (domestic travelers) for the meeting, and about 120 meeting participants at the hotel.  The invited speakers and guests will be reimbursed for their hotel accommodations, airfare, per diem, and ground transportation per Federal Travel Regulations (FTRs); per diem will be reduced by meals provided.  The meeting participants will pay their own hotel and travel expenses (no reimbursements).

The hours for the meeting at the Hyatt Regency-Bethesda are: 3:00-7:30 PM on Jan. 7th, 7:00 AM – 7:30 PM on Jan. 8th, and 7:00 AM – 1:00 PM on Jan. 9th.

STATEMENT OF WORK

Funding for this Task Order will be obligated in 2 segments:  June 2007 and November 2007.

PRE-MEETING:

Hotel

- Pay the hotel deposit for the meeting site and administer the contract with the hotel.

- Establish a room block of 75 sleeping rooms for travelers for 2 nights (Jan. 7th and 8th), 3 sleeping rooms for Jan. 6th, and 5 sleeping rooms for Jan. 9th.

- Reserve a main meeting room for 2.5 days that is sufficiently large to accommodate 120 participants; primary seating should be a U-shaped table for 50 participants with perimeter seating for about 70 attendees, with a lectern and a projection screen facing the participants.

- Reserve space for viewing 15 scientific poster boards (for 30 posters); posters will be put up after 3:00 PM on Jan. 7th, and removed by 12:00 PM on Jan. 9th.

- Provide light refreshments for the initial science and poster session from 4:30-7:30 PM on Jan. 7th for approx. 120 attendees.

- Ensure that coffee/tea/soft drinks/bottled water are available throughout 2.5 days.

- Provide continental breakfasts for Jan. 8th and Jan. 9th, morning and afternoon breaks for Jan. 8th, and a morning break on Jan. 9th for approx. 120 attendees.

- Coordinate with the Director of Sales at the Hyatt Regency Bethesda Hotel, Ms. Mireille Dizard, Direct Line: (301) 657-6406;  FAX: (301) 657-6478, mdizard@hyatt.com

- Ensure that the hotel receives appropriate Federal tax-free documentation.

Logistics

- Make direct telephone contact with speakers and their travel coordinators to ensure that they understand all travel arrangements and the extent of reimbursement.

- Solicit travel information from speakers, and develop detailed travel itineraries.

- Provide speakers with prepaid tickets, by courier or postal service, in advance of travel, if possible.

- Provide a registration website at least ten weeks prior to the meeting.

- Coordinate all pre-meeting mailings (email and/or postal service) and provide logistical and informational support for the meeting participants.

- Prepare pre-meeting and meeting packages for participants, to include an agenda, participant list, and other materials as defined by NCI-MMHCC staff; send to participants (email and/or postal service), and provide during the meeting.

- Mail meeting notices and updates to participants (email and/or postal service)

- Prepare name tags, name tents, and meeting folders, including agenda, participant list, and other duplicated materials as defined by NCI-MMHCC staff, no later than January 3, 2008

- Prepare any necessary paperwork related to the meeting as stipulated by NCI-MMHCC staff.

MEETING:

- Provide microphones for every 2-3 participants seated at the main U-shaped table.  Provide 2-3 free-standing microphones for use by participants in the perimeter seating.

- Provide a lavaliere microphone for lectern presentations.

- Provide all necessary audio-visual (AV) equipment for the meeting room (LCD projector, laptop computer, laser pointers, overhead projector).

- Provide a wireless Internet connection in the meeting room for the entire 2.5 days.

- Provide one (1) audio-visual technician.  This must be a knowledgeable audio-visual technician to be available during the 2.5 day meeting to set up and run PowerPoint presentations, using an LCD projector and laptop (PC- and MAC-compatible) computer system.  The Government’s preference is Mr. Carey Anthony Brown from C.A. Brown Enterprises, Inc.  His telephone number is (954) 501-4086; email is red97sscam@aol.com.  This is provided for information purposes only and is not considered restrictive for proposal purposes.

- Determine and pay costs for appropriate support services during the 2.5 day meeting, including 2 people at the registration desk to assist participants and register attendees.

POST-MEETING:

- Reimburse speakers for ground transportation and other travel-related expenses as permitted under Government FTRs and Government policies.

- Provide post-meeting services to include contacting all speakers to ensure that all travel and per diem costs are submitted and reimbursed; these services should extend for 3 months after the conclusion of the meeting.

- Provide meeting materials packets or information (by e-mail and/or postal service) to those meeting participants who request them, but were unable to attend the meeting.

- Provide NCI-MMHCC staff with a Word document list of all participants at the meeting and their contact information based on final registration.

- Return all unused meeting materials.

Deliverables

- Logistical information that is prepared and mailed or emailed to the participants.

- Participant name tags, name tents, meeting folders, etc., approved and prepared no less than 3 days prior to the meeting.

- Participant packages, final participant list, agenda, etc., approved and prepared no less than 3 days prior to the meeting.

- Professional Service Contract (PSC) equivalents provided to the invited speakers at the end of the meeting.