## COI-NJD-NOH-I5-RATS-WOM-WOS-DC
JULY 2009 | [7 empty] | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
COI | NJD | NOH | RATS | WoM | WoS | PDCI | Estimated Path Capacity | Day | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
C | [6 empty] | COI (N-S)
COI (S-N)
| J | [5 empty] | North of John Day
|  | H |  |  |  |  | North of Hanford
|  |  | R |  |  |  | RATS N>S
RATS S>N
|  |  |  | M |  |  | West of McNary
[5 empty] | S |  | West of Slatt
[6 empty] | D | PDCI NOB (N>S)
PDCI NOB (S>N)
[7 empty] | PDCI Power Order (N>S) | 26 Sun: 0
[7 empty] | PDCI Power Order (S>N) | 26 Sun: 0
[7 empty] | Description | Day: Util
C | [5 empty] | D | Malin: PCB 4037 including 500kV Reactor 2 (complete repairs to PCB and Reactor) 166148 COS 1-006639 | PGE | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | to 31DEC09
C | [5 empty] | D | Malin: 500kV Reactor 4 including LBD 11L4 (Installing new annunciators, actuation device and trip circuits) 192106 ……………….. COS (PAC) 1-005463 | PAC | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | to 31DEC08
C |  |  |  | M |  | D | Sacajawea: 500/115kV Bank 1 including PCB 4929 (Equipment failure, bank gassing) [Forces out Sacajawea Tap of Lower Monumental-McNary 1 500kV Line] els 173445/dls 172469/168665 COS 1-006985 | Day: BPA; 1 Wed: C 1500
C | J | H |  |  |  | D | Vantage: 500/230kV Bank 1 (Re-gasket A&C phase oil pumps and A&C phase 230kV bushings.) 210480 COS 1-009634 | BPA | [5 empty] | 0900 C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C 1800
C | [5 empty] | D | Summer Lake: PCB 4959 (Diagnostic Service) 204530 …………………………………………………………... COS 1-002046 | Day: BPA; 6 Mon: 0900 C; 7 Tue: C; 8 Wed: C; 9 Thu: C 1330
[7 empty] | Bonneville-Hood River 1 115kV Line (Complete service to Hood River PCB B-1680) els 204235/dls 205211 ……………………. COS 1-004036 | Day: BPA; 13 Mon: 0830 C; 14 Tue: C; 15 Wed: C; 16 Thu: C; 17 Fri: C 1400
C |  | H |  |  |  | D | Hanford: PCB 4089 (Routine service) 203045 ……… COS 1-003088 | Day: BPA; 13 Mon: 0800 C; 14 Tue: C 1330
[6 empty] | D | Celilo: Converters 1, 2, 3 & 4 (Station Wash) 211437 | Day: BPA; 25 Sat: 0500 1800
C | [5 empty] | D | Captain Jack-Malin 2 500kV Line (Removing bus between line drop and MOD 4988 at Captain Jack, allowing a new breaker and MOD to be installined in the bay.) 211319 ……………. COS 1-008026 | Day: BPA; 27 Mon: 0600 C; 28 Tue: C; 29 Wed: C; 30 Thu: C; 31 Fri: C 1100
C | [5 empty] | D | Allston: 500/230kV Bank 1, Station Service Bank 1 and 500/230kV Bank Spare T-1708 (Dryout and process oil on "B" phase) 210171 COS 1-009663 | Day: BPA; 27 Mon: 0700 C; 28 Tue: C; 29 Wed: C; 30 Thu: C; 31 Fri: C | to 07SEP09
C | [5 empty] | D | Big Eddy-Chemawa 1 230kV Line (Repairing insulators and conductor) els 210552/dls 212202 COS 1-008970 | Day: BPA; 27 Mon: 0730 C; 28 Tue: C; 29 Wed: C; 30 Thu: C; 31 Fri: C 1530
C | [5 empty] | D | John Day: PCB 4153 including 500kV Cap Group 1 (Routine PCB maintenance) 204021 COS 1-001868 | Day: BPA; 27 Mon: 0800 1500
C | [5 empty] | D | Sycan Compensation Group 3: 500kV Series Capacitor Group 3 including PCB 5066 (Routine Service) 204543 | Day: BPA; 27 Mon: 0900 C; 28 Tue: C; 29 Wed: C; 30 Thu: C 1300
C | [5 empty] | C | John Day: PCB 4197 (Routine PCB maintenance) 204022 [West Bus/Big Eddy 1] COS 1-001870 | Day: BPA; 28 Tue: 0800 1500
C | [6 empty] | John Day: PCB 4822 (Routine PCB maintenance) 204024 [East Bus/500/230kV Bank 1] COS 1-003085 | Day: BPA; 29 Wed: 0800 1500
C | [6 empty] | John Day: PCB 4825 (Routine PCB maintenance) 204025 [West Bus/500/230kV Bank 1] COS 1-001871 | Day: BPA; 30 Thu: 0800 1500
|  | H |  |  |  |  | Olympia-Grand Coulee 1 287kV Line (Grand Coulee transformer work in proximity to line) els 205165/dls 205179 (Line operating at 230kV) | BPA | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | to 26AUG09

## WoC-S, R-P, P-A & SoA
'JULY 2009 |  |  |  |  | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
WoC-S | RP | PA | S o A | Estimated Path Capacity | Day | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
S |  |  |  | West of Cascades - South |  | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX
| R |  |  | Raver-Paul | bar: 3 Fri
|  | P |  | Paul-Allston | bar: 3 Fri
|  |  | A | South of Allston | bar: 3 Fri
|  |  |  | Description | Day: Util
|  |  |  | Olympia-Shelton 1 115kV Line (Line upgrade) els 212018/dls 212217 COS 1-009073 | BPA | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | to 26AUG09
| R |  |  | Olympia-Grand Coulee 1 287kV Line (Grand Coulee transformer work in proximity to line) els 205165/dls 205179 (Line operating at 230kV) COS 1-009297 | BPA | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | to 26AUG09
|  |  | A | McLoughlin Tap of Mcloughlin-Sherwood-Pearl 1 230kV Line (Stringing conductor for new McLoughlin-Wilsonville 115kV Line on same tower) els 208165/dls 208212 | PGE | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | to 02OCT09
|  |  | A | Keeler-Oregon City 2 115kV Line (Change out danger poles in 7 to 19 mile) els 210633/dls 211417 COS 1-006780 | Day: BPA; 6 Mon: 0800 C; 7 Tue: C; 8 Wed: C; 9 Thu: C; 10 Fri: C 1530
| R |  |  | Olympia: 287/230kV Bank 3 (Diagnostic service) els 211625/dls 212XXX COS 1-008339 | Day: BPA; 13 Mon: 0700 C; 14 Tue: C; 15 Wed: C; 16 Thu: C; 17 Fri: C 1530
|  |  | A | St Johns-Keeler 2 115kV Line (Danger poles and cross arms) els 211579/dls 212337 COS 1-008490 | Day: BPA; 13 Mon: 0730 C; 14 Tue: C; 15 Wed: C; 16 Thu: C; 17 Fri: C; 18 Sat: C 1430
|  | P |  | Olympia-South Tacoma 1 230kV Line (Switch work and replace insulator) 212000 COS 1-009101 | Day: BPA; 13 Mon: 0800 1500; 14 Tue: 0800 1500; 15 Wed: 0800 1500; 16 Thu: 800 1500; 17 Fri: 800 1500
| R | P |  | Satsop: PCB A-607 (Mechanism service) els 211654/dls 212203 …………………………………… COS 1-008733 | Day: BPA; 13 Mon: 0730 1530
| R | P |  | Paul: PCB 4554 (Relay trip checks from Olympia relays) 204550 COS 1-001866 | Day: BPA; 14 Tue: 0800 1500
| R | P |  | Satsop: PCB A-610 (Mechanism service) els 211656/dls 212203 …………………………………… COS 1-008734 | Day: BPA; 14 Tue: 0845 1530
| R | P |  | Satsop: PCB A-613 (Mechanism service) els 211658/dls 212205 …………………………………… COS 1-008735 | Day: BPA; 15 Wed: 0845 1530
| R | P |  | Satsop: PCB A-616 (Mechanism service) els 211660/dls 212206 ………………………………….. COS 1-008736 | Day: BPA; 16 Thu: 0845 1530
| R | P |  | Satsop: PCB A-619 (Mechanism service) els 211661/dls 212208 ………………………………………….. COS 1-008737 | Day: BPA; 17 Fri: 0845 1530
|  |  | A | St Helens-Goble Section of St Helens-Allston 1 115kV Line (Danger poles) els 212176/dls 212329 COS 1-009410 | Day: BPA; 20 Mon: 0700 1900; 21 Tue: 0700 1900; 22 Wed: 0700 1900
| R |  | A | TPWR Cowlitz Tap of Chehalis-Covington 1 230kV Line (Change out wood poles at 8/3 to 8/8) 209818 COS 1-005110 | Day: BPA; 20 Mon: 0800 C; 21 Tue: C; 22 Wed: C; 23 Thu: C; 24 Fri: C; 25 Sat: C 1500
| R | P |  | Satsop: PCB A-620 (Mechanism service) els 211663/dls 212209 ………………………………………… COS 1-009296 | Day: BPA; 17 Fri: 0845 1530
|  |  | A | Goble-Rainer Section of St Helens-Allston 1 115kV Line (Danger poles) els 212177/dls 212329 | Day: BPA; 23 Thu: 0700 1900; 24 Fri: 0700 1900; 25 Sat: 0700 1900
|  |  | A | Carlton-Tillamook 1 230kV Line (Replacing poles in the 11 to 23 mile) els 210717/dls 211419 COS 1-006918 | Day: BPA; 27 Mon: 0800 C; 28 Tue: C; 29 Wed: C 1330
|  |  | A | Allston: 500/230kV Bank 1, Station Service Bank 1 and 500/230kV Bank Spare T-1708 (Dryout and process oil on "B" phase) 210171 COS 1-009663 | Day: BPA; 27 Mon: 0700 C; 28 Tue: C; 29 Wed: C; 30 Thu: C; 31 Fri: C | to 07SEP09
|  |  | A | Naselle Tap-Cathlamet section of Naselle tap of Allston-Astoria 1 115kV Line (Replace danger poles and arms) els 211603/dls 211634 | Day: BPA; 27 Mon: 0730 C; 28 Tue: C; 29 Wed: C; 30 Thu: C; 31 Fri: C | to 01AUG09
S |  |  |  | Big Eddy-Chemawa 1 230kV Line (Repairing insulators and conductor) els 210552/dls 212202 COS 1-008970 | Day: BPA; 27 Mon: 0730 C; 28 Tue: C; 29 Wed: C; 30 Thu: C; 31 Fri: C 1530

## WoC-N, NI & ELM
JULY 2009 |  |  |  | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
WoC-N | NI | ELM | NI & ELM Estimated Path Capacity | Day | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
S |  |  | West of Cascades - North |  | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX
| N |  | Estimated NI Westside (N-S) | bar: 3 Fri
Estimated NI Westside (S-N) | bar: 3 Fri
|  | E | Echo Lake-Monroe flow gate | bar: 3 Fri
|  |  | Description | Day: Util
| N |  | Sedro WoolleyBellingham 3 115kV Line (Rebuilding and reconductor line for upgrade) 205518 COS (PSE) 1-006639 | PSE | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | to 01OCT09
C |  |  | Olympia-Grand Coulee 1 287kV Line (Grand Coulee transformer work in proximity to line) els 205165/dls 205179 (Line operating at 230kV) COS 1-009297 | BPA | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | to 26AUG09
| N |  | Talbot Hill-South 230kV Line (Communications and relay upgrades) 212314 COS (SCL) 1-008125 | SCL | 0600 C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | to 30SEP09
| N |  | Murray-Custer 1 230kV Line (Replacing wood poles) 204124 ……………………………………………………………. COS 1-001862 & 1-001863 | Day: BPA; 6 Mon: 0600 C; 7 Tue: C; 8 Wed: C; 9 Thu: C; 10 Fri: C 1800; 13 Mon: 0600 C; 14 Tue: C; 15 Wed: C; 16 Thu: C; 17 Fri: C 1800
C |  |  | Olympia: 287.239kV Bank 3 (Diagnostic service) els 211625/dls 212317 COS 1-008339 | Day: BPA; 13 Mon: 0700 C; 14 Tue: C; 15 Wed: C; 16 Thu: C; 17 Fri: C 1530
| N |  | Custer 500/230kV Bank 2 (Tap changer service) 204141 …………………………………………………….. COS 1-002628 | Day: BPA; 13 Mon: 0700 C; 14 Tue: C; 15 Wed: C 1700
| N |  | Monroe: 230kV Main Bus (Main Bus PT Diagnostic Service and Oil weep rapair) 204321 | Day: BPA; 14 Tue: 0800 2000
| N |  | Snohomish: 115kV Main Bus Section 3 and PT's (PT diagnostic service) [Forces out 230/115kV Bank 3,Snohomish-Beverly Park 3 115kV Line and Snohomish Fdrs 2, 3, 7 & 9] 186723 | Day: BPA; 15 Wed: 0630 1500
| N |  | Custer 500/230kV Bank 1 (Tap changer service, diagnostic and accessory service) 204145 COS 1-001865 | Day: BPA; 16 Thu: 0700 C; 17 Fri: C; 18 Sat: C; 19 Sun: C; 20 Mon: C; 21 Tue: C; 22 Wed: C; 23 Thu: C; 24 Fri: C 1700
| N |  | Murray: PCB A-1510 (Routine service) 203905 COS 1-005973 | Day: BPA; 20 Mon: 0730 1730
| N |  | Murray: PCB A-1516 (Routine service) 203908 COS 1-001867 | Day: BPA; 22 Wed: 0730 1730

## MT>NW & WOH
JULY 2009 |  |  | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
MT>NW | WoH | MT>NW & WoH Estimated Path Capacity | Day | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
M |  | Estimated MT>NW (E-W)
Estimated MT>NW (W-E)
| W | Estimated WOH (E-W)
|  | Description | Day: Util
M |  | Garrison: PCB 4409 (Diagnostic Service) 209420 [Broadview 2/West Bus Tie] COS 1-005105 | Day: BPA; 1 Wed: C; 2 Thu: C 1300
M |  | Garrison: PCB 4412 (Routine Service) 209402 [East Bus/Broadview 2] COS 1-005104 | Day: BPA; 15 Wed: 0630 C; 16 Thu: C; 17 Fri: C 1200
M |  | Garrison: 500kV Reactor 5 including PCB 4362 (Diagnostic ervice & repair oil leaks) 209406 | Day: BPA; 20 Mon: 0700 C; 21 Tue: C; 22 Wed: C; 23 Thu: C; 24 Fri: C 1300
[30 empty] | 0700 C | C | C | C | C 1300

## ID-NW
JULY 2009 IDAHO-NW OUTAGES | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Day | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Estimated ID-NW E>W
Estimated ID-NW W>E
Estimated LaGrande E>W
Estimated LaGrande W>E
Estimated Harney
Description | Day: Util