VALUE ANALYSIS IN THE NPS

Description: Value Analysis (VA) is a process of arriving at an optimal solution to a complex issue through a structured and reasoned analysis of the factors and functions related to the issue.

Goal: The goal of Value Analysis is to provide a structured process that ensures that

- Essential functional requirement are met

- All viable alternatives are considered

- Factors used to evaluate them are sound and fully considered

- All alternatives are tested equally against these factors

- Solutions are cost effective on an initial and life-cycle cost basis

- Benefit to cost relationships were considered

- Independent second opinions and perspectives were considered

- Rationale for decisions is clearly documented.

The overarching goal is that everyone can feel confident that the best solution, the best value was, in fact, achieved.

Process: The traditional Value Analysis process involves the gathering of necessary background material, usually by the office requesting the Value Analysis; a Value Analysis workshop with a 5-7 person team led by a VA facilitator; an oral presentation and written report of the findings of the Value Analysis session. The composition of the value study team is tailored to meet project requirements, but is typically composed of people familiar with the project, as well as independent team members who bring perspective and insight to the study. It is also an ideal time to make sure sustainable concepts and other NPS policy issues are considered.

During the Value Analysis workshop the facilitator will lead the study team through the seven steps of the Value Analysis Job Plan:

- Information Phase

- Function Analysis Phase

- Creativity Phase

- Evaluation Phase

- Development Phase

- Recommendation Phase

- Implementation Phase

Essential functions for the project are studied, cost estimates are analyzed, and stakeholders identified. Creative alternatives to providing the essential function are brainstormed and those alternative solutions evaluated. Evaluation factors are developed and a structured evaluation method typically used. Choosing by Advantages (CBA) is one evaluation method utilized by the NPS, but weighted factors may also be used. The relative importance of the advantages or benefits of each alternative are weighed and considered in a cost, preferably life cycle cost, context. Recommendations are made by the study team, and the client group e.g. park superintendent and staff, design team then must consider which recommendations can be implemented. The client shall address the rationale for not implementing any value study recommendations.

Topics for Study: Value Analysis can be applied to decisions of any scale, from broad scope conceptual plans for a park, to decisions concerning building program, to selection of flooring, or to decisions concerning administrative issues such as reorganization of an office. Law mandates value studies for NPS projects over half a million dollars.

Time Frame: The entire Value Analysis process can vary in duration, ranging from 2 weeks to 9 weeks, dependent upon the scale and complexity of the project and the decision involved. The specific study format will be tailored to the project. Preparation of background materials may require 1/2 to 2 weeks. The workshop itself may require from 3 to 5 days, depending upon the complexity of the issues, with a shorter duration for simpler more targeted decisions. Study findings are presented orally with a summary document at the conclusion of the workshop, and a final report follows within approximately 3 to 6 calendar weeks. Mini-VA's targeted on smaller decision can be much shorter in duration.

Who is involved: Composition of the study team and the audience for the concluding presentation are critical to the success of the study. The team will typically include key members of the park or of the requesting office staff, key members of the DSC and/or A/E design staffs, the VA facilitator, and in most cases independent consultants or technical experts. Great success has been achieved with the inclusion of sustainable technical experts from the NPS or other agencies such as the National Renewable Energy Lab.

If not participating on the team, those involved in designing and development of a project are key participants. The study begins with a design presentation explaining how the preferred alternative or alternatives were developed and serving as consultants to the team.

Cost: The true cost of a Value Analysis is the value increased and the costs saved or avoided by a study versus the time and expenses of involved in gathering the background information, participating in the workshop, and preparing the final report. The National Park Service has experienced returns of 20-40 to each dollar invested in a value study. Actually study costs vary dependent upon the size of the team, whether their cost are charged to the project, use of contractors, and whether travel is involved.  A typical value analysis requires from 2 to 4 weeks on the part of the facilitator to prepare for the session, conduct it, and to write the report. Costs would include salary, materials used in the analysis session, reproduction costs, and travel and per diem expenses. Additional costs include salary and travel expenses of other team members (e.g. Denver Service Center Personnel, A/E consultants, support office participants, etc.).  Study costs will range from $10,000 to $50,000 dependent upon duration, complexity, and size of team.

CASE STUDIES:

Canyon View Information Plaza at Mather Point; Visitor Transportation and Orientation Center. This project has utilized value methods throughout the decisionmaking process for the facility, for a current total of approximately eleven value studies. Topics included site selection, building organization and massing, materials selection, and rail transit related issues. A value analysis was conducted at the pre-design level for the Plaza which identified over $2.0 million in implemented value savings, with an investment of approximately $70,000; a return on investment of over 25:1.

General Management Plan, Mount Rainier National Park.  Value methods were used to select and construct the proposed action for the General Management, including Choosing by Advantages (CBA) and life cycle cost modeling. CBA was used to evaluate the non-monetary advantages of each alternative e.g. how did the alternatives affect visitor experience or protect resources. Life cycle cost estimates for each alternative were prepared, modeling staffing variations, plowing costs, building maintenance and operations, possible visitor shuttle operations. Importance or benefit to cost relationships formed the basis for selecting the proposed action.

Canyon Village Lodging, Yellowstone National Park.  At the request of the park and their concessionaire, the Denver Service Center conducted a value analysis that looked at the existing design of a lodging facility at Canyon Village and then looked at long-term development scenarios for the replacement of deteriorating cabin facilities. The result of the study was a reduction in the cost per lodging unit, identification of specific revision required in contract documents and a beginning evaluation of options for a more effective replacement of cabins at Canyon Village.

Water Pipe Material Selection, Shenandoah National Park.  The mini-value analysis format was used to focus on a materials choice between ductile iron pipe and PVC pipe. An approximately half day VA was conducted, gathering various engineering disciplines together, to explore possible alternatives to the traditionally specified ductile iron pipe. Ideas considered ranged from different pipe materials to different ways of installing and bedding the pipe.

Cliff House, Golden Gate National Recreation Area. The park was presented with a pressing issue regarding public safety, historical significance, and continued use of the Cliff House Restaurant and associated buildings.  The existing structures and viewing plaza did not meet structural, seismic, accessibility or general building codes. The park employed the Value Analysis process to determine the best alternative to meet the needs of this site’s visitors.  It was determined that the two alternatives, with similar costs, most completely meet these needs. Other non-monetary differences, became the deciding factors, and the value analysis recommendation was to retain the historic core of the facility and to restore it to it’s 1909 exterior appearance, extensively remodel it’s interior to meet life safety and accessibility requirements, and to remove non-historic additions and replace them with new and visually compatible additions.