| Deliverable | When Due | Who Is Responsible For Deliverable | Steps To Get It Done |
| --- | --- | --- | --- |
| Special note: Bridge Funding Request for Final Payment Holdback. | Due to the 20% final payment holdback by UC, Bridge Funding must be requested 30 days prior to depletion of the cash advanced. | Division Analyst | Refer to Bridge Funding process document. |
| Final Fiscal Report (FFR) | 90 Days after Period of Performance (POP) | Accounts Receivable (AR) |  |
|  | First working day after POP | SPO | RAPID e-mail notification sent to Principal Investigator, Division Analyst, SPO CO and AR with links to close out documents on SPO website. |
|  | Within 60 days after POP | Division Analyst | Division prepares draft FFR based upon UCSRP guidelines & restrictions and sends to AR with e-mail notification that all costs are in and this is final. |
|  | Within 60 days after POP | Sponsor | Sends pre printed FFR with Current Working Budget to: For Breast Cancer Research Program - SPO For Tobacco Research Program - AR |
|  | Within 60 days after POP | SPO | Sends pre printed FFR to AR. |

| Final Fiscal Report (FFR) | 90 Days after Period of Performance (POP) | Accounts Receivable (AR) |  |
| --- | --- | --- | --- |

|  | Within 75 days after POP | AR | Compares Sponsor issued FFR (Current Working Budget column) with Division draft FFR. If budget numbers match, AR signs the FFR. If budget numbers do not match, Division and AR to reconcile differences. |
| --- | --- | --- | --- |
|  | Within 90 days after POP | AR | Submits final FFR to UCSRP. |
|  | Within 90 days after POP | AR | FFR copy sent to SPO. |
|  | Within 150 days after POP | SPO | When the sponsor accepts all the final reports, the final payment check (last 20%) is issued. SPO receives the final check and issues a SPAA to release the bridge. |
|  | Within 150 days after POP | AR | Bills the final costs (this actions clears the unbilled costs) & deobligates unspent funds (if necessary). Issue SPAA with copy to SPO and Division Analyst. |

| Final Progress Report (FPR) | 60 Days after Period of Performance (POP) | Sponsored Projects Office (SPO) |  |
| --- | --- | --- | --- |

|  | First working day after POP | SPO | RAPID e-mail notification sent to Principal Investigator, Division Analyst, SPO CO and AR with links to close out documents on SPO website. |
| --- | --- | --- | --- |
|  | Within 5 days after POP | Division Analyst | Notifies P.I. FPR is due to SPO. |
|  | Within 55 days after POP | Division Analyst | Submit final FPR to SPO. |
|  | Within 55 days after POP | SPO | Submit final FPR to Patents for review and approval |
|  | Within 58 days after POP | Patents | Review, sign and return Patent form to SPO |
|  | Within 60 days after POP | SPO | Submit FPR to UC via mail. |
|  | Within 80 days after POP | SPO | SPO forwards Final FPR to Division. |