| Open Action Items - NPOESS SARR/SARP TIM |
| --- |
| Action Item # | Responsible Party | Description | Date Created | Date Due |
| 31 | NOAA(Sessions) | To provide NGST guidance on the antenna gain vs ADCS/SARP saturation issue. | 2-Jun-04 | 1-Aug-04 |
| 32 | NOAA(Button) | To provide NGST/IPO guidance/status on 466 MHz NTIA/ITU PFD issue. | 2-Jun-04 |  |
| 33 | NOAA(Button) | To provide NGST/IPO guidance/status on 466 MHz NTIA/ITU 1st harmonic issue. | 2-Jun-04 |  |
| 34 | DND(LaPointe) | To provide NGST an update to ICD figure 1.1-1 | 2-Jun-04 |  |
| 35 | DND(LaPointe) | To provide NGST details/requirements on transformers situated between the 1553 bus and the instrument interface | 3-Jun-04 |  |
| 36 | DND(LaPointe) | To provide NGST(Akram) with xmit and receive filter profiles | 3-Jun-04 |  |
| 37 | All | To provide IPO(Cummings) with final comments to the Sarsat and ADCS project plan. | 3-Jun-04 | 15-Sep-04 |
| 38 | NOAA(Button) | To provide NGST(Lutz)with examples of current housekeeping telemetry. | 3-Jun-04 |  |
| 39 | NGST(Barber) | To change Sarsat references to SARR or SARP where appropriate | 3-Jun-04 | ongoing |
| 40 | NGST(Barber) | To provide a schedule to all with terms defined. | 3-Jun-04 | Deliver with TIM minutes |
| 41 | NGST | To develop interface box between CNES instruments and spacecraft. | 3-Jun-04 | 30-Apr-08 |
| 42 | NOAA | To seek information on the METOP SARP/ADCS to spacecraft interface box and provide it to IPO. | 3-Jun-04 |  |
| 43 | NGST | To provide CNES and DND with alerts that are outside of the GIDEP system. | 3-Jun-04 | ongoing, close with 1st delivery |
| 44 | CNES | To provide NGST with FMEA | 3-Jun-04 | 1-Oct-04 |
| 45 | DND | To provide NGST with FMECA | 3-Jun-04 | 1-Oct-04 |
| 46 | NOAA | Coordinate appropriate meetings between SEDL and Steve Young re commissioning tests | 3-Jun-04 |  |
| 47 | NGST | To provide the IPO(Vince, Mike) with formal, written answers to DND PAIP questions | 3-Jun-04 | 22-Jul-04 |
| 48 | NOAA(IPO) | To provide DND(LaPointe) with formal, written answers to DND PAIP questions | 3-Jun-04 | 23-Jul-04 |
| 49 | DND(LaPointe) | To provide NGST details on pallet to spacecraft mounting screws | 3-Jun-04 |  |
| 50 | DND(LaPointe) | To provide NGST with TIROS in rush currents for 406 MHz SARR and 1544.5 MHz xmitr. | 3-Jun-04 |  |
| 51 | DND(LaPointe) | To investigate the power switching scheme for excess redundancy. Report findings to NGST. | 3-Jun-04 |  |
| 52 | NGST | To provide CNES with flight standard harness for testing for ADCS. | 3-Jun-04 | 1-Sep-07 |
| 53 | CNES | To provide NGST the EMI test procedure related to SARP connector J223.(ADCS?) | 4-Jun-04 |  |
| 54 | CNES | To provide NGST connectors needed to make flight/test harnesses. | 4-Jun-04 |  |
| 55 | NGST | To provide CNES and DND with level discret command circuit diagram and details | 4-Jun-04 |  |
| 56 | CNES | To provide NGST with procedure for determining amount of contamination during thermal vac. | 4-Jun-04 |  |
| 57 | NOAA(Button) | To seek information on how EWR 127-1 was handled on Tiros with respect to SARP/SARR | 4-Jun-04 |  |
| 58 | NGST | To provide all with integration and test plan. | 4-Jun-04 | 1-Oct-04 |
| 59 | NGST | To provide DND with EDU plan. | 4-Jun-04 | 1-Oct-04 |
| 60 | NGST | To update ICDs with statements from the GIIS referenced in the UIIS, DND and CNES NGIID review comments and resolutions, and provide an official copy of ICDs to CNES/DND | 4-Jun-04 | 1-Aug-04 |
| 61 | CNES | To mark up ICD with UIIS Rev B and C changes and deliver to NGST | 4-Jun-04 |  |
| 62 | DND | To determine if SARR will accept the same power flux density range as SARP/ADCS shown in Annex 1Rev 1 to the January 26, 2003 Technical Memo? | 2-Jun-04 |  |
| 63 | CNES | To review 28 V Main Power Bus requirement (+/- 2% with 0.2 V pk-pk from GIIS) to see if it can be less stringent and closer to the NGIID reqt. (+/- 6 V and 1.0 V pk-pk). | 3-Jun-04 |  |
| 64 | DND | To provide NGST with updated SARR palette and component dimensions, and palette material definition. | 4-Jun-04 |  |
| 65 | DND | To provide NGST with updated SARR mass and power | 4-Jun-04 |  |
| 66 | NGST | To delete reference to Spacecraft Simulator in NGIID | 4-Jun-04 | 1-Jan-05 |
| 67 | DND | To provide RATS documentation | 4-Jun-04 |  |
| 68 | NGST | To put in place an eRoom for document distribution and retention between NGST/IPO and CNES, and NGST/IPO and DND | 4-Jun-04 | 1-Oct-04 |