Two (2) One-Day Symposia With Military Health System Leadership and  Academic Leaders

Facilitators: Tenley Albright, Ken Kaplan

MHS POC: Carol Scheman, Mike Dinneen

The Uniformed Services University of the Health Sciences intends to award a Cost plus fee contract to provide symposia to be held in two locations.  Part I (day one) will be held in Boston, MA and Part II (day two) will be held in the Washington, DC metro area.  The estimated value of the award will be between $130,000 and $175,000.  (Subject to the availibility of funds.)

A. Background/Objectives

The Uniformed Services University (USU) would like to encourage closer ongoing relationships with the United States academic and research community. In the Military Health System (MHS) and particularly within the Uniformed Services University (USU), much is to be gained by closer ongoing fundamental and applied research as well clinical care interactions between those in the civilian academic medical and biomedical communities and the MHS and the USU.  While there certainly are research relationships between individual members of the MHS and the civilian academic communities, much of the current interactions between these two sectors is Department of Defense (DOD) funded research at civilian institutions.  While this is enormously beneficial to the DOD and to the nation; especially in times of war when the MHS is by necessity on the cutting edge of developing new treatments and confronting new treatment challenges, it is important to better exploit transfer of knowledge from DOD to civilian sectors and from civilian sector to the MHS.

To that end USU has been tasked to develop and host two meetings to begin the dialogue and foster collaboration between the Military Health System and civilian leaders in academic medicine. The symposia will help to enhance such collaboration.

B.  Statement of Work

The purpose of this task is to provide logistical support and management for the MHS Symposia at a location to be determined in Boston and in Washington DC. The meeting will begin at 8:00 and end by 4:30. Each meeting will be one (1) day with 25-30 participants. There will be two meetings, one to be held in Boston, MA and the second to be held in Washington DC. The following is a description of the tasks the contractor will perform in support of this conference:

- Provide the expertise of a coordinator/subject matter expert who has knowledge of leaders in the research/clinical community. This coordinator will: arrange speakers, and develop the list of MHS and civilian leaders who will be invited to participate; as well as facilitate the symposia. Coordinator will prepare meeting proceedings including synopsis of presentations within 30 days of each meeting. Facilitator will propose a plan for future academic sharing activities within 30 days of the final meeting.  Suggested Coordinator/Facilitator is

Tenley E. Albright, M.D.

Director

Collaborative Initiatives at MIT

4 Cambridge Center, 2nd floor

Cambridge, MA 02142

tel: 617/252-0003

fax: 617/252-0015

email: tea@mit.edu

2.  Develop a planning timeline, plotting all deadlines for the logistical planning of the meeting.

3.  Research site/location for meetings/working lunch.  Final recommendations for locations and facilities must be approved by the COR.

3.  Food and beverage items to be covered include: Lunch and meeting materials and Audiovisual equipment.

4.  Process and issue payment for all meeting expenses including: facilities, food and beverage, and other items as determined necessary with the approval of the Contracting Officer’s Representative (COR).

5.  Mail all meeting materials to participating members.  Communication by email is recommended.

6.  The contractor must be able to maintain a computerized tracking system containing all pertinent information on the participants.

7.  Prepare and mail confirmation letters and emails.

8.  Provide one staff member to assist with logistics.

9.  Prepare progress and financial reports two weeks before the scheduled symposia.  Report shall cover expenses from meeting planning and production.   Provide an itemized list of expenses.  Any items over or under budget shall be discussed with the COR.

10.  Prepare and submit to the USU, within 10 working days following the conclusion of the conference, a final report listing a detailed description of all services provided and problems experienced.

11. Prepare and submit, within 10 working days following the meeting, a final financial report.

The facilitator will be responsible for developing the agenda which must be approved by the COR no later than 14 days prior to the first symposia.

Deliverables:

- Sign all hotel and vendor contracts;

- Develop and maintain a timeline;

- Select and supervise all food and beverage arrangements;

- Prepare a final financial and registration report;

- Provide itemized list of expenses and/or invoices

- Proceedings of all meetings.