SUPPORT FOR ORWH ACTIVITIES

OFFICE OF RESEARCH ON WOMEN’S HEALTH

NATIONAL INSTITUTES OF HEALTH

WOMEN’S HEALTH SEMINAR SERIES

SPECIAL EVENTS/LECTURES/SYMPOSIA

MEETING SUPPORT/ PRESENTATIONS/REPORT WRITING

### EXHIBITS/CLEARINGHOUSE

ADMINISTRATIVE/TECHNICAL SUPPORT

This Task Order describes the tasks associated with preparation and support Office of Research on Women's Health (ORWH) activities and projects.

#### TASK 1: WOMEN’S HEALTH SEMINAR SERIES

ORWH will sponsor four two-hour women’s health seminars.  These seminars will be held on the campus of the NIH.

Bulk Mailing

The contractor will provide support for the mailing of fliers announcing the seminars.  The ORWH will provide fliers and all materials/supplies.

Using ORWH-designated mailing list, print labels for mailing, affix labels to envelopes, stuff envelopes, and deliver to NIH for mailing.

Allow for up to 250 fliers per mailing.

DELIVERABLES

Fliers prepared for mailing

Logistics

The contractor will assist in securing NIH conference space and arrange AV for presenters’ presentations.

The contractor will provide travel agency services to include airline and rail reservations and ticketing, reimbursement for ground transportation and M&IE as permitted under Federal Government Travel Regulations.  Contractor will secure at the prevailing government rate and prepay sleeping rooms for up to 12 speakers (estimate three per seminar).  Contractor will immediately notify Task Order Leader of all requested deviations to this range

Contractor will pay consultant’s fee ($200 per day) to those speakers who decline to provide ACH information to ORWH.

Pre-Seminar Activities

The contractor may be asked to attend seminar planning meetings.

The contractor will prepare simple table tents for each speaker for the panel segment of the seminar.

Contractor will distribute approximately 1,000 table tents to each NIH cafeteria in Bethesda and Rockville (Building 1, Building 10 (2 cafeterias), Building 31, Building 35, Building 38A, Rockledge II, Natcher, Parklawn and up to three others to be identified) for each of the seminars.  Dates to set up table tents (and dates to remove tents from the Parklawn cafeteria only) will be given.  ORWH will provide the table tents.

On-Site Support

Contractor will provide manpower to set up and maintain literature/handouts table and to provide on-site assistance to seminar organizers, speakers, and attendees as needed.

#### TASK 2:  SPECIAL EVENTS/LECTURES/SYMPOSIA

ORWH anticipates sponsorship or co sponsorship of six special events of up to 2.5 days duration each.  For planning purposes, the contractor may anticipate up to 100 attendees per event.

# Logistics

The contractor will secure sleeping rooms for up to 25 invitees per event.  The contractor will prepay these rooms.   Contractor will immediately notify Task Order Leader of all requested deviations to this range.

The contractor will provide travel agency services to include airline and rail reservations and ticketing, reimbursement for ground transportation and M&IE as permitted under Federal Government Travel Regulations.

Contractor will pay consultant’s fee ($200 per day) to invitees who decline to provide ACH information to ORWH.

Contractor will arrange for shuttle service between hotel and meeting site.

# Pre–Meeting Activities

The contractor will provide support for the preparation and mailing of letters of invitation with attachments (estimate120 letters per event) to individuals and societies.   Contractor will be responsible for reproducing and organizing all associated meeting materials as required for each event, including:

Process confirmation forms

Format draft and final agenda, as directed

Provide updated biographical sketches for selected participants

Prepare required materials for inclusion in the meeting notebook

Assemble a sample meeting notebook

Reproduce and mail notebooks, or forward to hotel as directed

Assemble and reproduce all materials for one additional mailing, if necessary

The contractor will receive reference materials from the meeting participants and support initial phase of building an annotated bibliography from these materials for use.

DELIVERABLES

Letters of invitation

Agenda

Initial draft of annotated bibliography

Handout materials (estimate 10 handouts)

Name badges

Table tents

Participant list with email addresses for download into a list serve

# On-Site Support

Events will be held either on the NIH campus or at a nearby site identified and secured by the contractor and approved by ORWH.

Maintain registration table

Facilitate conference calls

Provide, designate, or facilitate recording/transcription services

Provide, designate, or facilitate audio/visual services

Photocopy handout materials as needed

Provide on-site text processing of documents

Arrange shuttle service between the and local airports

Prepare, according to design approved by ORWH, name badges for participants and approximately 10 table tents per event

Post- Meeting Tasks

Prepare Federal Express forms to send notebooks and materials to home sites for participants.  Forms will be pre-printed to bill ORWH.

Pack unused materials and supplies and return them to ORWH.  Provide final meeting attendance roster to Task Order Leader within five business days following the close of the meeting.   Provide electronic minutes of meeting (Microsoft Word) within 10 business days following the meeting.  If requested, provide electronic transcript of meeting (Microsoft Word) and CD within 10 business days following the meeting

DELIVERABLES

Federal Express forms

Meeting Roster

Minutes

Transcript

#### TASK 3: GENERAL COMMITTEE MEETING SUPPORT, PRESENTATIONS, AND REPORT WRITING

Rapporteur/Transcription Services

The contractor will provide audiotaping and notetaking services for the deliberations of the committee members of ORWH’s standing and ad hoc committees and transcribe these deliberations into a transcript (if requested) and minutes.  Minutes will be prepared in Microsoft Word using formats defined by the ORWH.  Transcripts will be submitted to ORWH on a CD.  Transcripts and minutes will be electronically transmitted to ORWH within 10 working days of the meetings.  Due dates for transcripts and minutes prepared for ad hoc committee meetings will be provided.

The contractor should anticipate 24 meetings of two to three hours in duration.  These meetings will include up to 40 participants each.  Meeting dates, times, and locations will be provided as that information becomes available.

Provide letter-writing service to respond to mass mailings campaigns and routine correspondence.  Anticipate three mass mailing campaigns per year.

Develop press releases and Federal Register Notices (estimate six).  Develop two major reports per year from inception through content clearance.  Provide scientific writing support for approximately six major articles for publication.  Develop an estimated four ORWH fact sheets and information bulletins.  Develop and maintain a daily clipping service to keep ORWH staff apprised of emerging topics of interest in the women’s health arena.  Assist in the development of a quarterly women’s health newsletter.

Provide scientific writing support for speechwriting and the development of related PowerPoint presentations and handout materials.  Anticipate 30 presentations.

DELIVERABLES

Minutes

Transcript

Speeches

Reports

Federal Register Notices

Press Notices

#### TASK 4:  EXHIBITS/CLEARINGHOUSE SUPPORT

Contractor will set up and break down ORWH exhibit at a total of 12 two-day local and three out-of-town exhibits. Contractor will be responsible for contracting or otherwise securing exhibit space and for transporting the exhibit and materials. Contractor will maintain literature supply at exhibit table and man exhibit booth.  The exhibit and exhibits materials will be warehoused by the contractor.

Contractor will provide warehousing for approximately 150 skids of ORWH materials, documents, and publications.  Contractor will receive and store materials, documents, and publications forwarded by NIH ICs for inclusion in ORWH exhibits, seminars, and other functions.

The contractor will provide pickup and delivery services between NIH campus and the warehouse. The contractor will also provide pickup and delivery service of these materials to all ORWH functions (Tasks 1 and 2), as well as events sponsored by other organizations, both on and off campus. Anticipate an average of one trip per week. Contractor will provide packing and mailing of materials for functions held outside the metro area.  Anticipate two mailings per month.

Contractor will fill requests for information received from the ORWH website, ORWH publication line, letters, and verbal requests.  Assemble and mail ORWH information packets.  Anticipate 1,000 information packets.

DELIVERABLES

Monthly publications manifest

# TASK 5:  GENERAL ADMINISTRATIVE/TECHNICAL SUPPORT

- Online Course

Provide technical support for the development, refinement, and management of a web-based scientific course, including technical design, electronic formatting, tracking and documenting student progress.

- Contacts Database

Maintain an appropriate database of ORWH contacts in a searchable format.  Provide data entry for the ORWH contacts database.

Full Name

Credentials (MD/PhD/DDS)

Title

Affiliation

Building and Street Address (City, State, Zip Code)

E-mail address

Office Phone - Area Code and Number

Office Fax - Area Code and Number

Scientific Society Membership

- Courier Service

Provide daily courier service between contractor and ORWH-occupied off-campus locations.  Other destinations will be added to this service on an as-needed basis.

- General Administrative Support

Provide for the development and general support of information management to include, but not be limited to a storage/retrieval system for paper and electronic files, email management, and electronic files management.  Provide data entry services on an as-needed basis.  Provide support for scanning and archiving historical and current ORWH documents, reports, and correspondence.  Provide general office support on an as-needed basis.

SOLE SOURCE JUSTIFICATION

Statutory Authority:  	FAR 6.302-2 (a) (1), (b) (1) and (2)

"When the agency’s need for the supplies or services is of such an unusual and compelling urgency that the Government would be seriously injured unless the agency is permitted to limit the number of sources from which it solicits bids or proposals.”

(b)(1) An unusual and compelling urgency precludes full and open competition; and

(2) Delay in an award of a contract would result in serious injury, financial or other, to the Government.

Educational Services, Inc (ESI), a small business, has provided logistics support to ORWH for approximately five years through the NIH CATS vehicle.  During this time, they have assisted in the planning and execution of numerous ORWH-sponsored special and recurring meetings, special events, and activities.  An award to ESI under the current CATS extension would permit ESI to continue working on ORWH projects without disruption until an alternate suitable contract vehicle can be identified, competed, and awarded.

ESI has begun foundation-laying activities for upcoming workshops, symposia, and seminars.  They also warehouse the numerous ORWH publications and exhibits (approximately 160 skids) featured at these events.  An award to a new contractor at this point would require a transfer of activities and materials.  The costs associated with bringing a new contractor on board (transfer of property, contracts, staff time required to bring a new organization into the planning and execution of these upcoming activities, etc.) would be unnecessarily excessive and prohibitive, considering the limited available ORWH funds as well as the limited performance period of the NCATS extension.