# MINOS Computing/Offline Software Status Report

Liz Buckley-Geer

May 4, 2005

Report #3

# Project Description

MINOS Computing

http://wwwserver2.fnal.gov/cfdocs/projectsdb/projdetail.cfm?ProjectID=81

MINOS Offline Software

http://wwwserver2.fnal.gov/cfdocs/projectsdb/projdetail.cfm?ProjectID=292

# Summary

Neither of these projects has made a status report since November 2003. Much work has happened since then.

### MINOS Computing

This task covers items such as data handling, control room support etc. The people involved are Liz Buckley-Geer, Art Kreymer and John Urish.

- MINOS Control Room

The control room on WH12NW is now fully functional thanks to work by John Urish. He has installed all the flat panel monitors on stands which group then together according to their function. He has installed wireless keyboards and mice to eliminate the tangle of cables. He moved all the computers onto a table in the corner. A lot of the configuration for the applications was done by a MINOS collaborator and John is meeting weekly with him to transfer the knowledge so that John will be able to look after all aspects of the systems.

- Hardware deployment

We purchased and deployed the production Oracle server minosora1. The development Oracle server is on order. We deployed a Linux cluster of 12 dual CPU nodes. These were eagerly awaited by the collaboration. We are decommissioning the SGI minos1. Logins are disabled and it will be turned off on June 1. We are deploying a new MySQL server with more disk and memory to replace the current one which is running out of both. We need to plan how to spend the current year’s equipment budget.

- Data Handling

We are moving full steam ahead with SAM deployment. This was slowed for a while due to the departure of Bruce Greenway in August 2004.  Art Kreymer joined the effort in February 2005 and we are now back on track. Currently all the raw data has been declared to the production Oracle database and is being updated daily. This will move to a once per hour update once we are happy everything is okay. Work is proceeding on generating the metadata for all the reconstructed data, about 220,000 files. The plan is to generate this metadata by reading in the python files containing the raw metadata and writing out files with necessary changes for the reco data.

The MINOS offline framework is able to access SAM and run jobs over SAM datasets. Thanks to Sinisa for his work on the C++ interface and making the necessary changes to allow us to run multiple projects in a single offline job.

We will initially have two stations, one which supplies files from dcache via URLs and another which can supply files from AFS space. We will deploy the dcache station first.

We will continue to allow users direct access to the data via dccp and the weak FTP door. A web utility has been provided that gives users lists of files in the appropriate format from the SAM catalog.

- Database

Migration of our offline database from MySQL to Oracle has been a long and painful saga and is not yet complete. Dennis Box has been helping with this activity. From the collaboration side the work is done by Nick West from Oxford. The MySQL server is administered by EXP personnel (system admin from CSS). The assumption that the use of OBDC as an interface would insulate us from the differences between Oracle and MySQL was naïve. About the only thing that ODBC provides is a uniform API. Dennis keeps a log of progress at http://home.fnal.gov/~dbox/minos/status_reports.html.

In addition we have some VERY LARGE tables being generated by the Light Injection Calibration process (21 GB at the last count). This has caused operational problems on the current MySQL server, we started running out of disk space. The large tables were moved to the second disk on the machine but updating them is currently on hold until we migrate to the new MySQL server. The hope is that the MySQL server would become a read-only replica of the Oracle master but we are not there yet.

- User Consulting

There is ongoing support of users which has the tendency to slow down progress on projects.

### MINOS Offline Software

Most of the offline software is written by university collaborators. However we are responsible for certain of the infrastructure and simulation.  This work is done primarily by Robert Hatcher. Most of the work described here has been done in the last six months.

- Geometry

Guide the migration to the ROOT geometry being done by Sue Kasahara at Minnesota.

- Magnetic Field

There has been a lot of work in this area. There have been various improvements to the code and performance improvements. There has also been an effort to understand the asymmetry between positive and negatively charged muons in the Far detector. A task force was convened and Robert participated in this.

- Detector Simulation

We updated the geometry to reflect the as-built detectors for both Near and Far. Various other improvements were made to make the detector descriptions more realistic. Work is progressing, albeit more slowly that we would like, on the new C++ simulation interface.

- Mock Data Challenge

This has taken much longer than originally planned. The original schedule was to have results by March 2004. This turned out to be too ambitious given the state of the software and the readiness of the collaboration to analyze the data. First results were presented at the March 2005 collaboration meeting. This has been a distraction from other projects like the C++ simulation.

- Database Updater

This package reads the raw data files and extracts various metadata from them and puts it in the database. This was completely overhauled to produce new and improved metadata for the offline database as well as generating the metadata for SAM.

- Support

There is always the ongoing task of user support, helping them find and fix bugs, fixing crummy user code etc. In addition all the above items have support associated with them.

### Resources used (budget, effort)

I summarize the percentage effort for the last six months

MINOS Computing

|  | Nov 04 | Dec 04 | Jan 05 | Feb 05 | Mar 05 | Apr 05 |
| --- | --- | --- | --- | --- | --- | --- |
| E. Buckley-Geer | 40 | 40 | 80 | 80 | 60 | 60 |
| Art Kreymer |  |  |  | 20 | 50 | 90 |
| John Urish | 4 | 10 | 28 | 35 | 45 | 30 |

MINOS Offline Software

|  | Nov 04 | Dec 04 | Jan 05 | Feb 05 | Mar 05 | Apr 05 |
| --- | --- | --- | --- | --- | --- | --- |
| Robert Hatcher | 68 | 57 | 93 | 95 | 85 | 92 |

MINOS Database Development

|  | Nov 04 | Dec 04 | Jan 05 | Feb 05 | Mar 05 | Apr 05 |
| --- | --- | --- | --- | --- | --- | --- |
| Dennis Box | 33 | 35 | 40 | 7 | 10 | 10 |

Budget for FY05

Amounts in K$.

| Task | Task Code | Budget | Obligated | Comment |
| --- | --- | --- | --- | --- |
| MINOS-DATABASE | 50.01.06.04.03 | 25.5 | 16.4 | Oracle development machine |
| MINOS-DISK | 50.1.06.04.05 | 21.4 |  | Dcache disk and analysis disk |
| MINOS-CPU | 50.01.06.04.06 | 79.2 |  | Farm and analysis CPU |
| MINOS-COMPUTING | 50.01.06.04.01 | 32.3 | 16.8 | General operating |
| MINOS-NETWORK | 50.01.06.04.02 | 2 | 1.1 | Fiber to the desktop on WH12W |

### Schedule/Milestones

We plan to start beta testing with SAM in May (as soon as we have the reconstructed data in the production database). We will move to full production at FNAL by mid-June.  The next step will be helping users set up SAM stations at universities.

Deployment of the offline database in Oracle is planned for mid-June.