PART 1834

MAJOR SYSTEM ACQUISITION

# TABLE OF CONTENTS

# SUBPART     1834.0              GENERAL

1834.003		Responsibilities.

SUBPART	1834.2	EARNED VALUE MANAGEMENT SYSTEM

1834.201			Policy.

1834.202  	Integrated baseline reviews.

1834.203				Solicitation provisions and contract clause.

1834.203-70			NASA solicitation provision and contract clause.

PART 1834

MAJOR SYSTEM ACQUISITION

Subpart 1834.0--General

1834.003    Responsibilities.

(a)	NASA's implementation of OMB Circular No. A-109, Major Systems Acquisition, and FAR Part 34 is contained in this Part and in NASA Policy Directive (NPD) 7120.4, "Program/Project Management," and NASA Procedures and Guidelines (NPG) 7120.5, "NASA Program and Project Management Processes and Requirements".

Subpart 1834.2--Earned Value Management System

1834.201 Policy.

(a) Application of an Earned Value Management System (EVMS) is required for all acquisitions for development designated as major in accordance with OMB Circular A-11, and for development or production contracts and subcontracts, including those for flight and ground support requirements, and institutional requirements (facility, IT investment, etc.) as follows:

(i) For contracts and subcontracts valued at $20M or more, and contracts and subcontracts for major acquisitions valued at less than $20M, the EVMS shall comply with the guidelines in the ANSI/EIA-748 Standard.

(ii) For contracts and subcontracts valued at $50M or more, the contractor shall have an EVMS that has been formally validated and accepted by the Government.

(iii) For contracts and subcontracts for other than major acquisitions valued at less than $20M, earned value management application is optional and is a risk-based decision that is at the discretion of the program/project manager.

(iv) EVM is not required on contracts for non-developmental engineering support services, steady state operations, basic and applied research, and routine services such as janitorial services or grounds maintenance services.  In these cases, application of EVM is at the discretion of the program/project manager.

(e)  Contracting officers shall request the assistance of the cognizant Defense Contract Management Agency (DCMA) office in determining the adequacy of proposed EVMS plans.

1834.202  Integrated baseline reviews.

(d)  Use of pre-award IBRs is limited to the second or subsequent phases of a phased acquisition (see 1817.73).  When a pre-award IBR is contemplated, the contracting officer shall include the instructions with respect to the schedule and conduct of the IBR in the proposal request.

1834.203 Solicitation provisions and contract clause.

The FAR EVMS solicitation provisions and contract clause are not used in NASA contracts.  See 1834.203-70 for the NASA EVMS solicitation provision and contract clause.

1834.203-70  NASA solicitation provision and contract clause.
 	Except for the contracts identified in 1834.201(a)(iv), the contracting officer shall insert –

(a) The provision at 1852.234-1, Notice of Earned Value Management System, in solicitations for contracts for --

(1) Development or production, including flight and ground support projects, and institutional projects (facility, IT investment, etc.), with a value exceeding $20M; and

(2) Acquisitions of any value designated as major by the project manager in accordance with OMB Circular A-11; and

(b) The clause at 1852.234-2, Earned Value Management System, in solicitations and contracts with a value exceeding $50M that include the provision at 1852.234-1.  The contracting officer shall use the clause with its Alternate I when the contract value is less than $50M.