STEEL PLATFORM DESIGN

FOR THE

ASPEN (PKN) LOCALIZER TYPE DIRECTIONAL AID

- Summary:

The purpose of this project is to produce a design for a galvanized steel platform that will replace an existing wood framed platform that supports a Localizer Type Directional Aid (LDA) located on the top of Aspen Mountain (elevation is approximately 11,700 ft).

Design will include the information necessary to fabricate the platform and construct the foundation that supports the platform.

The A/E Consulting Firm will furnish all labor, materials, supplies, testing, supporting engineering studies, surveying, legal descriptions, and other work required to accomplish the design described herein.  A/E’s design drawings and specifications will be used by the FAA to acquire a fabricator/construction construction contractor.

- General Description of Structure:

- Platform will support a 14 element, Thales Mark 20A Localizer type antenna (to be installed on the platform by the FAA).

- Top floor of the platform shall be 15’ x 108’ with a 42” high hand rail.

- Due to the slope of the ground at the antenna site, the height of the platform floor will vary, but is expected to be as high as 18 feet above the ground (existing ground slope can not be disturbed).

- An antenna counterpoise similar to what is in place at the current platform is expected.  Specific details of the shape and size of the counterpoise will be provided.

- Structure shall withstand 100 mph wind with ½” radial ice.

- Details:

  - Site Visit

The A/E Consulting firm shall complete at least one site visit, at their own expense, prior to submitting their proposal. This visit shall be coordinated with Bob Brown, FAA Project Engineer (303) 342 1837.  This visit shall serve as a familiarization with the area and to establish the physical restrictions of the existing site.

  - Coordination with the local authorities

The A/E consulting firm shall contact local authorities, including the Aspen Ski Company, Pitkin County, and the National Forest Service to determine the necessary approvals and permits necessary to construct the structure (includes requirements to access the site during construction).

  - Structural Design

The A/E Consulting Firm shall complete all drawings and specifications required to fabricate the steel platform/counterpoise and the required support foundations.

  - Life Span

The design shall require all steel components to be protected from corrosion by a system with a minimum life expectancy of 50 years without maintenance.

  - Review of Fabricator/Construction Contractor Submittals

The A/E Consulting firm shall review the fabrication submittals received by the FAA from the FAA’s construction contractor to insure that the information meets the requirements of the A/E’s design.

- Deliverables:

  - Drawings

Submit for approval of the FAA Project Engineer 50%, 90% and 100% revisions of the drawings. All drawings shall be completed in hard copy and electronically in AUTOCAD Release 2006 or later format.

  - Specifications

Submit for approval of the FAA Project Engineer 50%, 90% and 100% revisions of the specifications including but not limited to:

Division 2, Site construction,

Division 3, Concrete,

Division 5, Metals,

Division 7, Thermal and Moisture protection,

Division 9, Finishes,

Division 11, Equipment- Climbing devices,

Division 13, Special construction

All specifications shall be completed in Microsoft Word Version 2003 format. An electronic file of these specifications shall be delivered to the FAA at the end of each phase of this design.  The final 100% copy is intended to be publication ready, including the engineer’s stamp for relevant sections.

  - Calculations

Submit for approval of the FAA Project Engineer 60%, 90% and 100% revisions of the calculations and basis of design.  The final version of these documents shall be signed and stamped by a Licensed Structural Engineer, empowered to sign drawings and calculations in the State of Colorado. The A/E Consulting Firm shall secure the services of a local Geotechnical firm to be responsible for providing the soil investigations and reports deemed necessary for the proper design and construction of this project.

Calculations for each phase of this project shall be delivered in a sequential bounded format.

  - Schedule

Design Phase: The A/E Consulting Firm shall complete the design phase of this project as indicated below.  Dates may be adjusted by the Project Engineer to allow for coordination of participants and weekends and legal holidays.

Kick-off meeting and requirements definition		1 day, or as required

Preparation of 50% submittal				45 days

FAA review						14 days

50% Comments consolidation meeting			1 day, or as required

Preparation of 90% submittal				30 days

FAA review						14 days

90% Comment consolidation meeting			1 day, or as required

Preparation of 100% Package				15 days

FAA Final review					10 days

Issue Bid-ready construction drawings,

specifications, and calculations			3 days.

  - Detailed Cost Estimate

The A/E Consulting Firm shall provide a detailed estimate of the construction cost, at the 50%, 90%, and 100% design phases.  Provide at the end of each phase electronic versions of all estimates in Microsoft Excel version 2003 format.

- Codes, Standards and Recommendations

The A/E Consulting Firm shall list all codes standards and recommendations applicable for the proposal.

- Qualifications

The A/E Consultant or its sub-contractor shall have on staff a licensed Structural Engineer currently empowered to sign drawings and structural calculations in the State of Colorado.  This licensed engineer shall stamp the contractor’s final design submittal, including bid-ready drawings, specifications, and calculations.

- Point of Contact

The point of contact for visiting the site is the Bob Brown (303-342-1837), FAA Project Engineer.