| Responsible Office: | Code 400/Flight Programs and Projects Directorate |
| --- | --- |
| Title: | Lessons Learned |

###### Preface

- PURPOSE

The objective of Lessons Learned is to; a) allow Programs and Projects to benefit from experiences gained on prior activities, and b) similarly offer insights for future Programs and Projects so that best practices can be shared/replicated and prevent problems from recurring.  Lesson Learned is a process involving the; identification, capture, organization, analysis, targeting, dissemination, application, and feedback of experience/information developed to improve the effectiveness of Programs and Projects.  This GPG provides procedures and guidelines for applying Lessons Learned to GSFC Projects as required by NPG 7120.5, “Program and Project Management Processes and Requirements” for the Capture Knowledge process.

- APPLICABILITY

The procedure for capturing and sharing lessons learned shall be applied to all GSFC Programs and Projects.  This procedure shall also be applied to all deliverable instruments, spacecraft and other GSFC products designated by the GSFC Center Director.  This procedure applies to Program and Project formulation, approval, implementation and evaluation subprocesses, including mission operations.

- AUTHORITY

NPD 7120.4, Program/Project Management

- REFERENCES

- NPG 7120.5, Program and Project Management Processes and Requirements.

- NPG 8735.1, Procedures for Exchanging PM&P Data Using GIDEP and NASA Advisories.

- NPG 8715.3, NASA Safety Manual.

- NPG 8621.1, NASA Procedures for Mishap Reporting, Investigating and Recordkeeping.

- NPG 8000.4 Risk Management Procedures and Guidelines.

- NASA Federal Acquisition Regulations (FAR) Supplement (NFS) Parts 1807, 1815, 1823, and 1846.

- GPG 7120.1, Program and Project Management.

- GPG 7120.4, Risk Management.

- GPG 7120.5, Systems Engineering.

- GPG 8700.4, Integrated Independent Reviews.

- GPG 8700.6, Engineering Peer Reviews.

- GPG 1060.2, Management Review And Reporting for Programs and Projects.

- GPG 1710.1, Corrective and Preventive Action.

- GPG 8621.3, Mishap, Incident, and Close Call Investigation.

- 400-PG-8621-0-1, Anomaly Reporting System for Flight Programs and Projects.

- CANCELLATION

None

- SAFETY

None

- TRAINING

The purpose of training is to make personnel aware of the value, process and priority associated with sharing Lessons Learned within and among Programs/Projects.  Program/Project teams shall be trained in the process for sharing Lessons Learned as defined in paragraph 2.4.  Current and new staff (both Government and Contractor) shall be provided with general familiarization of the process for sharing Lessons Learned and how to make use of resources and tools to facilitate these activities.  Those individuals with direct responsibilities for implementing the process for sharing Lessons Learned will receive more detailed training on specific techniques for how to; identify, capture, disseminate and apply lessons.

- RECORDS

None

- METRICS

None

P.10	DEFINITIONS

- Lesson Learned – A Lesson Learned is that knowledge gained by study or experience that becomes useful as an instructive example.  Lessons that are learned result from activities where something different from an everyday event, or realization that an unexpected occurrence has taken place including; a mishap, accident or mistake.  Outcomes of work practices, either positive or negative, successes or failures, are also representative of Lessons Learned.  The value of an innovative approach or a path that did not produce the desired effect are useful Lessons Learned.  Lessons are learned during the course of, and at the completion of, planned activities.  Lessons Learned represent knowledge that is acquired and as such represents a valuable resource to be captured and shared with others.

Lessons Learned include stories about successes, failures, insights and experience of interest and value to others, examples of novel and innovative developments as well as suggestions on how processes can be improved.  Sources of lessons include; management and staff, retirees, contractors and consultants, stakeholders and Customers.

Specific lessons to capture and share include; a) problems, failures, incidents, anomalies and risks, b) issues, needs, results, and trends, c) best practices and pitfalls to avoid, d) design/decision processes and rationale.  Lessons may be gleaned from numerous existing resources such as; a) weekly activity reports and monthly status reviews, b) independent review team reports, c) top-ten lists, d) requests for actions and associated closure reports, e) award fee letters, f) Quarterly Executive Dialogs, g) after-action reviews, h) final reports, and i) case studies.

- Lessons Learned Process – Figure 1 indicates the Lessons Learned process.  This process shall be applied within each Program Office and Project to ensure that experience gained in the course of performing Pre-Formulation, Formulation, Implementation and Operations activities are captured and shared among Projects, throughout the Center and with Agency partners.  Figure 2 presents a detailed flow of GSFC activities associated with the Lessons Learned process.

Figure 1.  Lessons Learned Process

Figure 2.  Lessons Learned Activities

- Best Practice – Those activities, based on experience, considered to provide desirable outcomes for a particular process.  {These best practices are typically identified by performing organizations and are organized, reviewed and disseminated by the Systems Management Office.}

- Knowledge Management – Those Center and Agency efforts associated with principles, policies, common tools and associated resources applied to address transfer of experience throughout the organization.  Knowledge Management activities are focused on improving processes and institutional aspects within the NASA environment to facilitate sharing of explicit and tacit knowledge.

- Applicable Lessons Learned – Lessons are considered to be applicable if all of the following criteria are met:
              1.  Relevancy; a) significant bearing within NASA and b) useful for applications outside of
                   NASA,

2.  Understandable by someone; a) not intimately familiar with the Project or functional area 
                   and b) with reasonable skill,
              3.  Beneficial; a) recognizable impact within NASA, b) reasonable possibility that someone else
                   could face a similar situation, c) provides an opportunity for saving effort, time or money, or 
                   d) allows improvements in performance, safety, reliability or probability of mission success
              4.  Validity; a) factually and logically correct, b) consistent with laws, regulations and policies, 
                    c) well-grounded or justifiable, and d) expectation that a similar outcome either will (for a 
                    positive lesson), or will not (for a negative lesson) be repeated,
              5.  Realizable; a) capable of being implemented , and b) offers a practical not hypothetical 
                    solution,
              6.  Consistent; a) lesson fits within categories, b) an independent check of the lesson is 
                     possible, c) root cause analysis can be applied, and d) applicability, priority and target for 
                     implementation can be identified.

- Capturing Lessons Learned – The process for gathering Lessons Learned from individuals, Projects and Program Offices.  Lessons Learned exists in the knowledge that people have and in documents, these only have value to others if these sources of insight and experience are captured, organized and made available.

- Community of Practice – An informal group with common professional interests/needs/goals such as; Projects in Formulation, Implementation and Operations.  The structured environment for such a group to exchange information, identify individuals with relevant expertise/interests and provide the opportunity for collaboration.

- Review and Organization of Lessons Learned – The categorization, ranking and assessment of validity for a lesson learned that has been submitted.  These efforts will be performed by; a) each Project’s Lessons Learned Coordinator as part of an initial screening, and b) the Program Office’s Lessons Learned Lead to ensure consistency.

- Root Cause Analysis – A review of an activity, event, condition, result or occurrence to determine the essential common basis, underlying reason or systemic elements that gave rise to this condition.  The purpose of root cause analysis is to identify the contributing systemic factors, train of events, and common threads so that; a) a recurrence of negative outcomes can be prevented in the future, and b) best practices for positive outcomes can be identified.

- Applicability of Lessons Learned – Determination of what Program Offices, Projects and those individuals with particular interests, functional responsibilities or specializations that can benefit from a particular lesson.

- Action Plan for Lessons Learned – Identifying the priority for distribution of lessons and what techniques should be applied to ensure that the appropriate lessons reach the Programs, Projects and individuals when they can best make use of these lessons.  Priority descriptors for Lessons Learned include the following:

    - Red – Urgent; Item related to immediate concern with physical security,  personnel health and safety, direct impact on mission success or significant expected effect on performance, schedule and/or cost.

    - Yellow – Caution; Item has the potential for impact to physical security, personnel health and safety, possible effect on mission success or influence on performance, schedule and/or cost.

    - Blue – Information; Item is provided for background information to protect physical security,  personnel health and safety, mission success, performance, schedule and/or cost.

    - Green – Good Work Practice; Item is a positive example of an action, activity or practice that improves; physical security, personnel health and safety, mission success, performance, schedule and/or cost.

- Dissemination of Lessons Learned – Making lessons, and/or summaries of lessons available to the Programs, Projects and individuals that have the opportunity to apply them.  Dissemination of Lessons Learned includes both providing convenient access to resources of direct and indirect interest and forwarding alerts/updates to individuals willing to receive such information without having to search for it.  Technique that support dissemination of Lessons Learned include;  NASA LLIS Web site, NASA Technical Standards Web Site, EOS Pilot for Lessons Learned Web Site/Community of Practice Portal, email distribution of alerts/updates, meetings, teleconferences, workshops, working groups, employee exchange, training, mentoring, conferences.

- Feedback of Lessons Learned – Programs, Projects and individuals that receive lessons will provide periodic reports on the application and value of lessons learned within their areas of responsibility.  Suggestions will also be provided regarding improvements to the process for sharing lessons learned.

- Evaluation of Value – {Programs, Projects and/or SMO TBR} will develop estimates of the performance, schedule and cost benefits associated with implementing lessons learned.  The impact of applying lessons learned will also be assessed with regard to; mission success, safety, reliability, value to stakeholders/customers, and furtherance of Center/Agency objectives.  Staff is encouraged to indicate their view of lessons learned with respect to; improving the quality of their workplace experience, professional development benefit, and other aspects of personal priority to them.

Procedures

- Roles and Responsibilities

- The manager for each functional activity, Program Manager and Project Manager, shall have leadership responsibility for implementing a Lessons Learned process across the full scope of activities within their area of responsibility.  That leader, hereafter referred to as the Program/Project Manager (PM), is ultimately responsible for identifying, capturing, sharing and applying Lessons Learned, providing feedback on the Lessons Learned process as well as reporting on results of Lessons Learned activities to higher level management.  The PM defines and documents the Program/Project unique aspects of the Lessons Learned process and assigns responsibility to team members for implementation of Lessons Learned efforts.  The PM is responsible for determining the value and benefit associated with applying Lessons Learned to Program/Project activities.

- The PM shall assign specific responsibilities for Lessons Learned implementation to Program/Project team members as the PM judges to be appropriate.  Each major element and/or subsystem lead is expected to play a key role in the identification, capture and application of Lessons Learned specific to their area of responsibility and actively participate in system-level Lessons Learned activities.  The PM may also assign individuals to conduct additional Lessons Learned activities that cross multiple areas.

- The implementation of Lessons Learned is organized within each Program Office to ensure continuity and consistency of Lessons Learned efforts across multiple Projects.  Program Offices and Project Offices may be expected to utilize the expertise of individuals associated with System Engineering, Risk Management and Configuration Management to support the identification, capture, sharing and application of Lessons Learned.

- The implementation of infrastructure, tools, processes and procedures for Lessons Learned are part of the safety and mission assurance process, specifically known as Knowledge Management.  The Systems Assurance Manager (SAM) and Systems Safety Manager assigned to the Project management team shall define, with PM approval, the safety and mission assurance requirements and manage the related surveillance activities necessary to effectively assess and support implementation of Lessons Learned processes for each Project.

- The GSFC Program Management Council (PMC) reviews the capture and application of Lessons Learned and verifies that resources are adequate as part of each  PAPAC process defined within NPG 7120.5.  The PMC reviews Lessons Learned as part of the monthly status, confirmation, and mission readiness review processes.  See GPG 1060.2 for further information on these PMC processes.

- The GSFC Flight Programs and Projects Directorate (FPPD) is responsible to the Center Director for Lessons Learned policy, procedures, guidelines and best practices.  These Lessons Learned elements shall be consistent with the GSFC Systems Management Office (SMO) Knowledge Management policy, procedures, guidelines and best practices.  The SMO also has the Agency-level responsibility for Knowledge Management training and provides Lessons Learned consultation to NASA Program/Project teams.

- Requirements

- GSFC Projects shall implement a systems management approach that formalizes and integrates the Lessons Learned process throughout the system life cycle.  All elements of the system shall be addressed (e.g., flight, ground and launch vehicle segments, hardware and software, critical ground support equipment).  All phases of the life cycle shall be considered (e.g., fabrication, assembly, integration and test, environmental testing, transportation, launch site processing, launch deployment, in-orbit check out, operations and decommissioning).  

This implementation shall include the use of tools and methodologies to support the identification, capture, and application of Lessons Learned in the system design and associated development and operations activities.

- GSFC projects shall incorporate the requirements of the Knowledge Management (KM) initiative as part of the Lessons Learned process.  The purpose of KM is to convey NASA’s focus on sharing knowledge among Projects and staff as a means to improve mission success throughout NASA.

- Project-specific implementation of the Lessons Learned process shall be documented for each project in a Lessons Learned Plan (LLP).  The LLP shall be reviewed by the SAM, approved by the PM and concurred by the FPPD Director.  The LLP shall be developed, approved and implemented early in Project formulation, no later than the mid point of the planned formulation period and prior to any mid formulation review gates imposed by the funding Enterprise (i.e., Office of Space Science Interim Confirmation Review).  The LLP is a controlled document and shall be maintained by the PM throughout the project life cycle and should be included in each Formulation Plan as well as subsequent Project Plans.

The LLP shall include:

- Introduction— Specify the Project Lessons Learned objectives and policy toward Lessons Learned.  Explain the purpose, scope, assumptions, constraints, key ground rules, and policy pertaining to the Project Lessons Learned process.

- Overview of process—Provide an overview of the Lessons Learned process and information flow; describe how the Lessons Learned process integrates and relates to other project management and system engineering activities. Include strategies for identification, capture, organization and application of Lessons Learned to be employed throughout Project life cycle.

- Organization—Show the organization, roles, and responsibilities of Program, Project, customer, and supplier key personnel with regard to Lessons Learned.  Document how team members will be trained in the application of Lessons Learned methodology.

- Process details—Provide the Lessons Learned process details and related procedures, methods, tools, and metrics.  Include here, or in an appendix, the specific methodologies to be used for identification, capture, organization, and application of Lessons Learned.  Include the process to be used for continual assessment of the value of Lessons Learned applied to the Project.  Describe how Lessons Learned information will be communicated both internally to the Project staff and throughout the NASA management chain.

- Documentation of Lessons Learned—Specify the format and data elements that will comprise the Project Lessons Learned List, how the list will be used and updated.  Tell how team members will be able to access the current list at any time. Include in the LLP the initial set of identified Lessons Learned and the action plan for application of each Lesson Learned.

The FPPD website: http://fpd.gsfc.nasa.gov/ contains Lessons Learned background information, and other sample LLP’s, information on Lessons Learned techniques and tools.

- The PM shall provide Lessons Learned training early in Project formulation to the Project team, including major partners and suppliers, as defined in the LLP.  Training in Lessons Learned is available from the FPPD Office.  PM’s and other senior systems management personnel should receive advanced training in Lessons Learned and Knowledge Management.  The SMO and Headquarters Office of Safety and Mission Assurance are sources of advanced training in Knowledge Management.

CHANGE HISTORY LOG

| Revision | Effective Date | Description of Changes |
| --- | --- | --- |
| Baseline |  | Initial Release |

Figure 3.  Lessons Learned Submission Form

| LESSON LEARNED | FILE NO. | Page of |
| --- | --- | --- |
|  | CATEGORY (Primary/Alternate): |
| TITLE/SUBJECT: | KEYWORDS: |
| EVENT DESCRIPTION: |
| LESSON LEARNED: |
| RECOMMENDATIONS: |
| ATTACHMENTS: | REFERENCES: |
| SUBMITTED BY: | PROJECT/OFFICE: | ORG./COMPANY: | LOCATION: | DATE OF OCCURRENCE: |
| TELEPHONE: | EMAIL: | SPECIALIZATION: | BUILDING/ROOM: | DATE SUBMITTED: |

Figure 4.  Description of Lessons Learned Submission Form Items

| To be provided by Submitter | Comments |
| --- | --- |
| Category (Primary/Alternate)---------------------> | Identify functional areas where the lesson falls within (see Figure 5) |
| Title/Subject | Provide a short, specific and complete reference |
| Keywords | Use terms that describe concepts to facilitate retrieval via search |
| Event Description | Summarize key events and facts, avoid attribution to individuals or organizations |
| Lesson Learned | Brief primary theme along with applicability |
| Recommendations | Specific future actions for improvement |
| Attachments | Supporting documentation associated with the lesson |
| References | Relevant documentation and/or individuals (with contact information) |
| Submitted by | Individual who prepared the lesson learned |
| Project/Office | Project or organizational activity that the originator is associated with |
| Organization/Company | NASA organization code or contractor where the originator is employed |
| Location | Site where the submitter is located |
| Date of Occurrence | Date when the event occurred |
| Telephone | Office telephone of the submitter |
| Email | Office email address of the submitter |
| Specialization-----------------------------------------> | Expertise of the submitter (see Figure 6) |
| Building/Room | Office location of the submitter |
| Date submitted | Date of the lesson submission |

Figure 5.  Categories for Lessons Learned Submission Form

| Management | System Engineering | Access to Space |
| --- | --- | --- |
|  | Agreements |  | Allocations |  | Launch Facilities |
|  | Business |  | Configuration Management |  | Launch Processing |
|  | Contracts |  | Contamination Control |  | Launch Services |
|  | External Relations |  | Environmental Protection |  | Launch Systems |
|  | Finance |  | Environments |  | Range Support |
|  | Lessons Learned |  | IRDs/ICDs/IIDs |  |  |
|  | Meetings and Reviews |  | Requirements | Operations |
|  | Organization-Staffing |  | Review Boards |  | Algorithms |
|  | Procurement |  | Studies & Analyses |  | Anomalies, Incidents, Failures |
|  | Resources |  | Verification |  | Command |
|  | Schedule |  | WBS |  | Data Acquisition |
|  |  |  |  |  | Data Dissemination |
| Mission |  | Engineering (Hardware/Software) |  | Data Management |
|  | Space segment |  | Analyses |  | Data Processing |
|  | Instruments |  | Design |  | Data Products |
|  | Observatory |  | Development |  | Data Storage and Retrieval |
|  | Spacecraft |  | Integration |  | Flight Software |
|  | Launch segment |  | Manufacturing/Coding |  | Ground Software |
|  | Flight Support Equipment |  | Materials |  | Mission Engineering |
|  | Ground Support Equipment |  | Parts |  | Mission Planning |
|  | Launch Vehicle |  | Processes |  | Operations Concepts |
|  | Ground segment |  | Specifications |  | Telecommunications & Networking |
|  | Communications |  | Test |  | Telemetry |
|  | Mission Data Processing |  | Test Support Equipment |  |  |
|  | TTC&M | Engineering Specialization | Administrative |
|  |  |  | Mechanical/Structural Systems |  | Action Items |
| Science |  |  | Electromechanical/Mechanisms |  | Contacts |
|  | Assessment |  | Electrical Systems |  | Correspondance |
|  | Calibration |  | Power Systems |  | Education |
|  | Data Assimilation |  | RF/Microwave Communications |  | Facilities |
|  | Measurements |  | Guidance, Navigation, and Control Systems |  | Human Resources |
|  | Models |  | Optical Systems |  | ITAR |
|  | Research |  | Electro-optics/Lasers |  | Library/Technical Information Services |
|  | Science Working Group |  | Microwave Systems |  | Logistics/Transportation/Supply |
|  | Validation |  | Detector Systems |  | MIS/IT |
| Science Specialization |  | Cryogenics |  | Outreach |
|  | Atmospheric Science |  | Software |  | Presentations (Internal/External) |
|  | Geophysical/Geologic Science |  |  |  | Project Support |
|  | Oceanographic Science | Mission Assurance |  | Public Affairs |
|  | Biospheric/Biologic Science |  | Independent Reviews & Investigations |  | Reports (Weekly/Monthly) |
|  | Hydrologic Science |  | Product Assurance |  | Scheduling |
|  |  |  | Problem Reporting |  | Security |
| Technology |  |  | Quality Assurance |  | Training |
|  | Apertures |  | Reliability |  | Travel |
|  | Bus Subsystems |  | Risk Management |  | Workshops |
|  | Components |  | Safety |  |  |
|  | Data Distribution |  | Software Assurance |  |  |
|  | Data Integration |  |  |  |  |
|  | Data Stream Processing |  |  |  |  |
|  | Detectors |  |  |  |  |
|  | Instrument Technology |  |  |  |  |
|  | Sensors |  |  |  |  |

Figure 6.  Specializations for Lessons Learned Submission Form

| Project/Program/Instrument Management (PM, DPM, DPMR's) | Cryogenics |
| --- | --- |
| Reliability Engineering | Materials |
| Mission Assurance Management/Engineering | Contamination |
| Flight/Ground Systems Safety Engineering | Industrial Safety |
| Systems Engineering | Environmental Protection/Engineering |
| Software Engineering Methods, Standards, Processes, and Reliability | Facilities Engineering, Maintenance, and Operations |
| Flight/Ground Engineering Data Systems - Software | Applied Math/Computational Science and Analysis |
| Flight/Ground Data Systems - Hardware | Atmospheric Science |
| Administrative Computing | Geophysical/Geologic Science |
| Mission Operations Engineering | Oceanographic Science |
| Telecommunications and Networking | Biospheric/Biologic Science |
| Mechanical/Structural Systems Development, Integration, and Test | Hydrologic Science |
| Electromechanical/Mechanism | General Business/Administrative |
| Electrical Systems Development, Integration, and Test | Financial/Resources Management/Program Analysis |
| Power Systems Development, Integration and Test | Logistics/Supply/Transportation |
| RF/Microwave Communications | Technical Information Services/Library Science |
| Radiation Effects and Component Technologies | Security |
| Guidance, Navigation, and Control Systems Development, I&T | Procurement |
| Optical Systems | Public Affairs |
| Electro-optics/Lasers | Education |
| Microwave Systems | Secretarial/General Clerical |
| Detector Systems |  |

Appendix A.  Outline for Project/Program Office Lessons Learned Plan

  - Introduction

    - Applicable Documents

  - Lessons Learned Process Overview

    - Terms and Definitions

    - Lessons Learned Process

    - Roles and Responsibilities

    - Allocation of Resources

  - Lessons Learned Identification

  - Lessons Learned Capture

  - Lessons Learned Organization

  - Lessons Learned Application

  - Lessons Learned Valuation

  - Lessons Learned Documentation and Communications

    - Lessons Learned Reports and Reporting Milestones

    - Lessons Learned Awareness and Education

    - Project Tools

Appendix A -  Lessons Learned Form
Appendix B – Project Lessons Learned Philosophy/Criteria

Appendix C - Acronyms

# Text boxes

Organize

Target

Identify

Analyze

Disseminate

Capture

Feedback

Apply