# Monthly Status Report for caCORE Product Line

# For Month of August 2008

# Key Accomplishments

- Current

caGrid

CORE

The main focuses of this month’s effort were on development of feature enhancements targeted for caGrid 1.3.

- 5 bugs closed, 2 new unfixed bugs reported, 9 feature requests closed, 9 new unimplemented feature requests submitted.

- The article we co-Authored for the special issue on e-Science of IEEE Computer magazine will be featured on the cover.

- The first phase of scenario testing was completed by the QA team.

- Investigated performance/usage issues with the production grid.

- Finalized the first draft for caGrid 1.3 scope and began work on establishing timelines for the project plan.

- Implementation of features for caGrid 1.3 including ws-enumeration support in FQP, Introduce CSM and GridGrouper authorization plug-ins, GME enhancements, and secure discovery of Authentication Services.

    - Continued execution of deliverable “C.1.D.4 Gforge Site” in the form of:

      - Creating and updating the status appropriately of all Bugs and Feature Requests on the Tracker section (http://gforge.nci.nih.gov/tracker/?group_id=25)

        - Bugs Opened/Closed, August 2008:

| 16319 | cog-jglobus.jar file is not updated in syncgts globus container deployment | Closed |
| --- | --- | --- |
| 16137 | Introduce Grid Grouper PDP requires default proxy to connect to Grid Grouper | Closed |
| 15757 | Gaards UI throws an error popup that makes the UI unusable | Open |
| 15609 | Multiple GAARDS documentation pages reference the &quot;ui&quot; target of projects which no longer exists | Open |
| 14860 | Introduce Log Viewer hangs in certain scenarios | Closed |
| 13952 | Error importing a schema that imports other schemas. | Closed |
| 10897 | caCORE (version 3.1,3.2,3.2.1) backed data services don't handle queries with single quotes in query parameters | Closed |

        - Feature Requests Opened/Closed, August 2008:

| 16339 | Installer to add execute permissions to scripts used by prerequisites it installs | Open |
| --- | --- | --- |
| 16336 | Ability to discover Terminology Services (and their metadata) | Open |
| 16328 | Ability to create Terminology Services within Introduce and deploy to grid | Open |
| 16274 | Data service creation wizard has mac issues. | Open |
| 16192 | DCQL foreign association on multiple attributes | Open |
| 16065 | Websso configuration files should be better template | Open |
| 15912 | Add support to resource property helper for client side authorization. | Open |
| 15822 | Reformat GAARDS UI to display properly on the MAC | Open |
| 15820 | Add Account Auditing to Dorian | Open |
| 15819 | Add the signing certificate for SAML Assertions to the Authentication Service Metadata. | Open |
| 15605 | CSM Introduce Authorization Extension | Closed |
| 15604 | Grid Grouper Introduce Authorization Extension | Closed |
| 15602 | Create Introduce Authorization Extension | Closed |
| 15461 | Document UI changes to ja-sig CAS | Open |
| 15214 | Grid Authentication Manager/Security Integration | Closed |
| 15211 | GME Namespace implementation in SDK | Closed |
| 14864 | syncGTS to have sync policy extended to allow for describing a portion of the fabric to be trusted | Closed |
| 13615 | Ability to start SyncGTS as a daemon from Command line | Closed |
| 12968 | Reorganize testing resources to reduce size | Closed |
| 7171 | AuthenticationService needs integration test | Closed |

    - Worked with the caCORE SDK team on design and planning on various integration efforts:

      - Continued to support the design the integration of Grid Security (https with proxy certificates) into the SDK Application Service as a means of user authentication.

      - Created the common project for CQL and its Hibernate query implementations which will be jointed developed by the SDK and caGrid teams, and will facilate CQL query reuse on the grid and with the SDK APIs. (http://gforge.nci.nih.gov/projects/cql/)

    - Continued support of Santhosh Garmilla regarding the design of new WebSSO features.

    - Friday August 22nd, had the CQL2 technology preview kickoff, and began to identify formal and informal participants.

    - Worked with CBIIT’s System’s team to investigate file system and CPU usage resource issues with the Global Model Exchange service, and identified the cause to be multiple deployment of the caGrid portal using a new feature of the portal which made excessive schema lookups.  The portal configuration was changed to lessen the load and the overall process will be addressed in the upcoming portal release.

    - The QA team successfully completed the first round of scenario testing and identified one new unreported bug (#16319), which has since been fixed.  We are meeting in September to debrief and discuss the timing and process for the scenario testing of caGrid 1.3.

    - Installed and configured the new testing integration server (gridtest.bmi.ohio-state.edu).

    - Worked with caGrid Project Manager to complete the first draft of the caGrid 1.3 scope, with the actual timeline to be finalized in September

- Investigating performance issues surrounding deserialization and serialization of large data sets.

    - Beginning the design process for Transfer Service metadata to provide additional information about data being transferred out of band via the service

    - Provided CBIIT System’s Team procedures for changing caGrid core services’ database passwords.

GAARDS:

      - Added the ability to all GAARDS client APIs to specify client-side authorization policies.  This will be leveraged by the new process for discovering trusted identity providers from Dorian.

      - Added support to the GAARDS UI for discovery of trusted identity providers, as well as the ability to prompt for multiple authentication mechanisms (using the new authentication profile metadata).

      - Implemented necessary database upgrade process for the Dorian, to add support for trusted identity provider management to existing Dorian installations.

Introduce:

      - Fixed bug #16137 which prevented the GridGrouper authorization plugin from using the correct credential (the service’s) to lookup client membership in a group; this was due to an undocumented Globus behavior, which we communicated to the Globus team as an issue.

      - Completed implementation of the authorization extension plug-ins for GridGrouper and the CSM.

Data Services:

  - Completed initial implementation of ws-enumeration support for the FQP service, continued design and implementation for CDS and transfer integration.

  - Created additional system tests for FQP which exercise the ws-enumeration capabilities, and both synchronous and asynchronous queries.

Metadata

  - Decided caGrid 1.3 will make steps toward Gold compatibility of core services by first registering key information models into the caDSR, such as the common metadata models and CQL.

  - Continued work on the new Global Model Exchange (GME) service, implementing a model for batch schema bundle downloads, and creating additional unit tests.

- Configured the new Dell server (gridtest.bmi.ohio-state.edu) for integration testing

    - Continued execution of deliverable “C.1.D.5 Technical Support” in the form of email support via the caGrid User’s email list, and meetings with project teams

      - 51 Threads with 227 messages on the caGrid User’s list for August 2008 (https://list.nih.gov/cgi-bin/wa?A1=ind0808&L=cagrid_users-l)

caGrid Portlet

  - Attended caGrid project meetings.

  - Attended caGrid Portal meetings.

  - Participated in design meetings.

  - Attended iteration planning meetings.

  - Prepared for and attended caBIO portlet meetings.

  - Met with ONIX Portal team to discuss potential collaboration opportunities

  - Prepared for and attended Ontology Query working group meetings

  - Actively monitored users list and responded to user queries.

  - Provided production support

  - Wrote use cases for next release (2.0.3)

  - Fixed bugs 15253, 15025, 15824, 16187, 16420 and tested the fixes.

  - Worked on RFE 16305.

  - Fixed End Users guide

  - Installed training instance of Portal.

  - Worked on several other development tasks.

  - Coordinated with the QA for testing.

caCORE Product Line

  - Created template for CORE TPM’s for their project plans

  - Created Change Control Support (CCS) Guidelines & Procedures Document

  - Conducted the weekly CCS meeting, to discuss approach and tactical to-dos for vision

  - Created the Master Story list for CORE

  - Completed consolidation effort of  the GME Wiki Pages

  - Coordinated with LexBix and UCD teams for topics of discussion on Developers calls.

  - Coordinated COPPA dependencies and Issues Meeting

  - Updated the Master Story list for CORE

  - Updated the Master Story list for additional tools

  - Coordinated to get Use Cases for Service Loader

  - Coordinated with TPM’s to get vision at a high level

  - Setup Meetings for EA Excel Plug In’s and COPPA Pre-Review Model

EVS

  - caBIG Support.

- caDSR Support:

  - caMOD v2.5 rv5: finished, file returned

  - GP v1 rv1: finished, file returned

  - DMR v1 rv1: finished, file returned

  - LexBIG v2.3 rv1: in progress

  - Vocabulary Develoment

    - NCIt editing

  - caNanoLab (caBIG project)– preliminary modeling of nanotechnology related instruments and techniques for caNanoLab. Waiting for SME feedback from NCL and user group.  Spreadsheets sent to Stanford and Georgia Tech for review and feedback.

  - Nanotechnology – other – met with WashU re: their draft implementation of nanoparticle ontology using upper level BFO ontology.  First version for publication anticipated end of summer.

  - PMRP (Personalized Medicine Research Portal)– Entered 1st, 2nd and 3rd groups of PMRP genes and gene products into TDE, NCI Protégé and BiomedGT Protégé.  (Syndromes mined from OMIM related to brain). Sent final group back for QA. Also work on diseases and syndromes modeling related to terms from PMRP.

  - Ligand Binding gene product work continuing.

  - NCI Cancer Bulletin reviewed for new content.

  - FDA: UNII Code terminology continues in progress (new batch arrived);

  - CDASH  (5 concepts added for CDISC)

  - SEND – some new concept creation

  - ISO – unit of measurements review/ comparison for ISO consortium

  - ICH Unit of Measruement QA/ editing

  - CDISC: Package 2 & 3 work; SDTM anatomical locations;

  - Drug Terminology – Heavy work on restructuring drug tree, with more emphasis on therapeutic drug class; work on adjuvant structure; work on drug class measurement tree.

  - Routine work on Lab Procedure, Findings, Anatomy.

  - Dual editing ongoing in TDE and Protégé.  Daily classifications; Weekly PROMPT and TDE vs Protégé baseline reviews.  (Last TDE baseline Sept 12).

  - NCI Metathesaurus Content and Production:  NCI2008_04, 5 and 6D inserted and edited.  PDQ2008_06 editing completed.  New version of NCI Meta containing Radlex 2.0 exported (to go to production early Sept).  Update for RadLex 2.0 in progress following additional data cleaning by RSNA.  UMLS2007AC test insertion in progress.

  - Product Support

    - NCI Thesaurus version July 2008 (08.07d) is on Production DTSRPC server at ncidts.nci.nih.gov, port 6550 or http://nciterms.nci.nih.gov .History files are available on anonymous ftp server at ftp://ftp1.nci.nih.gov/pub/cacore/EVS/. Summary files are available on the intranet at https://ncicbintra.nci.nih.gov/intra/caCORE/evs/Thesaurus_Summary/

    - NCI Meta – The NCI Metathesaurus, export date July 28th, 2008 (tracking version NCI2008_03D), is in production.  This version contains RadLex 2.0, which incorporates the RadLex Playbook project.

    - GO Aug 2008 on production.

  - Project: caCORE/EVS API (highlights)

    - EVS API 4.2 release candidate and testing in August.  Second release candidate going to QA in September.  Has changes to model to allow grid services compatibility.  Will be the first release of the LexEVS grid service. Planned release for early-mid Oct.

    - LexBIG 4.0 model in silver compatibility review.

  - Bioportal

  - Bioportal tweaked to wirl with EVS API 4.2.  Some new functionality for exact matches and searching by property.  Release with the EVS API 4.2 release cycle.  Still in Dev as of early Sept.

  - Terminology Open Portal – Bioportal 2 was released by Stanford.  Meeting re: Bioportal 2 architecture discussion and applicability to TOP being scheduled for September.

  - Project: Protégé OWL/NCI Edit Tab and BiomedGT Wiki

    - NCI Protégé 1.2.3 patch released in late August. Release notes available on GForge wiki and GForge, and NCI Thesaurus editors are doing parallel editing with TDE for final transition Sept 15. Patch included performance enhancements for classification (more work done on server instead of client) and some bug fixes/ minor enhancements.

    - Continued planning re: Protégé 2.0 with Protégé 4.  (Not a go yet.)

    - NCI Protégé 1.3 release testing in Sept for release in October to incorporate database inclusion (and other related changes) to enable federation in database mode.

    - Semantic Media Wiki / BioMedGT Wiki

      - Supportied CTCAE update project through first cycle.  Preparing reports for steering committee and MedDRA.

      - Added few additional features/ checks, and added help pages.

      - Wiki build minor tasks left.

      - Moved to 3 tier production until official release (still in alpha / beta mode).

      - Planned for fall release cycles, including work flow enhancements and integration with Protégé.

caDSR

Product Development

  - caDSR 4.0 Iterations

Development work during August 2008 was primarily to correct defects identified during QA testing and to streamline the deployment process

    - caDSR 4.0.0.0

      - Database and Domain Model:

        - 6 database deployments were applied to the QA database as a consequence of bugs found in other tools or as a result of issues with the database deployment itself; a full scale installation test was conducted on QA before submitting for Stage deployment

      - Form Builder

        - Deployed 3 builds to address QA problems and improve integration with Object Cart

      - Semantic Tools

        - Continued work on GME enhancements (SIW 4.0.0.1), including documenting test cases

      - CDE Browser

        - Corrected defects identified in QA and created database deployment script for tool options entries particular to CDE Browser

      - Administration Tool

        - Minor issues raised from QA testing will be fixed in a subsequent release

      - UML Model Browser

        - Completed QA bug fixes

        - Used JProfiler to record performance statistics on UML Model Browser queries and on the display of the query result sets; preparing final report

      - Freestyle Search

        - No significant activity during August 2008; development, QA testing, and successful AppScans had been completed earlier.

      - Sentinel Tool

        - No significant activity during August 2008

      - Curation Tool

        - Completed 4 QA bug fixes; one minor issue will be fixed in a future release

  - Operations and Maintenance / Troubleshooting

      - Completed Bugs (QA Testing Bugs are not counted) and Feature Requests

| Tracker Items | Admin Tool | Concepts Loaded / Updated | Sentinel Tool | Freestyle Search | caDSR Database | SIW / UML Loader | Curation Tool | CDE Browser | UML Model Browser |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bugs | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Feature & Support Requests | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

  - Other Work

    - caDSR Wiki

      - Continued to post and refine content

    - caCORE Project Management

      - Worked with Sapient contractor to coordinate schedule development across caDSR, caCORE SDK, EVS, and caAdapter

      - Began weekly project management coordination meetings ("Change Control Support Group")

    - Metadata Quality Improvement

      - No significant development work; the Content team continued to review/assess initial findings and to formulate business rules to guide further content consolidation

    - User Centered Design

      - UCD representatives presented their findings and assessment regarding their review of CDE Browser / Form Builder to a series of Friday caDSR Reviews

    - Assessed relevance of HL7 Clinical Document Architecture (CDA) ballot issues to caDSR initiatives (found not relevant); further looked into CDA as possible basis for caDSR Forms metamodel

  - Led caDSR Team Technology Exchange meetings and reviews

  - Acted as liaison between Confluence Wiki implementation team and caCORE development team

  - Reviewed GForge trackers for completeness

  - Completed bug fixes as a result of QA testing for Sentinel Tool v4.0

  - Completed bug fixes as a result of QA testing for Curation Tool v4.0

  - Coordinated tasks between development, QA and Systems teams for caCORE v4.0 release

  - Began documenting the caDSR API benchmarks to take official performance timings

  - Continued coding enhancements to Sentinel Audit Reports

  - Began documenting vocabulary metadata requirements for the Mayo EVS team

  - Reviewed the caDSR domain model

  - Working with NMDP on process and performance improvements for caDSR Tools

  - Worked on the Context Privileges issue; tested the updated stored procedures

  - Reviewed CDE Curation Tool help documentation; provided updated screenshots for the documentation team.

  - MDR Futures

Object Cart

- Completed preparations for Stage deployment.

MDR

- Created presentation on state of MDR to COPPA.

- Identified stakeholders for Registry Services Use Cases

- Created summary for Registry Services and direction.

- Clarification of MDR direction regarding COPPA and Services

MDR Warehouse

Tuning Tips for Materialized views

- Performed research to find tunings tips for Materialized views, using the Oracle documentation and the various documents suggested by Dave

- Created a document reporting on the tuning tips that will be implemented and tested for the warehouse

Warehouse Performance Testing on Oracle Platform

    - Created a document detailing a testing methodology for measuring the performance of the three Oracle implementations of the warehouse

    - This methodology was reviewed with Denis Avdic, Ye Wu and Patrick Conrad, in a meeting on 7/31.

    - Started work on tuning the objects and queries within each implementation, using the SQL Access Advisor.

    - Worked on researching the “mechanics” of view queries and Oracle queries in general, in particular the role of the Cost Based Optimizer (CBO).

    - Setup the three oracle schemas on local machine and DEV to run the performance tests.

    - Ran tuning sessions, using the SQL Access Advisor tool from Oracle, to tune the workload queries for the MDR performance tests

    - Implemented tuning suggestion from Advisor, prior to running the tests

    - Collaborated with Ye Wu (QA Manager), to setup JDBC connections and requests in JMeter, for test runs to measure query performance across the three Oracle implementations of the warehouse

    - Executed the JMeter tests on local machine and the MDR warehouse development environment.

    - Put in a DBA request for privileges to have more DEV access for the warehouse schemas.

    - Added a shared pool flush of the Oracle cache to alleviate the SQOL caching effect on the performance of the test queries.

    - Started work on documenting the performance results from the JMeter test runs

    - Completed Warehouse Performance Testing by rerunning invalid JMeter runs and gathering Oracle ADDM reports for documentation purposes.

    - Worked on documenting the performance results from the JMeter test runs for the three Oracle implementations of the warehouse.

    - Document was reviewed on 8/13 by Denis Avdic (MDR Lead Developer), Patrick Conrad (Oracle Developer) and Steven Hunter (QA Manager).

    - Met with Dave Hau on 8/14 to present and review the document.

    - Updated the MDR Wiki and Gforge by adding all the latest MDR Documents.

    - Completed a Best Practices Document to detail the Lessons Learned from the MDR warehouse performance testing. Document was completed on 8/18.

    - Following a meeting on 8/20, about the need for a dedicated MDR instance and server for development and testing purposes, researched the Oracle documentation to find notes on the privileges needed to support materialized view replication for separate source and target schemas on a shared instance. These documents had been requested by the DBA team.

Warehouse Performance Testing on MySQL Platform

    - Researched an appropriate open source tool/utility that could be used to replicate data from Oracle to MySQL.

    - Researched and provided hardware and software specs for an Oracle sandbox server that would be configured for warehouse database development and testing.

    - Performed some research to find ways to perform seamless heterogeneous replication between Oracle and MySQL, including heterogeneous database connectivity services, Oracle streams, etc….

    - Started testing on the configuration of an Oracle heterogeneous service, called HSODBC to load tables in a MySQL database from within and Oracle database

    - Completed work on creating an ETL process, using MS-DOS batch scripting, to load the MDR warehouse data on a MySQL database, from an Oracle transactional system equivalent to caDSR.

    - Created and ran tests in JMeter to measure the performance of the MDR Warehouse on the MySQL platform.

    - Started Documentation for the warehouse MySQL ETL Load process and the results of the performance testing.

caDSR Training

- Updated caBIG CBIIT Training Team tracker spreadsheet

- Conducted web-based training sessions of caCORE Training ( Course 1072, 1073, 1062, and 1063)

- Updated all caCORE and caDSR FAQ pages on the Confluence Wiki

- Generated a draft template for Quick Start guides in MS Publisher format

- Updated one-pager content on the Confluence Wiki

- Generated email templates to support the new automated use of the LMS for caBIG Developer Boot Camp registration and tracking

- Reviewed and finalized the transcript for the caCORE SDK portion of the caBIG Developer Boot Camp

- Updated the caCORE Training Schedule on the NCICB website

- Worked with caBIG website development team to update the caBIG website with links to the caCORE training curriculum

- Finalized the workflow process diagram of how the LMS will be integrated into the caBIG Developer Boot Camp registration process; worked with LMS team to implement the process

- Documented caBIG Developer Boot Camp pre-requisite recommendations for the India folks

- Generated new draft caCORE Course: Using the Common Logging Module

- Generated new draft caCORE Course: Using the Common Security Module

- Completed scripting for caBIG Annual Meeting presentation on caGrid (caCORE Course 3010)

caAdapter

- Tools Suite Support  (version 4.0)

  - Addressed questions from users and provided technical support

- caAdapter MMS v4.1

  - Finalized the User’s Guide document

  - Integrated the new online help system with the module

  - Finalized the separation of the module to be released as a stand-alone tool.

- UCUM SDK (Unified Code for Units of Measures)

  - Updated the design document

  - Began the development of the construction and validation modules

- caAdapter Mapping and Persistence Service (CMPS) Module

  - Finalized the CMPS Scope Document

  - Finalized the Use Case Document

  - Finalized the Software Requirements Specifications document

  - Performed technical analysis on various schema types and data types to be supported by the new module

  - Developed the Software Design document

  - Began the development tasks

- HL7 v3 Normative Edition 2008

- Inspected the newly released Normative Edition 2008

- Performed gap analysis to identify the modifications needed for caAdapter to support the new normative edition

- Began making the modifications to the caAdapter code to accommodate the new normative edition

CSM/CLM

- CSM 4.1 Iteration 2 Implementation

After completion of CSM 4.1 Iteration 2 scope and release planning, the CSM team resumed implementation of Iteration 2 requirements.

- CSM GAARDS User Migration Module

CSM team has completed the implementation and testing of CGMM.

- Support for Bundles and other Teams – Ongoing

The CSM / CLM team provided support by solving various tickets which were received by Application Support.

caCORE SDK

- Support – Provided email and onsite support to various customer queries including caNano, caBIO, caDSR, caIntegrator and others

- Grid Authentication implementation - Implemented grid based authentication in the SDK generated system. The implementation involved in using grid infrastructure to obtain user’s grid credentials and then subsequently passing those credentials to the SDK generated system. The SDK generated system uses the grid credentials to establish SSL between client and server and subsequently for the authorization purpose as well.

- GME Namespace implementation - Completed implementation for the GME namespace based XSD and XML mapping file generator. The work involved in using the specifications developed by consensus among several development teams including cagrid, SIW, caAdapter and SDK team.

- CQL Integration - Started integration of the CQL in the SDK. This implementation will allow the SDK users to write query in CQL format and seamlessly migrate on the grid environment

- Permissible Values – Modified the XSD generator to include constraint on the permissible values. This is an optional feature which can be enabled based on the user’s input from the configuration file. When enabled, the validation configuration files are used to generated restriction list in the XSDs

- Validation – Communicated with the caDSR and caTissue team to identify the requirements for the validation in SDK. The communication involved 1) getting a list of the values from some source like flat file, XMI or caDSR and 2) generating the system with validation rules embedded in it. The implementation of this feature has been postponed to the next release of the SDK to ensure all the requirements gets captured and implemented in appropriate manner.

Planned

caGrid Portlet

- Fix show stopper bugs.

- Gather and prioritize requirements for the next release (2.0.3) thru meeting with stakeholders

- Develop use cases for new requirements

- Implement new use cases

- Provide production support for the current version

caCORE Product Line

  - Maintain Integration Master Schedule for all products across caCORE

  - Solicit & Implement feedback from Managers Scope Document

  - Create COPPA/CORE HLP based on dependencies and milestones identified

  - Update Master Story List with All Managers Input for CCS Meeting

# EVS

# NCI Thesaurus Content:

# Continue same projects and routine editing.  Heavy work on drug hierarchy.

# NCI Metathesaurus Content

    - Finish MTH2007AC insertion.

    - Finish export with June 08 NCI Thesaurus

    - Insertion of Radlex2.01 (update)

    - MTH 2007AA test insertion.

BiomedGT Content:

    - Continue Gene product work, semantics of BiomedGT, continue work on binning content under upper level ontology;  Meet with nanotech group, continue work with CTCAE update group.  Follow up with Pitt re: use case in September.

# Project: NCI Protégé Software

# 1.3 testing/ early QA

# NCI Thesaurus editing final transition from TDE to Protégé. (Sept 15)

# Iteration 3 and start 4 for BIomedGT wiki and workflow (see confluence wiki)

# caDSR

Product Development

caDSR 4.0

°	Complete QA testing of caDSR 4.0.0.0 release and conduct coordinated deployment to Stage

°	Seek CIT approval for NCI firewall exceptions needed to open Stage, Production and Sandbox URLs for public access

Other / Future Releases

°	Implement automated testing in support of caDSR development activities

°	Implement automated deployment  for remaining tools using manual deployment

°	Complete scope review for next caDSR increments

  - Monitor connections on all tiers

  - Continue to track user feedback and report bugs in GForge for all tools

  - Deploy Curation Tool 4.0 to STAGE

  - Deploy Sentinel Tool 4.0 to STAGE

  - Deploy Freestyle 4.0 to STAGE

  - Review GForge trackers to define candidate items for caCORE 4.0.0.1 scope

  - Begin working with users to document 4.1 requirements; develop full use cases where appropriate

  - Begin creating 4.1 scope and requirements documents for CDE Curation Tool, caDSR Sentinel Tool and Freestyle API Search

  - Begin design discussions for transitioning Create Classification Scheme functionality into the CDE Curation Tool

  - Develop plan to incorporate more automated testing with JUnit

  - Develop caDSR tools architecture evolution plan

  - Participate in User Acceptance Testing for the caCORE v4.0 release

MDR Futures

Object Cart

- Support deployment to stage and production.

- Grid Service development

MDR

- Complete Common Registry Service draft.

- Develop prototype service as a baseline for further specification refinement.

MDR Warehouse

- Continue Work with the caDSR/caMDR developers to add/review/update all MDR data Architecture  documentation

- Continue work on caMDR Iteration 2 tasks: Complete the documentation and design of the Warehouse ETL implementation on the MySQL platform, Test the performance of the MySQL ETL implementation, Identify new Uses cases for the warehouse, Modify the warehouse model to accommodate implementation of new use cases, create and load environment to test updated warehouse model

caDSR Training

  - Prepare for caBIG Developer Boot Camp III (October 21-22 – DC)

  - Complete scripting for caBIG Annual Meeting presentation on caGrid

  - Convert caCORE Course 1061: Curating Metadata from Forms Session 1 into Articulate to support self-paced format

  - Convert caCORE Course 1062: Curating Metadata from Forms Session 2 into Articulate to support self-paced format

  - Convert caCORE Course 1071: Curating Metadata from UML Models Session 1 into Articulate to support self-paced format

  - Convert caCORE Course 1072: Curating Metadata from UML Models Session 2 into Articulate to support self-paced format

  - Implement new automated registration and reminder email process in the LMS to support caBIG Developer Boot Camp registration and pre-requisite tracking

  - Update caCORE Course 1010: caDSR Implementation of ISO/IEC 11179 with current content and more examples of caDSR data elements

  - Document information learned at the 2-day Camtasia training; present at the next CBIIT Training Team meeting

  - Revise and update self-paced course: 2010: Using the caCORE SDK

  - Begin reviewing content for caBIG 3rd Party Compatibility Reviewer training (Nov 2008)

# caAdapter

# o

# CSM/CLM

- CSM 4.1 Iteration 2 Early adopter release

The CSM team will be working on providing the Early Adopter release to go with the caCORE SDK early adopter release.

- CSM GAARDS User Migration Module Early adopter release

The CSM team will provide the Early Adopter release to other teams.

- CSM 4.1 Iteration 2 Implementation

After completion of CSM 4.1 Iteration 2 scope and release planning, the CSM team will implement Iteration 2 requirements.

- CSM 4.1 Iteration 2 Quality Assurance Tests

After completion of CSM 4.1 Iteration 2, the CSM team will provide support to QA for testing the CSM v4.1. The QA team will resume their test execution for CSM v4.1.

- Post Release Support

The CSM Team will provide Post Release Support to the CSM, CLM and CSM SDK release.

# caCORE SDK/API

- Provide support to the SDK users

- Modify the Grid Authentication implementation to meet the security requirements

- Complete CQL integration

- Defect fixes

- Work with the QA team to prepare the test cases for SDK 4.1

- Provide support to the QA team to perform testing

- Start working on the documentation for the SDK 4.1

# Outreach and Communications

- Current

caGrid

- Continued participation in the Security Working Group weekly meeting

- Continued participation in the Gold Compatibility Review Working Group as the lead of the API subgroup

- Continued work with the Information Models subgroup lead to detail issues surrounding UML naming conventions and their impact on the Gold reuse requirements in a whitepaper.

- Continued participation in the Analytical Services Best Practices Working Group and the High Throughput Data Working Group of the ICR workspace.

- Investigating performance issues surrounding deserialization and serialization of large data sets.

- Beginning the design process for Transfer Service metadata to provide additional information about data being transferred out of band via the service.

- Met with the Community Development and Improvement of Globus Software (CDIGS) team to discuss caGrid/caBIG’s needs of the Globus infrastructure and relayed our opinions on the priorities for future releases.  This spawned two additional meetings 1) to discuss the short term concerns with the Index Service’s scalability

- Met with caGrid Knowledge Center and the CBIIT build automation teams to discuss plans for a central Ivy repository for caBIG and the needs and options for robust installers for caGrid, for use by end-users as well as for the production grid deployment.

- Participation in weekly developer, weekly management, bi-weekly caGrid Status, and bi-weekly Architecture Workspace teleconferences, and monthly caGrid User’s calls

caCORE Product Line

# EVS

# Continue nanotech, CTCAE, CDISC, FDA and other outreach as before.

caDSR

o	Weekly caDSR Review Meetings (Fridays)

- Participated in caCORE Bi-weekly Team meetings

- Participated in caCORE Bi-weekly Software Meetings

- Participated in NCI CBIIT Change Management Meetings

- caDSR Team Technology Exchange meetings and reviews

- Participated in Automated Build & Deployment meetings

- Participated in management and technical discussions regarding the caDSR Tools current and future development

- Acted as liaison between Confluence Wiki implementation team and caCORE development team

- Attended meeting with Mayo EVS team to discuss LexBIG, Vocabularies, and the caDSR.

- caDSR/MDR Engineering Meeting, Tuesdays, biweekly.

- MDR Project Status Meeting, Mondays

- Forms builder design review meeting, 8/6

- MDR presentation for COPPA, 8/7

- Review meeting of the warehouse Performance testing document, with  Denis Avdic (MDR Lead Developer), Patrick Conrad (Oracle Developer) and Steven Hunter (QA Manager), on 8/13

- Presentation of the completed warehouse Performance testing document, with Dave Hau, on 8/14.

- Meeting on 8/20, with  Dave Hau, the DBA Team represented by Vanessa Caldwell and Yeon Choi, the Systems team represented by Doug Hosier, about the need for a dedicated MDR instance and server for development and testing purposes

# caDSR Training

# Participated in bi-weekly caCORE Context Administrator’s Meetings

# Participated in bi-weekly caBIG VCDE Workspace Meetings

# Participated in bi-weekly caBIG Documentation and Training WS calls

# Participated in weekly caCORE Training Team calls

# Participated in LMS Change Management calls

# Participated in caBIG CBIIT Training Team calls

# Attended Camtasia 2-day training course (August 14-15, 2008)

# caAdapter

# Participated in the caCORE status meetings

# Conducted the caAdapter MMS training at the caCORE Boot Camp

# Supported caAdapter users with various caAdapter questions

- Planned

caCORE Product Line

EVS

caDSR

# Weekly caDSR Review Meetings (Fridays)

# Form Builder meetings

  - Continue to track user feedback and report bugs in GForge for all tools (ongoing)

  - Continue to provide support in resolution of caDSR user questions (ongoing)

  - Continue to participate in other caDSR and caCORE weekly and bi-weekly meetings

  - Continue to meet regularly with Mayo and EVS team to discuss LexBIG, Vocabularies and the caDSR

  - caDSR Training

# -	Continue to participate in weekly caCORE training status meetings

# -	Continue to participate in monthly caBIG CBIIT Training Team meetings

# -	Continue to participate in other caCORE and caBIG bi-weekly meetings

# -	Attend CTMS Face to Face mtg (Sept 8-9, 2008)

# -	Attend VCDE/ARCH Face to Face mtg (October 26-27, 2008)

# -	Prepare for caBIG Developer Boot Camp III (October 21-22, 2008)

# -	caBIG 3rd Party Compatibility Reviewer training (Nov 2008)

# Issues and Recommended Solutions

# caGrid

# A few bugs in the 1.2 release have been identified, work-arounds posted, and fixed.  But we may want to post a cumulative bug fix 1.2.1 point release.  We should work with QA team to establish a QA process first

# A new requirement of wanting core services to be Gold compatible was identified.  This will affect the timeline and scope of next release, and may have backwards compatibility ramifications

  - We should be scoping the next release during the current release process, as the development team starts to work on new features as soon as the current release stabilizes.  This may help address the fact the following release’s project plan is often not done until months into the development cycle.

# caCORE Product Line

# caDSR

  - The CIT vulnerability assessment will be performed on the Stage tier; any vulnerabilities found will need to be fixed and redeployed through DEV and QA for further assessment.  A 10 day contingency development timebox has been incorporated into the caDSR 4.0.0.0 deployment schedule to allow for this work.   If the fixes take more than 10 work days the Production deployment date will slip.

  - Work with Systems team to implement further automated deployments

caAdapter

- Continue to support the Federal Adverse Event Task Force (FAET) project to use/extend the caAdapter HL7 v3 capabilities on the project

- Continue to participate in the caCORE status meetings

- Conduct caAdapter demos upon request

# Conferences and New Items

# caCORE Product Line

# .