## -CHANGE REQUEST COVER SHEET

## Change Request Number: 06-25

## Date Received: 3/7/06

Title:  GAO Findings Response and Standard FAA Program Milestones

# Name: David Woodson

Routing Symbol:  ATO-A, Acquisition and Procurement Policy Branch

Phone: 267-7601

Policy OR Guidance: Guidance

Section/Text Location Affected: Multiple

Summary of Change: This change proposal includes the following:

Guidance

- Establishes guidance for evolutionary product development.

- Establishes guidance for the FAA’s knowledge-based product development process for systems.

- Establishes guidance that identifies and defines standard program milestones for systems (sheet 1) and facilities (sheet 2).

- Adds to the introduction of the contracting module in the developmental hardware and/or software process flowcharts the requirement to include in any prime contract for system development those deliverables necessary for an investment program to satisfy decision criteria for transition from product integration to product demonstration and from product demonstration to full production.

- Modifies the development process flowcharts in FAST for developmental hardware and/or software to add the product demonstration decision.

- Modifies the implementation process flowcharts in FAST for developmental hardware and/or software to add the production decision.

Reason for Change: GAO Report 05-23, FAA’s Acquisition Management Has Improved, but Policies and Oversight Need Strengthening to Help Ensure Results, made the following recommendations for improving the FAA Acquisition Management System:

- Develop explicit written criteria for key decision points called for under best practices 1, including the capture of specific design and manufacturing knowledge

- Require corporate executive-level decisions at these key decision points (before an acquisition moves from integration to demonstration and again before it moves to production)

1 GAO Report 02-701, Best Practices, Capturing Design and Manufacturing Knowledge Early Improves Acquisition Outcomes.

The FAA Acquisition Executive agreed to implement the decision points and associated criteria, but stated that the decision-maker would be the Vice President or Director of the implementing service organization, as appropriate.

The change request also includes standard FAA program milestones requested by the ASAG Secretariat.

Development, Review, and/or Concurrence: Policy and guidance was developed by the GAO Response Team, established by the ASAG, with representatives from ATO-A, ATO-F, ATO-P, ATO-E, ATO-T, ATO-W, and ATO Quality Assurance.

Target Audience: AMS workforce

Potential Links within FAST for the Change: Multiple links between the new policy and guidance.

#### Attachments: KBDM – EPD Policy 02-06, KBDM – Final Investment Decision, KBDM – Final Investment Analysis, KBDM – Solution Implementation, KBDM Guidance R6, Evolutionary Product Development Guidance, KBDM – Contracting Activity Description, KBDM – Product Demonstration Decision, KBDM - System Integration Activity Descriptions, Program Milestones R3.

### ASAG Briefing Conducted: 3/7/06

ASAG Responsibilities: Review, comment, and endorse.

System Process Flowcharts / System Development Work Activities (Revised 10/2005)

Industry / Government Partnership

System development work activities span the period from Investment Analysis to the completion of the Design Qualification Test when the government accepts the developmental product from the contractor and authorizes field implementation. The most important event in this entire process is selection of the developmental contractor and formation of the government / industry partnership. Both the government and contractor are stakeholders in the process. It is vitally important to establish and maintain a positive working relationship. Neither can succeed without the other, and each has its own challenges and constraints.

The government is the customer and senior partner in the enterprise. The government brings all team members to the table and integrates the diverse activities associated with system development, implementation, and lifecycle support. The focus of its agent, the Product Team, is technical leadership, the government / industry partnership, and overall program integration and management. Contractors and subcontractors, on the other hand, focus on the very detailed engineering aspects of the system and its interfaces.

Development contractors are faced with certain very real constraints that the Product Team must allow for. Companies cannot afford to have large teams of engineers sit idle waiting for a contract they may not receive. A significant amount of time is needed after contract award to form the developmental team. This effort is especially important during the initial phases of a system development, and is seldom taken in to account by the government when planning contract schedules. The Product Team needs to recognize this condition and allow time for the contractor to 'gear up'.

Government planners must also allow adequate time for a thorough analysis of requirements. In an effort to meet unrealistic early milestone dates, contractors often short change this analysis and fail to achieve a clear, mutual understanding of requirements with the government. Studies have shown conclusively that omissions occurring in the requirements analysis phase have a disproportionately greater effect on program cost and schedule than errors occurring in later phases.

Management and Assessment of the Engineering Development Process

Programs rarely fail because of deficiencies in technology. Most failures stem directly from inadequate management. Everyone involved in program management must take a "proactive" role to ensure the deployment of a successful system. Each government employee must think beyond his or her individual piece of the system and take action to identify and meet challenges before they enlarge into serious problems. It is tempting to get down into the details and sometimes it is necessary. But Product Team members must take a broader view, and should perform the critical higher level tasks of managing, assessing, integrating, and taking action to solve problems when they arise.

It is critically important for the Product Team to insist on successful completion of early development activities, such as design of the system architecture and completion of critical design, and not allow the program to progress for the sake of "maintaining schedule". Proceeding to such activities as source code development without a sound overall system / software architecture usually results in a great deal of fruitless work, and has resulted in complete failure of entire acquisition programs.

The key to a successful system acquisition program is the integration of all associated engineering disciplines into an efficient, coherent process that achieves the development of equipment that meet user requirements. Even when there is an "integrating contractor", the government must work very hard at achieving harmonious orchestration. The engineering management process depicted in this section governs and controls product development. It addresses all key aspects of total system performance (such as security, logistics support, and configuration management), and provides a technical baseline for the Integrated Program Plan. Its primary function is to provide a management and engineering framework with which the Product Team can structure developmental activity that will result in a product that meets cost, schedule, and performance objectives over the entire product lifecycle. The following are examples of contractor activities that Product Team members will find themselves overseeing and guiding during this intricate and detailed process:

- Trade-off studies among requirements (operational, functional, performance), design alternatives (and their related manufacturing, testing, and support processes), schedule, and lifecycle cost.

- Risk management to identify, evaluate, assess, and mitigate potential sources of risk associated with the contractor’s design, manufacture, test, and support approach.

- Configuration management of system products, processes, and related documentation. This effort includes identifying, documenting, and verifying the functional and physical characteristics of an item; recording its configuration; and controlling changes to the item and its documentation.

- Integrated data management to capture and control the technical baseline (configuration documentation, technical data, and technical manuals); provide traceability among requirements, designs, decisions, rationale, and other related program planning, reporting, and support configuration procedures; and serve as a ready reference for the systems engineering effort.

- The determination of metrics for use as measures of technical progress relative to what was planned in the areas of performance, risk mitigation, cost, and schedule. Performance metrics must be traceable to performance parameters in the Requirements Document and System Specification

- The establishment of interface controls to ensure changes to all internal and external interface requirements are properly recorded and communicated to all affected configuration items.

- The development of a structured review process that demonstrates and confirms completion of required accomplishments and their exit criteria, as defined in program planning.

Assessing and Reporting Progress

Rigorous internal program control systems are essential to effective and accountable program management. They enable acquisition functions to be performed efficiently and effectively by maximizing the utilization of resources. The focus should be on results, not process. One key is to integrate cost, schedule, and technical performance is the application of Earned Value management. Another is to ensure that the individuals responsible for day-to-day management of the acquisition contract feel they have ownership of and are responsible for their elements of the Work Breakdown Structure. When this approach is taken, the Product Team is more likely to achieve full integration of cost, schedule, and technical performance within the quantifiable terms of earned-value – and not just rely on the completion of technical or schedule events or milestones.

One of the most important outputs of Earned Value Management is reliable, timely, and quantifiable data that enables the Product Team Lead to accurately determine the Estimate at Complete (EAC). Historically, a lack of understanding of information in Cost Performance Reports and Cost/Schedule Status Reports or the processes and methodology used to generate them have made it difficult for the Product Lead to make critical program decisions. Knowing how the contractor earns value for a particular element of work allows the Product Team to manage their areas of responsibility with confidence.

Providing Direction

Sound direction from the government comes only from accurate assessments of where the program is compared to where it is supposed to be. Periodic program management reviews using Earned Value techniques provide a mechanism for determining where you are. With this information, the Product Lead can provide confident direction to each contractor and team member involved in the development program.

| Activity: Approve Contractor Management Plans D-1 |
| --- |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor develops Service Team specialists review and comment | Approved contractor management plans | Service Team |  |
| Description: The quickest, cheapest way to build quality software is to avoid mistakes during development and to remove errors early in design before beginning the coding. The driving factor behind successful software-intensive systems is software quality rather than simply cost or schedule. Quality software development depends on the management processes and procedures used by the contractor. As the first crucial activity after contract award, the Service Team reviews and comments on contractor management plans, which become part of the contractor’s management baseline after approval. Changes to these documents are coordinated with the Service Team before being implemented by the contractor. Examples of contractor planning documents include: Project Management Plan, System Engineering Management Plan, Software Development Plan (including quality assurance processes), Configuration Management Plan, and Subcontractor Management Plan. Point your browser at http://sepo.nosc.mil/ and select the "SQA" menu item for some good tools on SW Quality Assurance plans, processes, and procedures. |
| Activity: Oversee System Requirements Analysis D-2 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor performs Service Team specialists oversee | Revised System Specification Preliminary System, Segment Specification Interface Control Documents (Segment to Segment) | Service Team lead engineer |  |
| Description: The Service Team oversees and generally supports contractor assessment of system specification requirements and identification of technical risks associated with satisfying those requirements. This activity determines whether user requirements can ultimately be achieved. As much as half of all software errors emanate from errors in requirements, and the main reason is lack of communication with the user. Requirements may be fleshed out in greater detail during this analysis through user interviews, simulations, prototyping, demonstrations, or any activity that gives confidence the requirements are well understood and well defined. This activity provides the basis for defining the entire system, its components, and their interrelationships, as well as for providing a foundation for measuring the extent to which program requirements, objectives, and priorities are satisfied by system design. Assessing / refining system requirements; Identifying segments and allocating requirements to segments (HWCIs, CSCIs); Defining design constraints; and Defining and supporting external interfaces. |
| Activity: Conduct System Requirements Review (SRR) D-3 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor conducts review Service Team specialists assess, evaluate, and comment | Refined System Specification System, Segment Specification Interface Control Documents | Service Team |  |
| Description: The System Requirements Review (SRR) forms the basis for determining whether (1) system requirements are consistent, achievable, and complete, and (2) the government and contractor have a clear and mutual understanding of them. While the contractor conducts this review, the government takes an active part by clearly defining expectations and standards before the review and by participating actively in the event. The review typically covers the System Specification, System / Segment Specification, and Interface Control Documents. The products of functional analysis, syntheses, and trade studies may also be reviewed. |
| Activity: Oversee Design of System Architecture D-4 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor designs Service Team specialists oversee | Revisions to System Specification Revisions to System / Segment Specification Preliminary Software Requirements Specification Preliminary Interface Requirements Specification Preliminary Systems / Segment Design Document Requirements Traceability Matrix Update to Software Development Plan | Responsible Service Team specialists |  |
| Description: The Service Team oversees and generally supports contractor activity to define, develop, and baseline the system architecture. The contractor partitions system requirements to software and hardware configuration items and evaluates alternative design approaches, leading to preliminary system / subsystem designs and the identification of system components. Each subsystem design is integrated into the total system and evaluated against program constraints of time and cost. The flow of data and the flow of control are also determined. Trade studies and system modeling may also be performed. The contractor also develops a Requirements Traceability Matrix that identifies which configuration item will achieve each requirement in the System Specification. Requirements are allocated in the System Architecture Baseline and Allocated Baseline. If an open architecture has been chosen, point your browser to http://www.itl.nist.gov/div897/pubs/index.htm and see Special Publication 500-187, Application Portability Profile (APP). The U.S. Government's Open System Environment Profile, OSE/1, Version 1.0. is based on an open system environment defined by non-proprietary specifications. Components may be added or deleted as technology changes and as Federal requirements change. |
| Activity: Conduct System Design Review D-5 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor conducts SDR Service Team specialists review contractor design documents | Comments on documents | Appropriate Service Team specialist |  |
| Description: The contractor conducts the System Design Review (SDR) with the Service Team reviewing and evaluating the status and maturity of system design. This activity is intended to confirm that (1) system requirements can be met, and (2) the contractor has a sound top-level design with system requirements segmented to appropriate configuration items. The following should be complete prior to the System Design Review: All subsystem, functional, and interim system reviews with unresolved issues documented; Definitions of functional and performance requirements for system development, manufacturing, verification, deployment, operations, support, training, and disposal; System trade studies, as well as trade studies supporting the preparation of draft Configuration Item development specifications; System architecture to the specified level; Draft Configuration Item architecture to specified level; Draft Configuration Item (including CSCI) development specifications to the desired level below the system specification. The following design documents are typically reviewed during the SDR: System / Segment Specification; Preliminary Software Requirements Specification; Preliminary Interface Requirement Specification; System / Segment Design Document; and Requirements Traceability Matrix. |
| Activity: Oversee Software Requirements Analysis D-6 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor develops Service Team specialists and users evaluate | Final System / Segment Specification Final Software Requirements Specification Initial CSCI Preliminary Design Final Interface Requirements Specification Updated System / Segment Design Document Updated Requirements Traceability Matrix Data from Feasibility Prototyping (if used) Data from Modeling and Simulation (if used) | Responsible Service Team specialist |  |
| Description: The Service Team oversees, tracks, and generally supports the contractor’s analysis of software requirements. This phase of software development converts system-level requirements allocated to software in the System / Segment Specification to statements of requirements that are complete, consistent, testable, and feasible for software implementation. As part of this process, the contractor develops the overall software architecture, identifies principal CSCIs and CSCs, and allocates resources to them using the Requirements Traceability Matrix database. Results are documented in the Software Requirements Specification. This process also updates interface requirements and performance information. Risk management and fault prevention are extremely important at this point in the software development process. Errors discovered and corrected here are much less costly to correct than errors discovered during implementation or maintenance. Feasibility prototyping and modeling / simulation are the most common methods of risk mitigation. Feasibility prototyping may consist of conceptual prototyping or demonstration prototyping. Conceptual prototyping provides a tangible representation of the concept of operation and human / machine interface that can be critically reviewed by the customer or user. This class of prototyping often uses rapid prototyping techniques requiring the use of non-target hardware, constraining the display and menu formats and medium (i.e., graphics, color, fonts, etc.) to those supported on the target machines. Demonstration prototyping seeks to ensure that at least one solution exists for a stated requirement. Demonstration prototyping is accomplished on the target equipment, and often demonstrates only those parts of the target environment that are impacted by the specific requirement being demonstrated. For instance, a demonstration prototype may show a solution on a computational server without simulating the entire network. Simulation and requirements modeling are used to demonstrate feasibility in those cases where mathematical or other techniques exist that provide insight into the question at hand, or for those questions where prototyping of a solution may be too expensive or time-consuming. Modeling of requirements requires an evaluation plan that documents the proposed techniques to be used, the type and amount of data to be collected, the algorithms to be used, the characteristics of the system to be included, and the schedule to be followed. |
| Activity: Conduct Software Specification Review D-7 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor hosts the review Service Team specialists review and comment | Baseline Software Requirements Specification | Service Team software engineer |  |
| Description: The contractor conducts a formal review of the Software Requirements Specification (SRS) in accordance with MIL-STD-1521B. The intent is to demonstrate that all segment and Interface Control Document requirements are allocated and traced to Computer Software Configuration Items, and that the methods of verifying and validating requirements are reflected in the SRS. The Service Team reviews the allocation of performance requirements to major architectural components, as well as external and internal interface requirements. Additionally, the Service Team evaluates the impact of any proposed changes to the System Requirements Specification. The Air Force Acquisition Model (AFAM) is a good tool to use when determining the requirements for all Systems Engineering Reviews, particularly for software. It is available on CD ROM and includes Best Practices and Lessons Learned. |
| Activity: Conduct Hardware Specification Review D-8 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor conducts review Service Team specialists participate and resolve problems |  |  |  |
| Description: The contractor and Service Team jointly review hardware specifications in the System Specification to ensure all requirements can be satisfied by the vendor’s COTS / NDI hardware. Any discrepancies or conflicts must be corrected now before proceeding further in development. When problems emerge, it may be possible to implement functionality in software rather than hardware or it may require a change to the System Specification or program. |
| Activity: Oversee Software Preliminary Design D-9 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Service Team software engineer | Software Design Document Interface Design Document Preliminary Software Test Plan Updated RTM Design prototyping data Operational prototyping data Software Development Folder(s) |  |  |
| Description: The Service Team oversees, tracks, and generally supports the preliminary design effort during which the contractor partitions Computer Software Configuration Items (CSCIs) into Computer Software Components (CSCs) and Computer Software Units (CSUs), and allocates requirements to them. The contractor also: Updates the Requirements Traceability Matrix to reflect the allocation of software requirements to each CSC or CSU; Generates preliminary software acceptance test descriptions and procedures; and Develops a preliminary Software Test Plan. As development progresses, the contractor finalizes the top-level software architecture and places products under software configuration management. The contractor may perform some design prototyping to assess all or parts of the CSCI design (e.g., interfaces with new hardware or new operating services). Because these prototypes demonstrate a solution, they often provide the bulk (if not all) of code delivered with the product. As such, prototyping can complete the design and accomplish some developmental testing while still formally being part of the design effort. The contractor assumes the risk of non-acceptance of code by the customer, and mitigates that risk by conducting reviews that match the reviews conducted on more classically developed software. The contractor may perform some operational prototyping during the design phase to meet high-priority user requirements or to demonstrate project-wide capabilities. Selecting a component for operational prototyping depends on the risk associated with the remaining system design. Operational prototyping is recommended for: Critical operational considerations that support specific, narrowly defined user needs; Software augmentations to operating system services, data management, or network functions; Software back planes required to support multiple builds/releases; Libraries needed early in the development cycle; and Interfacing code to existing external systems to allow continued operation during switch over. Operational prototypes are expected to provide fully operational code. They are totally designed, implemented, and tested while the actual design of the overall product is underway. As with design assessment prototyping, the contractor mitigates risk by conducting reviews at points within the prototype development that match more classically developed software. |
| Activity: Conduct Preliminary Design Review D-10 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor conducts Service Team specialists review and comment | Formal review of contractor design approach Formal comment on all design documents | Service Team software engineer or appropriate specialist |  |
| Description: The contractor presents the preliminary system architecture, overall design approach, and Configuration Item (CI) structure to the Service Team at the Preliminary Design Review (PDR) in accordance with MIL-STD-1521B. The objective is to demonstrate formally that they are sufficiently mature to begin detailed design. Sometimes the contractor conducts a series of PDRs, one for each Configuration Item or aggregate of CIs leading to a system PDR at completion. Each PDR must (1) ensure the process used to arrive at functional and performance requirements for each Configuration Item is rigorous and complete, including trades and allocations; and (2) establish an audit trail from user requirements to the functional baseline, substantiating changes as necessary. The PDR is intended to demonstrate the contractor has: Developed a satisfactory preliminary design for implementing segment requirements; Allocated and traced all requirements to the CSC level; Identified all open issues and identified a plan for closing them; Identified all technical and programmatic high-risk areas; Developed a viable database design; and Developed a complete and adequate plan for software and operations testing. |
| Activity: Oversee Software Detailed Design D-11 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor designs Service Team oversees and supports | Preliminary Software Design Document Preliminary Interface Design Document Updated Software Test Plan Preliminary Software Test Description Updated Requirements Traceability Matrix Test Requirements Matrix Updated Software Development Folder(s) | Service Team software specialist |  |
| Description: The Service Team oversees, tracks, and generally supports the contractor’s detailed software design effort during which each Computer Software Component (CSC) is decomposed into a complete structure of lower-level CSCs and Computer Software Units (CSUs). Interfaces are described to the lowest component level; data structures and contents are defined; input and output details are designed; and decisions are made on handling errors. As design activities proceed, the contractor finalizes the Software Design Document and Interface Design Document, begins development on the Software Test Description, and updates the Requirements Traceability Matrix. |
| Activity: Conduct Critical Design Review D-12 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor conducts Service Team specialists review and comment | Detailed CSCI Design Documents Detailed CSCI Interface Design Documents Preliminary Software Test Descriptions Draft CSCI test procedures Updated Requirements Traceability Matrix Undated CSCI development metrics Undated cost and schedule estimates | Appropriate Service Team specialist |  |
| Description: Critical Design Review determines (1) whether the detailed design meets the specified requirements in the appropriate developmental baseline, and (2) whether the design is complete and ready to be implemented via detailed software code and test. The contractor conducts the Critical Design Review in accordance with MIL-STD-1521B, with the Service Team reviewing and evaluating contractor activity and progress. Often, a series of Critical Design Reviews are conducted, one for each Configuration Item in the configuration tree, rather than a single "system" CDR. Specifically, the CDR reviews formally the design of each hardware and software configuration item and determines whether: All software requirements are allocated and traced to the CSU level; Detailed designs reflect an architecture that satisfactorily minimizes risk; Database design is complete and meets all requirements; A complete and adequate plan is in place for software and operations testing; and Changes to requirements have been analyzed for impact on detailed software design, including internal and external interfaces (particularly associated COTS / NDI hardware). As part of this activity, the contractor should prototype both CSCI external interfaces to other NAS systems and internal interfaces to COTS / NDI hardware. The contractor should also identify those requirements that have already been tested and for which test data is available (typically NDI / COTS components). Activity: Make Product Demonstration Decision D-13 Responsible Agent Product Approval Authority Tools and Aids Service team leader provides information that demonstrates achievement of product integration decision criteria Product Demonstration Decision Memorandum Vice President (ATO) or Director (non-ATO) of the implementing service organization Discussion: The service team leader presents the results of product integration to the Vice President (ATO) or Director (non-ATO) of the implementing service organization. The Vice President or Director, as appropriate, reviews product knowledge to determine if the following decision criteria have been satisfied: Key product characteristics are defined; Stakeholders agree that product design and functionality satisfy customer requirements; System design reviews are complete; Engineering drawings are complete; Detailed software/firmware design is complete, including critical software processes and threads; RMA goals are defined and planning is complete; Failure modes and effects analysis is complete; and Critical manufacturing processes are identified If so, the decision authority issues a decision memorandum authorizing the investment program to proceed to initial manufacturing of first-article units for use in product demonstration. Findings are recorded in the decision memorandum along with any required actions. |
| Activity: Oversee Software Coding and CSU Testing D-14 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor develops Service Team oversees, tracks, supports | CSU code Updated Software Development Folder(s), including CSU Test Procedures Updated RTM Test Requirements Matrix Test Development Folder(s), including Software Turnover Plan | Service Team software specialist |  |
| Description: The Service Team oversees, tracks, and generally supports contractor software CSU coding and testing. Coding and testing generally begins after completion of detailed design and a successful CDR, although some prototype code may have been produced during requirements analysis or preliminary design. Coding and CSU testing implements the design validated by the CDR. This activity produces a set of program units that completely implement the functional requirements specified in the Software Requirements Specification. Go to http://www.stsc.hill.af.mil and click on the subject "SW Testing" in "Technology Areas" for information on ATPS, a set of expert system-based tools designed to aid acquisition staffs in the oversight of test and evaluation. |
| Activity: Oversee Hardware Acquisition D-15 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor obtains hardware Service Team Quality Reliability Officer enforces contract provisions and accepts qualified units | Fabricated hardware components | Quality Reliability Officer or designated official |  |
| Description: The contractor fabricates or procures the COTS / NDI hardware components of the system. The Service Team ensures hardware components are fabricated in accordance with provisions of the contract and accepts delivery of hardware units upon completion of all required testing and quality assurance checks. |
| Activity: Conduct Integration Test Review D-16 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor conducts review Service Team reviews and evaluates contractor readiness to integrate and test | Comments on code quality Permission to proceed to integration testing | Service Team software specialist |  |
| Description: The contractor conducts the CSC / CSCI Integration Test Review (ITR) at the completion of CSC testing and before release of code for integration. The Service Team evaluates the quality of CSC code and reviews contractor readiness to enter integration testing. This review examines: Correctness of code interactions as specified in ICDs and design Interface Agreements; Completeness and consistency of CSC test results with the predicted output; Correctness of data transformation within the code; Ability of code to meet timing, resource, or performance restrictions; and Ability of code to deal with error conditions, out-of-tolerance processing conditions, and out-of-limit data values. Following the Integration Test Review, software is presented to the integration test organization for review, evaluation, and eventual turnover. Upon acceptance, CSCI code and supporting test data are placed under formal configuration control and the change authority is transferred from the developing organization to the project change control board. |
| Activity: Oversee CSC / CSCI Integration and Testing D-17 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor performs Service Team oversees, tracks, and supports | Integrated software baseline Updated Test Development Folder(s), including integration test results Updated Software Development Folder(s) | Service Team software specialist |  |
| Description: The Service Team oversees, tracks, and generally supports contractor CSC / CSCI integration and testing. CSC / CSCI integration testing assembles partitioned CSU components into the respective CSC, and those CSCs into the whole CSCI that represents part or all of the product under development. The integration of multiple CSUs into the parent CSC is an iterative process of accepting CSUs from unit test, testing them together, correcting any deficiencies, and repeating the process with the next CSU. This continues until all CSUs have been integrated into the parent CSC. Likewise, CSCs are then integrated and tested sequentially to form the CSCI. After completion of CSC / CSCI integration testing, software is turned over for CSCI integration and testing. |
| Activity: Oversee CSCI Integration & Testing D-18 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor performs integration and testing Service Team oversees, tracks, and supports | Final Software Design Document Final System Test Procedures Integrated software baseline (tested) | Service Team software specialist |  |
| Description: The Service Team oversees, tracks, and generally supports CSCI integration and testing by the contractor. Also known as software build / release testing, CSCI integration and testing identifies and corrects software problems through the execution of system test procedures before the start of Formal Qualification Testing. During this activity, the contractor: Executes system test procedures to verify that baselined software meets system requirements; Executes an endurance test to monitor system performance under sustained loading; Resolves any problems encountered during testing; Freezes the software; and Conducts a dry run of all system test procedures prior to the Test Readiness Review. |
| Activity: Oversee Hardware Configuration Item Integration and Testing D-19 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor integrates and tests Service Team oversees | Integrated and tested hardware units | Quality Reliability Officer or designated official |  |
| Description: The contractor tests each Hardware Configuration Item (HWCI) to confirm each satisfies System Specification requirements allocated by the Requirements Traceability Matrix. In a similar manner as with CSCI integration and testing, the contractor sequentially links and tests HWCIs to the degree practical. When HWCI interfaces are provided by software, the integration and testing of HWCIs occurs during System Integration and Testing. |
| Activity: Oversee System Integration & Testing D-20 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor performs integration and testing Service Team oversees, tracks, and supports | Updated Software Development Folders | Service Team software specialist |  |
| Description: The Service Team oversees, tracks, and generally supports system integration and testing by the contractor. This activity integrates CSCIs with interfacing HWCIs and CSCIs (including COTS / NDI), tests the groupings to determine whether they work together as intended, and continues the process until all CSCIs and HWCIs are integrated and tested. Software-related information such as analysis and test results is recorded in appropriate Software Development Folders. |
| Activity: Conduct Test Readiness Review D-21 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor conducts review Service Team evaluates results and determines system readiness for FQT | Final System Test Procedures Agreement to proceed with Formal Qualification Testing | Service Team test specialist |  |
| Description: The contractor conducts a System Test Readiness Review (TRR) in accordance with MIL-STD-1521B to provide the Service Team with documented proof that all requirements necessary to start Formal Qualification Testing (FQT) have been met. The review is conducted at the software unit and component level to evaluate the completeness of test procedures, and to ensure the contractor is ready for formal testing. Test procedures are evaluated for compliance with the Master Test Plan. Test plan descriptions are evaluated for adequacy in accomplishing test requirements. Preliminary testing is reviewed to compare results against baseline, and to ensure necessary coding changes have been accomplished. Informal testing and any updates to operational and support documents are also reviewed. At a minimum, the Service Team evaluates the following types of data and information to assess the readiness of the developed system for FQT: Results obtained from the dry-run of system test procedures; Results of lower-level hardware and software tests; Outstanding Program Trouble Reports and waivers, along with assessment of impact upon test readiness; and Formal recommendations by the software quality assurance organization. |
| Activity: Witness Design Qualification Test D-22 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor conducts DQT Service Team witnesses DQT and accepts system on completion | Program Trouble Reports (Resolved) Software Test Report Updated Software Development Folder(s) Fully qualified system | Service Team Quality Reliability Officer or designated official |  |
| Description: The Service Team and quality assurance representatives witness the Design Qualification Test (DQT) conducted by the contractor. The DQT demonstrates the system’s ability to satisfy all requirements of the System / Segment Specification and Interface Requirements Specification. This testing involves fully integrated CSCIs and HWCIs, with the CSCIs installed on the approved hardware configuration. The contractor executes all test scripts from approved System Test Procedures, and evaluates results against the acceptance criteria included in test documentation. All Program Trouble Reports opened during DQT must be resolved before the conclusion of testing. Successful completion of the DQT marks the end of developmental testing and transfer of ownership of the system to the FAA. |
| Activity: Conduct Production Acceptance Test Each Unit D-23 |
| Responsible Agent | Product | Approval Authority | Tools and Aids |
| Contractor conducts testing Service Team monitors | Accepted production units | Quality Reliability Officer or designated official |  |
| Description: The contractor tests each production unit using test procedures approved by the FAA to verify the assembly line is producing units with the same quality and performance as the first article. The Quality Reliability Officer (QRO) monitors production acceptance testing, and is the approving official for successful compliance with test procedures and test criteria. |