## VLHC Cryo Cost Estimate - Total
VLHC Phase I Cost Estimating Spreadsheet
Description |  | Cryogenic System |  |  | Tunnel Cryogenics |  |  |  | Name |  | Norris/Klebaner
[5 empty] | Refrigerator Plants |  |  |  | Estimate date |  | 2001-04-24
|  |  |  | MATERIAL |  |  |  | LABOR
| Identifier | Item description |  |  | No. of | FY01 $ | Total | Labor | FTE | $ per | Total | Total
|  |  | basis | Unit | units | per unit | M&S $ | type | (m-year) | FTE | labor $
|  | Sum for this sheet |  |  |  |  | 105175273.58 |  |  |  | 11953600 | 117128873.58
| 1 | Compressor System | 1,2 |  | 7 | 2630375.16 | 18412626.12 | Engineer | 3.9 | 96000 | 374400 | 18787026.12
[8 empty] | Tech | 15 | 76000 | 1140000 | 1140000
| 2 | Cold Box, 4.5 K(Upper and Lower) | 1,2,3 |  | 8 | 4003896 | 32031168 | Engineer | 4.5 | 96000 | 432000 | 32463168
[8 empty] | Tech | 18 | 76000 | 1368000 | 1368000
| 3 | Oil Removal System | 1,2 |  | 8 | 237787.68 | 1902301.44 | Engineer | 0.8 | 96000 | 76800 | 1979101.44
[8 empty] | Tech | 2.8 | 76000 | 212800 | 212800
[8 empty] | Designer | 0.8 | 76000 | 60800 | 60800
| 4 | Ancillary Equipment | 1,2 |  | 8 | 2682330 | 21458640 | Engineer | 2.1 | 96000 | 201600 | 21660240
[8 empty] | Tech | 7.8 | 76000 | 592800 | 592800
[8 empty] | Designer | 3 | 76000 | 228000 | 228000
| 5 | Refrigerator Controls | 1,2,8 |  | 8 | 1262720 | 10101760 | Engineer | 21 | 96000 | 2016000 | 12117760
[8 empty] | Tech | 24 | 76000 | 1824000 | 1824000
| 6 | Warm Header | 1,2 |  | 1 | 12979824.02 | 12979824.02 | Engineer | 2 | 96000 | 192000 | 13171824.02
[8 empty] | Tech | 25 | 76000 | 1900000 | 1900000
[8 empty] | Designer | 1.5 | 76000 | 114000 | 114000
| 7 | Connecting Boxes | 4 |  | 6 | 295634 | 1773804 | Engineer | 0.5 | 96000 | 48000 | 1821804
[8 empty] | Tech | 7.5 | 76000 | 570000 | 570000
[8 empty] | Designer | 1 | 76000 | 76000 | 76000
| 8 | Shield's Cryo Valve | 5 |  | 870 | 2500 | 2175000 | - | - |  |  | 2175000
[8 empty] | - | - |  |  | 0
| 9 | Shield's Thermometer | 6 |  | 870 | 65 | 56550 | - | - |  |  | 56550
[8 empty] | - | - |  |  | 0
| 10 | Valve/Thermometer Interface Board | 7 |  | 1038 | 200 | 207600 | Engineer | 0.25 | 96000 | 24000 | 231600
[8 empty] | Tech | 1 | 76000 | 76000 | 76000
[8 empty] | Designer | 0.3 | 76000 | 22800 | 22800
| 11 | Valve Actuator Board & Actuators | 7 |  | 1038 | 2000 | 2076000 | Engineer | 0.3 | 96000 | 28800 | 2104800
[8 empty] | Tech | 0.1 | 76000 | 7600 | 7600
[8 empty] | Designer | 0.2 | 76000 | 15200 | 15200
| 12 | Distribution Box | 4 |  | 8 | 250000 | 2000000 | Engineer | 0.5 | 96000 | 48000 | 2048000
[8 empty] | Tech | 3 | 76000 | 228000 | 228000
[8 empty] | Designer | 1 | 76000 | 76000 | 76000
Technical description/ basis notes
| 1 | SNS (actual installation cost) | 8 | CERN Cryogenic Controls( IAS)
| 2 | Jefferson Laboratory(actual installation cost)
| 3 | Linde KryotechnikAG(quote)
| 4 | Fermilab Cryogenic Department( actual req's)
| 5 | Fluid Process Control Corp/Cryolab
| 6 | Lake Shore Cryogenics
| 7 | Fermilab Controls Department(guess)

## VLHC Cryo Costs - Break Down
VLHC 4.5kW
COMPRESSOR SYSTEM
QUANITY
DESCRIPTION |  |  | COST PER | TOTAL COST
1st stage compressor |  | 5 | 45000 | 225000
Helium/oil HX's |  | 5 | 33240 | 166200
Oil Pumps |  | 5 | 16000 | 80000
Oil injection Valve |  | 5 | 8000 | 40000
Micromenter Valves |  | 10 | 1500 | 15000
Flex hoses |  | 20 | 600 | 12000
Motors, Low stage |  | 5 | 40000 | 200000
Motor Control Center, LS |  | 5 | 20000 | 100000
Couplings |  | 5 | 1300 | 6500
Spool valves |  | 5 | 700 | 3500
2nd Stage Compressor |  | 5 | 40000 | 200000
He/Oil HX's |  | 5 | 50641 | 253205
Oil Pumps |  | 5 | 16000 | 80000
Oil injection Valve |  | 5 | 6000 | 30000
Micromenter Valves |  | 10 | 850 | 8500
Flex hoses |  | 20 | 600 | 12000
Motors, High Stage |  | 5 | 55000 | 275000
Motor Control Center, HS |  | 5 | 40000 | 200000
Couplings |  | 5 | 1500 | 7500
Spool valves |  | 5 | 700 | 3500
Skid Design |  |  | 0 | 0
Skid Fabrication |  | 10 | 15000 | 150000
|  | Total Cost Mat'l/6 Skids |  | 2191979.3 | 6% Shipping Included
|  | Total/ skid, Labor |  | 0
|  | Increased Shield Flow |  | 2630375.16
|  |  | Total Cost= | 2630375.16
OIL REMOVAL SYSTEM
MATERIAL
QUANITY
DESCRIPTION |  |  | COST PER | TOTAL COST
Pressure Vessels Set |  | 1 | 130000 | 130000
Coalescers Elements |  | 5 | 10000 | 50000
Valves/steel/RV's/Misc |  | 1 | 24888 | 24888
Flow meters |  | 4 | 2860 | 11440
Pipe/Flanges etc E |  | 1 | 8000 | 8000
|  |  | Total Material | 224328
|  | Shipping all Material= |  | 13459.68
|  |  | Total material | 237787.68
|  |  | Total Labor | 0
|  |  | Total Cost= | 237787.68
FRIG SYSTEM CONTROLS
MATERIAL
QUANITY
DESCRIPTION |  |  | COST PER | TOTAL COST
Pressure instruments |  | 1 | 37000 | 37000
TD's |  | 40 | 400 | 16000
TP's |  | 20 | 250 | 5000
Flowmeters |  | 1 | 2000 | 2000
Unix Workststion,HPb180L |  | 1 | 7460 | 7460
C pkg |  | 1 | 700 | 700
C++ pkg |  | 1 | 750 | 750
VxWorks Development License |  | 1 | 5000 | 5000
Color Printer (HP 1600CM) |  | 1 | 2000 | 2000
VME crate |  | 1 | 3000 | 3000
ioc (mv167/32MB) |  | 1 | 6900 | 6900
VxWorks Target License |  | 1 | 150 | 150
VME ADC (32ch, 12bit) |  | 4 | 1500 | 6000
VME DAC (16ch, 12bit) |  | 2 | 1400 | 2800
VME Digital Input (64ch) |  | 1 | 1700 | 1700
VME Digital Output (32ch) |  | 1 | 1200 | 1200
VME Diode Scanner (16ch) |  | 2 | 2600 | 5200
VME crate |  | 10 | 3000 | 30000
ioc (mv167/32MB) |  | 10 | 6900 | 69000
VxWorks Target License |  | 10 | 150 | 1500
VME ADC (32ch, 12bit) |  | 10 | 1500 | 15000
VME Diode Scanner (16ch) |  | 20 | 2600 | 52000
VME LVDT Scanner (8ch) |  | 20 | 2800 | 56000
VME Pulse Generator (8ch) |  | 20 | 2000 | 40000
VME LL Scanner |  | 10 | 2000 | 20000
EV Actuator |  | 74 | 2500 | 185000
Cables, connectors, etc. |  | 1 | 60000 | 60000
|  |  | Total material | 631360 | CEBAF's cost for SNS type frig.
|  |  | Total Labor | 0
|  |  | Total Cost= | 1262720 | The total cost of VLHC controls is 10% of frig cost based on LEP/LHC experience
4.5 K COLD BOX
MATERIAL
DESCRIPTION |  | QUANITY | COST PER | TOTAL COST
Turbines ## Q |  | 6 | 250000 | 1500000
Turbine Duty, 4.5 % |  |  |  | 67500
Heat Exchangers, |  | 10 | 80000 | 800000
Piping, Internal |  | 2 | 60000 | 120000
Shipping Pipe, 6 % |  |  |  | 7200
Vessel # |  | 2 | 150000 | 300000
Shipping costs, 6 % |  |  |  | 18000
Warm valves |  | 20 | 5000 | 100000
Diffusion Pump |  | 1 | 8000 | 8000
Mech Pump |  | 1 | 6428 | 6428
Vac Instruments |  | 1 | 1500 | 1500
Adsorber Vessels, 80K |  | 3 | 6000 | 18000
Cryo-valves |  | 20 | 11000 | 220000
Piping, External |  | 2 | 25000 | 50000
Shipping 6 % |  |  |  | 3000
Load Heater |  | 1 | 10000 | 10000
Super Insulation |  | 1 | 8000 | 8000
8" Q |  | 32 | 1488 | 47616
6 " Q |  | 16 | 852 | 13632
4" Q |  | 12 | 462 | 5544
2" Q |  | 8 | 270 | 2160
|  |  | Total material | 3306580
|  | Structual material= |  | 30000
|  |  | Total material | 3336580
|  |  | Multiply by 20% for split cold boxes | 4003896
|  |  | Toatal Labor | -
|  |  | Total Cost= | 4003896
ANCILLLARY EQUIPMENT
MATERIAL
DESCRIPTION |  | QUANITY | COST PER | TOTAL COST
Piping/Installation |  | 1 | 50000 | 50000
LHe Dewar, 10000 Gallons # |  | 3 | 500000 | 1500000
80K Purifiers, External |  | 2 | 60000 | 120000
Purifier Compressors |  | 2 | 18000 | 36000
Skid Fabrication |  | 2 | 15000 | 30000
Controls E |  | 1 | 2500 | 2500
Storage Tanks, 30kgal |  | 15 | 40000 | 600000
External Piping E |  | 1 | 15000 | 15000
Towers |  | 2 | 50000 | 100000
Motors |  | 1 | 8000 | 8000
Pipe |  | 1 | 10000 | 10000
Pumps |  | 2 | 12000 | 24000
Instrument Air Compressor |  | 2 | 5000 | 10000
Arc Cell |  | 1 | 15000 | 15000
Hydrometer |  | 1 | 10000 | 10000
|  |  | Total material | 2530500
|  |  | Shipping 6% | 151830
|  |  | Total Material | 2682330
|  |  | Total Labor | 0
|  |  | Total Cost= | 2682330
WARM HEADER PIPE
MATERIAL
QUANITY
DESCRIPTION |  | Ft(1) | $$ per ft | TOTAL COST
Transfer Line, 200m |  | 600 | 5000 | 3000000
Return Header,200m |  | 600 | 300 | 180000
Cooldown Line, 6" |  | 766447 | 11 | 8430917
Jigs/ Fixtures, one lot |  | 1 | 75000 | 75000
Expansion joint |  | 466 | 1200 | 559200
(1) ROUNDED LENGTHS |  |  | Total Material | 12245117
Assume 40 ' sections |  |  | 6% Shipping | 734707.02
|  |  | Total Material | 12979824.02
|  |  | Total Labor | 0
|  |  | Total Cost= | 12979824.02
CONNECTING BOXES
QUANITY
DESCRIPTION |  |  | COST PER | TOTAL COST
Vacuum Vessel |  | 5 | 1000 | 5000
Copper Shield |  | 5 | 100 | 500
Flex Hoses |  | 30 | 100 | 3000
Cryo-Valves |  | 20 | 11000 | 220000
Instrumentation |  | 50 | 700 | 35000
Piping, Internal |  | 20 | 5 | 100
Fittings |  | 40 | 20 | 800
Relief Valves |  | 20 | 1000 | 20000
|  |  | Total Material | 278900
|  |  | 6% Shipping | 16734
|  |  | Total Material | 295634
|  |  | Total Labor | 0
|  |  | Total Cost= | 295634