DOE FEMP

DRAFT

Agency Project Management Plan for Super

Energy Savings Performance Contracts

(Super ESPCs)

February 21, 2003

TABLE OF CONTENTS

Summary	3

1.0 PROJECT DESCRIPTION	3

2.0 PROJECT MANAGEMENT	4

2.1 KEY PERSONNEL	4

2.2 ESPC PROJECT DEVELOPMENT PROCESS OVERVIEW	5

3.0 SCHEDULES	10

4.0 LEGAL AND CONTRACTUAL	11

5.0 SAFETY	11

6.0 COMMISSIONING	12

APPENDIX A - ACRONYMS AND ABBREVIATIONS	17

APPENDIX B –KICK-OFF/DES MEETING AGENDA	18

APPENDIX C – POST AWARD CONFERENCE	20

APPENDIX D – APPROVAL/REVIEW/AUTHORITY ITEMS	22

APPENDIX E – WEEKLY MEETING AGENDA	24

APPENDIX F – MONTHLY REVIEW AGENDA	25

APPENDIX G – MATERIAL/DESIGN REVIEW FORM (Sample)	26

APPENDIX H – M&V FOR ESCO FINAL PROPOSAL	27

APPENDIX I – PRE-CONSTRUCTION CHECKLIST	28

APPENDIX J– PROJECT/ECM ACCEPTANCE CHECKLIST	29

APPENDIX K – CONSTRUCTION COMPLETION DOCUMENT	30

DRAFT

###### AGENCY PROJECT MANAGEMENT PLAN FOR SUPER

###### ENERGY SAVINGS PERFORMANCE (SUPER ESPC)

###### CONTRACTS

# Summary

This draft project management plan is created to allow for consistent development of project planning for energy savings projects and to create a series of master checklists and guides for activities that must be considered in any project.  The purpose is to put forth the basic items for project management that need to be covered, and then suggest methods of implementing a “graded approach” for the refinement of the planing activities to coincide with the size and complexity of the project.  Depending upon the specifics of any given project, other requirements may be necessary and can not be anticipated by this draft plan.  This draft plan is therefore, indicative of the functions that normally would be accomplished in the management of any project, and is intended to assist Agency Project Managers in the implementation of the ESPC Delivery Order project.

The main thrust for the development of a project management plan is to insure proactive consideration of the activities necessary for a successful and timely ESPC project completion.

A list of Acronyms is included in Appendix A.

# 1.0 PROJECT DESCRIPTION

The project description is the responsibility of the Energy Service Contractor (ESCO), and should be written after determination of the final project Delivery Order (DO), and included in the final proposal from the ESCO.  The project description defines the project including a list of Energy Conservation Measures (ECMs) to be incorporated, where they are to be incorporated, and gives an overall view of the project.  It should address items such as specific approaches to energy and related O&M savings, Measurement and Verification (M&V), etc.  Responsibility for the operation and maintenance of the installed equipment should be defined, as well as the overall time for contracting period.  Equipment commissioning requirements and responsibilities shall be defined and a commissioning plan submitted prior to the start of the commissioning process, allowing adequate review time.  The applicable requirements in all checklists contained herein shall be addressed for the project duration.  ESCO and Agency services and requirements should be defined in the final proposal.

# 2.0 PROJECT MANAGEMENT

Project Management defines the roles, authority, and responsibilities of the key members of the project team.  This section outlines the management approach to maintaining cost, technical, and schedule knowledge for all parties, as well as defines the decision making process for management of the project day-to-day activities.  Lines of communication and chains of command should be described for all key personnel.  All personnel holding permit and/or work authorization authority should be identified.  For this report we give the below-suggested list of potential personnel to be considered for the project team as well as a checklist of actions normally (Appendix D) requiring submittal and approval by the Agency.

Super ESPC contracts are contracted for by the Agency(s) with an Energy Services Company (ESCO). A list of ESCOs in any region can be obtained from the DOE Regional Office (RO).  DOE Project Facilitators can be obtained for assistance by the Agency if they want to contract for this service from DOE.

Partnering is an excellent methodology for the smooth introduction of a contractor onto a work site and should be considered for larger and more complex projects.  It consists of one or more facilitated sessions during which the principle people involved in the project, including those responsible for the day-to-day work and work permits, are brought together for the purpose of establishing good working relationships and team building.  The benefits are that each party becomes familiar with the requirements of the other parties they must work with, and the requirements of both sides are disclosed up-front rather that waiting for the natural sequence of events to reveal them.  Partnering can be as simple as a meeting at startup to facilitate communications, and as complex for larger projects, as including quarterly, bi-annual, or annual refresher meetings.  The meetings should be held as often as necessary to maintain focus, account for personnel turnover, shifting priorities, and other problems that effect progress.

# 2.1 KEY PERSONNEL

Identification of the key personnel for each major phase is critical to the project.  It should include the principle points of contact, the approval authorities, the reviewers, and the permitting authorities, as examples.   Not all personnel are required for every phase.

Agency/Facility

Energy Manager

Facility Manager

Budget Manager

Project Manager

Contracting Officer (CO)

Contracts Specialists.

Contracting Officers Representative (COR)

Building Managers

Facility Engineers

Environmental Compliance Officer

Safety Manager

Security

Historical Protection Manager

Personnel authorizing electrical, steam, water, excavation, etc., work permits for the facility.

ESCO

Project Manager

Financial Manager

Construction Manager

Site “Point of Contact”

Measurement & Verification Expert

Energy Engineer

Quality Control/Quality Assurance Manager

Safety Manager

Environmental Specialist

Key Subcontractor’s Point of Contact

Commissioning Engineer

Contracting Agency (If separate Agency is used for contracting)

Contracting Officer  (CO)

Contracting Specialist

Contracting Officers Representative (COR)

Commissioning Agent

GSA Property Managers (if agency is in GSA owned buildings)

DOE/FEMP (If Agency contracts for DOE services)

Contracting Officer (CO)

Regional Support Officer (RSO)

Project Facilitator (PF)

Measurement and Verification Expert

Engineering/Project Management Support

Commissioning Consultant

# 2.2 ESPC PROJECT DEVELOPMENT PROCESS OVERVIEW

The process for the development of an ESPC project is broken up into 5 phases, depicting the areas of major focus and decision making.  This draft plan will focus on Phases 4 and 5 of the ESPC project management process, assuming that phases 1 through 3 have already been accomplished.

Phase 1: Assemble Acquisition Team, Develop Project Plan, and Partner with an ESCO.

Phase 1 consists of the high-level assessment of a facility to determine if sufficient energy and related O&M cost savings opportunities exist to warrant pursuing an energy savings contract.  If it is determined that the potential is present, the Agency acquisition team is identified and assembled, the support of site management is sought and if obtained, the selection of an ESCO partner is accomplished.

Phase 2: Project Development

Phase 2 is the process of obtaining a preliminary survey and initial proposal from the selected ESCO(s) to allow assessment of energy waste and corrective actions and identification of energy-related O&M cost savings opportunities.  M&V (see Appendix H) approach should be broadly defined.  The completion of this phase results in either no action, or the decision to proceed with an ESPC.

It is highly recommended that the designated Agency Project Manager be a part of the agency acquisition team from day one, and participate in the kickoff meeting. This ensures a smooth transition into later stages of the delivery order process, such as Phase 4, when strong PM leadership through the design submittal and construction phase is critical to a timely and successful project acceptance. See Appendix B for suggested details of the kickoff meeting.

Phase 3: Negotiate and Award Final Delivery Order.

During Phase 3 the ESCO performs a Detailed Energy Survey, works with the agency to develop the definition of an acceptable project, and submits a revised proposal after receiving an “Intent to Award” and DO RFP from the Agency.  The Agency evaluates the revised proposal and proceeds with negotiations and establishment of the final Delivery Order.  The Notice of Award, etc. is issued.  M&V definition should be upgraded to Appendix I requirements.

It is highly recommended that the designated Agency Project Manager be a part of the agency acquisition team from day one, and full-fledged participant in the final proposal discussions in this phase.

Phase 4: Implementing the Delivery Order.

  - Conduct post-award conference.  All Agency key personnel and ESCO project team should be at the post-award conference.  A sample of topics to be included is contained in Appendix C.  This meeting covers the aspects of clarifying contract requirements and assisting in the mobilization of contractor forces and/or subcontractors onto the construction site (security, badge/passes, vehicle permits, etc.).  It is extremely important to include those not involved in the contract negotiations since they need to be made current.  On larger projects, an Approval/Review/Authority matrix similar to that shown in Appendix D is often very useful to communicate the proper requirements to all parties as well as to track project status.

  - The list of Key Agency Personnel should be mobilized by the Agency at this time to make sure they are budgeted and available to provide timely support to the ESCO.  Project delays cause loss of energy and related O&M cost savings, which undermine the integrity of the project

  - The Project Description should be finalized by the ESCO and should include all the negotiated updates to the project as well as the final engineering design configuration as approved by the agency.

  - If the site-specific M&V plan in Final Proposal approved at DO award includes further data collection and existing equipment monitoring to finalize the energy baseline, the ESCO should proceed immediately with the documentation and establishment of the pre-construction energy baseline.  The Agency and the ESCO must agree with this baseline since it will be used for all performance verification and/or energy cost savings calculations unless modified in future years during the annual true-up.

  - The ESCO should initiate Engineering Design to finalize all ECM configurations, prepare construction packages, and obtain agency approval.

  - A final update of the M&V plan shall be provided if appropriate, incorporating documentation of the pre-construction energy baseline and giving full definition on instrumentation lists if any, locations, ranges, timing, etc. based upon the final approved engineering configuration.

  - Equipment and materials procurement should be initiated as soon as engineering drawings and specs are available and approved.  Long lead items should be initiated with an advanced approval if necessary.

  - The project manager and appropriate team members for the Agency should conduct weekly meetings with the ESCO to maintain current knowledge of project status, see Appendix E for outline.  Good communications are the key to success.

  - The Agency should conduct monthly review meetings with their upper management personnel to keep the Agency knowledgeable with the project status.  See Appendix F for suggested outline and topics.  The ESCO project manager should attend this meeting.  Good communications are the key to success.

  - As the project progresses from mobilization into engineering and procurement, followed by construction, and into commissioning and O&M, the project manager and key Agency personnel should monitor, review, and approve as necessary, all ESCO submittals in a timely manner.  A suggested form for formalizing and documenting the review is included in Appendix G.  The requirement is to ensure the design is proper and the equipment is proper and installed and tested to the requirements, etc.  The normal in-house policies and procedures should be adequate to control and document these functions.  A time limit should be imposed on the review cycle, in order to protect the schedule, after which the ESCO can proceed without risk.

  - Permitting requirements and Plans, as applicable for the Agency, for hazardous material, Environmental Protection Plan, Spill Contingency Plan, ground excavation, hot-wire work, lock & tag, crane and rigging, power outages, etc. should be followed and requested in a timely manner.  These permits should be coordinated by the ESCO and worked with the cognizant Agency personnel for approval.

  - After completion of engineering and prior to the start of construction, the Agency should conduct a pre-construction meeting to revisit the items from the post-award conference (see Appendix J for topics).  The intent here is to review, after completion of engineering design, to make any changes in the project that might effect work scope or the planning already accomplished.  A check of all permitting activities should be conducted with this meeting.

  - Configuration Control of all facilities is essential and should be maintained by proper control and monitoring by the Agency and the ESCO for all drawing red-lining and as-builts, to accurately document all changes and conditions within a facility.

  - The ESCO should submit a commissioning plan for approval prior to completion of construction.  The Agency should review and approve the plan.  As-Built drawings shall be accomplished at this time, preferably prior to commissioning, but definitely prior to acceptance.  Credit for energy cost savings usually coincides with completion of commissioning, but should be as defined in the DO.

  - The Agency should develop Functional and Operational Test Plans defining the requirements and duration of the testing for all equipment installed by the ESCO, based on the approved ESCO commissioning plan.  Agency should provide Project Manager or a representative to witness acceptance testing of ECMs as required.

  - The Agency Project Manager or representative shall prepare acceptances letter(s) for installed, tested and commissioned ECMs.  The agency will issue an acceptance letter to ESCO to initiate DO performance period.  A sample Project/ECM checklist is provided in Appendix J. Provide other implementation period close-out functions as required by agency.

Phase 5: Performance Period Through Close-out. (Annual Duties)

  - Phase 5 of the ESPC process starts when commissioning and government acceptances have been completed and the Operating and Maintenance begins.  The period for this phase is set forth in the DO award. The following (tasks 5-2 through 5-6) are required on an annual basis.

  - Verify that monthly invoices contain any required M&V documentation and approve invoices.

  - Manage, administrate, and communicate to verify that the ESCO is delivering the negotiated performance period services, including proper response times for service, proper preventative maintenance, quality of performance, etc.

  - Verify that the ESCO has delivered the guaranteed level of energy and related O&M cost savings over the year through review of the ESCO’s annual M&V report.  Prepare annual savings verification memo for contract file.

  - Resolve any annual true-up requirements for the energy baseline that are required due to changes of facility use, revision of equipment, etc.

  - Prepare ESCO performance evaluation reports for DOE annually.

  - Prepare close-out documents at end of DO term (last year only).

##### Phase 5 Activities Summary

| Frequency | ESCO | Agency |
| --- | --- | --- |
| Monthly | Provide any necessary reports describing quantity and type of savings and generate invoice. | Verify that monthly invoices contain any required M&V documentation and approve invoices. |
| Quarterly | Internally review service performance. Check response times, P.M. schedules, and customer satisfaction. | Verify that the ESCO is delivering the negotiated performance period services, including proper response times for service, proper preventative maintenance, quality of performance, warranties, etc |
| Annually | Submit annual M&V and True-up report showing energy and O&M savings. | Verify that the ESCO has delivered the guaranteed level of energy and related O&M cost savings over the year through review of the ESCO’s annual M&V report. Prepare annual savings verification memo for contract file. |
| End of Contract | Conduct agency training on ECMs, prepare final invoice and transfer equipment title and other project data? | Prepare close-out documents at end of DO term. |

# 3.0 SCHEDULES

Upper Level Project Review Criteria

Post award, pre-construction schedules shall be developed to define the major milestones for the project.  Gantt charts are recommended.  At a minimum, the schedule for upper level personnel review shall include:

| Super ESPC Delivery Order Development - Project Timeline |  |
| --- | --- |
| (Below is a suggested timeline, fill in actual timeline compatible with project size and plans. Times are Months After Go-Ahead (MAGA) or duration of periods) |  |
| Activity | Person/Group Responsible | Target Completion Date |
| Selection of ESCO | Agency |  |
| Initial Project Kick-off meeting | All | 0.5 MAGA |
| List of Buildings to Survey | ESCO | 0.5 MAGA |
| Initial Site Survey | ESCO | 1.0 MAGA |
| PMA Report (prelim measures assessment) | ESCO |  |
| Initial Prop Prepared, Issued and Presented | ESCO | 2.0 MAGA |
| Initial Proposal Reviewed/Questions to ESCO | Agency | 2.5 MAGA |
| Initial Proposal Consensus Meeting | All | 3.0 MAGA |
| Sign IAG with DOE | Agency/DOE | 3.0 MAGA |
| Letter of Intent to Award prepared & issued | Agency |  |
| DO RFP Finalized & issued | Agency | 4.0 MAGA |
| Meas. & Verification Meeting | All |  |
| DES Kick-off meeting | All | 4.5 MAGA |
| Complete DES, Prepare/Refine Estimates of Savings and Costs, Issue Findings (30% DESIGN) | ESCO | 2 – 3 MONTHS |
| Final Proposal Prepared & Issued | ESCO |  |
| Final Prop. Questions to ESCO | Agency | 30 DAYS AFTER PROPOSAL |
| Final Proposal Consensus Meeting | All | 45 DAYS AFTER PROPOSAL |
| Formal Negotiations Period Begins | All |  |
| DO Awarded | All | 6 - 9 MAGA |
| Post award kick-off meeting | All |  |
| Design/ OBTAIN QUOTES | ESCO |  |
| Final Comments to ESCO | Agency |  |
| Order Equipment | ESCO |  |
| Obtain Bids | ESCO |  |
| Installation | ESCO |  |
| Training | ESCO |  |
| Commissioning | ESCO |  |

Project Team Review Criteria

Detailed working schedules should be developed to control the work scope in more detail for the weekly coordination of the ESCO’s subcontractors and the facility personnel being impacted by the intrusion of the project into their living and/or work space.  Facility actions such as building availability, need dates for permits to turn services off or on, interruption of service, periods for building evacuation, site excavation, etc. shall be defined for purposes of coordination of efforts between the ESCO and the Agency.  The working schedule shall be prepared and maintained by the ESCO to define the near-term work scope for purposes of contract status reporting and evaluation of contractor performance.  This detailed schedule shall reside with the ESCO, but be made available to the Agency at least monthly to confirm schedule status and to allow proactive coordination of “soon-to-come-due” activities and requirements.

# 4.0 LEGAL AND CONTRACTUAL

Legal and Contractual issues of equipment ownership, liability for equipment failures, taxes, warrantees, environmental compliance, Federal, State, County, and Municipal laws and regulations, etc., as applicable, are as defined in the Contract and the Delivery Order.  All changes to the contracted effort must be implemented through the contracting officers of the signing parties.

# 5.0 SAFETY

Working in a safe environment is essential, and effort must be continuously accomplished to create the right “Safety Atmosphere”.  Appendix M contains a list of several checklists that are designed for a Project Manager and/or other top-level personnel.  The lists give only the more salient aspects of safety codes, and are not totally inclusive of all the requirements of OSHA, etc.  The lists are intended to give management and other upper level personnel enough knowledge and direction for them to make a cursory and easy inspection to see if general safety principles are being observed.  A few such inspections will also tell the workers that safety is important to management and must be taken seriously.  The ESCOs work crews and the Agencies personnel will be safer and a good safety program and atmosphere will reduce the Agencies’ liability.

Agencies provide Safety & Health inspections using S&H plans as prescribed by site-specific Agency policies and regulations.

# 6.0 COMMISSIONING

The ESCO shall commission each ECM to assure the government that ECMs perform in accordance with the design intent.  Design intent is defined as the detailed technical description of the ideas, concepts, and criteria defined by the building owner to be important, and including facility functional, operational and environmental needs. The commissioning will be accomplished through a process of verification and documentation, from design phase to construction acceptance that all ECMs perform interactively and in accordance with the design documentation and intent, and in accordance with the owner’s needs.  The ESCO shall supply to the government a commissioning plan that addresses each ECM and the steps that will be taken in the commissioning process. The plan outline addressing each ECM will be provided in the ESCO final proposal.  Specific ECM commissioning details will be further developed during the ECM design, procurement and installation phases and will be developed using a graded approach based on complexity.  Specific ECM commissioning plans will be issued for government review and approval with the design and construction package.

Commissioning is defined as “the process of ensuring that the systems are designed, installed, functionally tested, as capable of being operated and maintained to perform in conformity with the design intent.” (ASHRAE, 1966)

Equipment commissioning is required to verify both that the equipment has been properly installed per the original or the current redlined drawings, that it is operating per manufacture specifications, and that it is interfaced properly with the facility and is operating to the needs of the facility.

Acceptance is the responsibility of the Agency and assumes commissioning is completed.  Government may desire to run some operational tests, depending upon the equipment involved and the systems with which the equipment interfaces.  The Appendix J contains a suggested checklist for government Agency acceptance, and goes beyond the testing requirements to include the contract closeout activities.

The following is an explanation of the checklist items in Appendix J.

(a) All ECMs have been installed

Each ECM should be acknowledged by the ESCO to be complete and ready for inspection and commissioning.

(b) All ECMs have been through a Physical Installation Inspection to the requirements of all Drawings and Specifications

Each ECM should be inspected to insure it is installed per the project drawings and the component and/or system specifications.  This inspection confirms all electrical continuity and connections, lines, piping, and ducting are verified to be properly connected, with all valves, etc. in their normal unpowered position and all equipment is ready to be operated.  Electrical wiring should have passed any required testing to insure proper wire sizing, etc.

(c) All physical installation inspection discrepancies noted have been corrected

All discrepancies noted in the equipment installation inspection should be corrected and verified prior to equipment use.  This is required prior to the operation of the equipment.  Any that remain should be added onto the Project Punch List to track resolution status.

(d) All Items on the Project Construction Punch List completed and accepted.

The post-construction punch list shall be used to track the final completion of construction, and shall include not only the equipment installed by the contract, but also, all items associated with the installation of the equipment.  The punch list shall include everything from housekeeping, to construction scope, to all new and revised equipment interfaces, etc.  The intent is to have the facility back to the pre-installation conditions, but with the new equipment installed.

(e) Appropriate training on Operations and Maintenance was conducted for each ECM

All training shall be accomplished, and videotapes made of the training for future use to allow training of new hires and/or retraining of personnel.

(f) Operation and maintenance manuals and procedures have been provided and accepted.

Preliminary O&M manuals should be used as part of the training process and updated and approved after completion of ECM installation, with any updates and corrections provided to the training participants.  O&M procedures should be sufficiently detailed to allow the trained user to perform necessary maintenance.  This detail should include: lock and tag information, baseline operating conditions, necessary calibration equipment identification and steps, troubleshooting steps, spare parts listings and ESCO or manufacture contacts for support.

(g) Recommended spare parts lists and spares have been provided and accepted.

The spare parts lists and spares provisioning shall be reviewed and shall include sufficient information to maintain the ability to take advantage of all equipment warrantees

(h) As-Built drawings have been received and approved.

The As-Built drawings should be Job-Walked with the ESCO to insure completeness, accuracy, and Clarity.  The drawings shall agree with and supplement the operations and maintenance manuals and training.

(i) Post-installation measurement and verification set-up completed

The M&V installation shall be verified against the project proposal and with the M&V plan to insure it is capable of providing all information necessary to determine project performance for the periodic contractual verifications of savings.

(j) Post-installation Performance Baseline established.

The Post-installation Performance Baseline shall be established using the approved M&V instrumentation.

(k) Utility rebate inspections and paperwork approved and submitted.

Utility rebates are usually only available upon completion of the equipment installation and testing.  They must be submitted for payment at this time to insure the rebate is approved and available in a timely manner.

(l) Manufacturer warranty and registration paperwork submitted.

Warranty and registration issues are the responsibility of the ESCO, however, The Agency should insure that this has been submitted by the ESCO.

(m) All Delivery Order Data Submittals complete and accepted.

All Delivery Order Data Submittals that are not yet satisfied by the 95% installation complete should be noted on the construction punch list as open items to allow tracking of their status.

(n) Project Commissioning completed to approved Commissioning Plan and Accepted.

The ESCO is responsible for the development of and submittal of a commissioning plan, for Agency approval.  After completion of the commissioning in accordance with the plan, the completed commissioning report and data shall be submitted to the Agency for approval as part of the Agency final inspection and acceptance.

(o) All ECMs have performed properly for 30 days as of   _______________________

(p) Agency final inspection and acceptance is confirmed as of _____________________

The Agency declares that the project is complete and accepted.  This is co0ntractually noted by completion of the form in Appendix K, or its equivalent.  There are allowable exceptions, which are managed within the final acceptance form, shown in Appendix K.  ECMs may be installed in an off-season and cannot be fully tested.  The exceptions noted in the form in appendix K address those issues, i.e., ECMs that install air conditioners in Mid-winter, and the reverse for boilers.

Final Commissioning Report (Suggested Contents - Building Commissioning Guide July 1998)

- Project Name

- Name, address, firm, and phone number of Commissioning Authority

- Description of building, including size, location, use, construction type, HVAC systems, etc.

- List and description of commissioning tasks

- Commissioning Plan

- Complete Documents

- Completed design intent document

- Completed pre-functional test checklists

- Completed functional performance tests

- All non-compliance forms

- Summary of commissioning findings

- Recommendations for system recommissioning

- Recommendations for monitoring the ongoing performance of systems

- Recommendations for system improvements.

The acceptance form shown in Appendix K, or something equivalent, should be used to track the project through the completion of construction (starting with the punch list at construction 95% complete).  This form can process individual ECMs or partial scope of the total project, or can be used as the project acceptance document.  This form should be initiated with the Punch List, and maintained current as the project closeout occurs.  Allowances are made for ECMs such as heating or cooling, which are completed in the off-season, and must wait for testing at a later date.   Also, it allows for acceptance of ECMs that can be accepted while other ECMs are waiting for closeout.  Beneficial use then can be made of completed ECMs without impacting warrantees, etc.

APPENDICIES

LIST OF APPENDICES

A	List of Acronyms

B	Preliminary Proposal Kick-off Meeting Agenda

C	Post Award Conference

D	Approval/Review/Authority Items

E	Weekly Meeting Agenda

F	Monthly Review Agenda

G	Material/Design Review Form

H	M&V for ESCO Final Proposal

I	Pre-Construction Checklist

J	Project/ECM Acceptance/Commissioning Checklist

K	Construction Completion Document

# APPENDIX A - ACRONYMS AND ABBREVIATIONS

BAS		Building Automation Systems

CO		Contracting Officer

COR		Contracting Officer's Representative

DES		Detailed Energy Survey

DO		Delivery Order

DO-RFP	Delivery Order-Request for Proposal

DOE		U.S. Department of Energy

ECM		Energy Conservation Measure

EPA		Environmental Protection Agency

ESPC		Energy Savings Performance Contract

ESCO		Energy Service Company (also referred to as "contractor")

FEMP		(Office of) Federal Energy Management Program(s)

IDIQ		Indefinite Delivery Indefinite Quantity

M&V		Measurement and Verification

NEPA		National Environmental Policy Act

O&M		Operations and Maintenance

OSHA		Occupational Safety & Health Act

PE		Licensed Professional Engineer

QA/QC	Quality Assurance/Quality Control

RFP		Request for Proposal

RO		DOE Regional Office

# APPENDIX B –KICK-OFF/DES MEETING AGENDA

Team Introductions

- Agency

- ESCO

- DOE COR and Project Facilitator  (if FEMP Services acquired)

DO Review & Comments

- This item is only applicable for Government–Identified projects (DO RFP is developed later for Contractor-Identified projects).

Scope of work

- This should cover items that are exceptions…particular areas of the facility that cannot be entered or ECMs the site has determined should not be done. Share info on known problems any project must resolve, must-have items, nice-to-have items, etc.

- Facility Master Plan information.

- Potential energy related O&M Savings.

- Design Intent – Commissioning Requirements Discussion.

Preliminary Site Survey Process & Logistics

- Utility rates for gas, oil, coal, electricity, water.

- Access to mechanical rooms –

- Drawings –

- Interviews with Building Management - On site contacts.

- Site Security Requirements -

- Communications - Key Contacts, Conference Call Update Schedule.

- Design Standards, Design Basis, Design Intent & Commissioning

Anticipated Project phases and schedule

- (E) Preliminary Survey and Initial Proposal -  time frame ______ days

- (G) Government review ___ days - Government review requirements

- (E) Detailed Energy Survey and Final Proposal -  time frame ______ days

- (G) Congressional Notification (30 days) –

- (G) Government review and final proposal negotiations ___ days

- Award Target date – ______

- (E) Design (____ weeks – depends on ECM complexity)

- (E) Construction (____weeks – depends on ECM complexity)

- (E) Substantial completion and target acceptance date ______.

- (E) Testing, commissioning, training dates _____, _____, _____

Other Issues

- Rebates from utilities.

- Agency/DOE actions

- Discuss agency process, approval authorities for Congressional Notification

- Discuss agency funding for equipment or energy systems replacement or repair that could be applied as buy down if impacted by ESCO proposed ECMs

Review Requirements

- Proposal Transmittal Copies & Distribution

- Items to be reviewed

Action Items with Associated Due Date

- Agency

- ESCO

- DOE/PF  (if FEMP Services acquired)

Proposal Requirements

- Contract

- Baseline & M&V

- Energy versus O&M Savings

Attendee Listing

- Name, phone, fax, email, address, title, agency or company, project assignment

# APPENDIX C – POST AWARD CONFERENCE

CONFERENCE AGENDA

- Team Introductions

- Agency Acquisition Team

- ESCO Project Team

- DOE COR & Project Facilitator  (if FEMP Services acquired)

- Safety & Environmental

- Job site safety walk-down and supervisor orientation schedule.

- Safety aspects of job evaluated, identified and workers informed.

- Check worker licensing and certifications.

- Burn Permit approval requirements.

- OSHA health cards up-to-date as required by site.

- Scaffolding inspections signed.

- Check job-site for any confined spaces and insures compliance with entry.

- Check to insure any underground utilities have been located and identified.

- Check to insure any in-the-wall utilities have been located and identified.

- Check to insure all hazardous materials either stored or as a part of the facility, has been located and identified.  Site specific requirements for hazardous material handling identified.

- Insure all personnel have been made aware of fire exit corridors and procedures.

- Site Injury reporting and response requirements.

- Emergency Notification Process.

- Environmental permits prior to construction.

- Organization and Communications

- Key Contractor and site contacts. (Names/Phone/Cell/Pager)

- Schedule for design/construction update meetings.

- Change notice review and approval process.

- Emergency Notification Process.

- Timeline – Design/Construction Schedule

- Design and design approval schedule.

- Service Interruptions Scheduling

- Construction Schedule.

- Design

- Design Intent Review – requirements for ECMs.

- Engineering drawing approval requirements – prior to construction.

- Redline authority approved for as-build drawings during construction.

- Equipment data sheets submittal and approval requirements.

- Facility Access & Security Requirements

- Contractor personnel site and/or building access requirements.

- Security Badges.

- Escorts.

- Allowable equipment.

- Vehicle Access approval requirements.

- Outages

- Utility service interruption permits approval.

- Utility reconnect permits approval. (Including hot-wire permits.)

- Site personnel support for outages.

- Construction

- Excavation permits approval requirements.

- Crane movements and locations reviewed for overhead hazards.

- Construction start coordination requirements. (Building manager and occupants).

- Materials and equipment confirmed at job-site or scheduled to arrive prior to need.

- Establish acceptable lay-down yard and/or office space allocations for contractors.

- Job/Work lists prepared and approved.

- All worker certifications (welding, electrical, etc.) up-to-date.

- All vehicle licensing up-to-date.

- Commissioning

- Commissioning Requirements

- Commissioning Plan Approval

- Acceptance After Completion of Commissioning.

# APPENDIX D – APPROVAL/REVIEW/AUTHORITY ITEMS

APPENDIX D – APPROVAL/REVIEW/AUTHORITY (Continued)

# APPENDIX E – WEEKLY MEETING AGENDA

The following are a suggested list of topics to be discussed with the ESCO on a weekly or BI-weekly basis to establish the status of the project.  The items reviewed will change as the project progresses from initiation to completion.  Weekly meetings are to be attended by the Agency, the ESCO, and any of the ESCO subcontractors required to properly obtain accurate current status.

- Safety Issues and topics.

- Procurement activities.  Status of long term items, soon to come do items, overall percent complete of procurement and status of deliveries compared to construction requirements.

- Design Status.  Status of engineering design and discovery of any deviations from original ECM concept as a result of the design progression.

- Baseline documentation Status,

- Permits status.  Environmental, excavation, utility interrupt/activation, etc.

- Construction status.  Percent complete, areas in-process, punch list resolution, etc.

- M&V Status.

- Test Status.  Percent complete,

- Commissioning Status.

- Review of Action Item List.

- Issues and Concerns.  Any problems requiring coordination, problems delaying progress, problems causing changes, etc.

# APPENDIX F – MONTHLY REVIEW AGENDA

Monthly review meetings should be held with Agency management personnel to relate to them the top-level status of the project, to solicit support for any show stoppers, and to give a project overview.  Detail as discussed in the weekly meetings is not required at this level.  The DOE Project Facilitator, the Agency Project Manager, the Energy Manager, the Lead Engineer, the Agency CO, and the department heads should attend this meeting for each of these individuals.  It may be proper to also include building managers, etc. where construction is in progress.  Topics should include:

- Safety issues and topics.

- Overview of the schedule including percentage completion’s for Procurement, Engineering Design, Construction, and Testing.

- Status of any Agency requirements to support the project, such as environmental permitting, review/approval of ESCO submittals, ECM acceptance, etc.

- Summary of Agency support costs and budgets for the project.

- Issues and Concerns.  This will be the major items from the weekly issues and concerns, plus any requirements the Agency is having difficulty in providing.

- Action Item List Review. (Major topics requiring Management attention)

# APPENDIX G – MATERIAL/DESIGN REVIEW FORM (Sample)

# APPENDIX H – M&V FOR ESCO FINAL PROPOSAL

Checklist for M&V Plan and Periodic Submittals (Post DO Award)

- Baseline Equipment and Conditions.

- Existing equipment (inventory and performance) is defined.

- Space conditions (foot-candles, temps, etc.) are defined.

- Assumptions and stipulations- show supporting information or measurements.

- How and why any baseline adjustments will be made is discussed.

- Post-Installation Equipment and Conditions.

- Plan for defining new equipment (inventory and performance) is described.

- Plan for defining new space conditions (foot-candles, temps, etc.) is described.

- Assumptions and stipulations- show supporting information or measurements to be taken.

- Metering equipment is specified.

- Schedule of metering, including duration and when it will occur is defined.

- Who will provide equipment, establish and ensure its accuracy and perform calibration procedures, is described.

- How data from metering will be validated and reported, including formats, are defined.

- How electronic, formatted data, directly from a meter or data logger, will be provided.

- Any sampling that will be used, sample sizes, documentation on how sample sizes were selected, is defined.

- Annual verification and measurement activities are defined.

- Who will conduct the M&V activities and prepare M&V analyses and documentation is defined.

- How quality assurance will be maintained and repeatability confirmed is defined.

- Reports are defined, including what they will contain and when they will be provided.

- Electronic formats and software programs to be used for reporting are defined.

- Initial and annual M&V costs for each measure (totals only).

# APPENDIX I – PRE-CONSTRUCTION CHECKLIST

PRE-CONSTRUCTION CHECKLIST

- Job site walked for safety and supervisor orientation.

- Make arrangements for all contractor personnel to have site and/or building access.  Names and identification should be supplied.

- Check worker licensing and certifications for all effected personnel.

- Excavation permits all approved.

- Crane movements and locations reviewed for overhead hazards.

- Utility service interruption permits approved.

- Utility reconnect permits approved. (Including hot-wire permits.)

- Engineering drawings approved for construction.

- Redline authority approved for as-builts drawings during construction.

- OSHA health cards up-to-date for at least one person per crew per shift.

- Construction start coordinated with building manager and occupants.

- Materials and equipment confirmed at job-site or scheduled to arrive prior to need.

- Equipment data sheets submitted and approved.

- Job/Work lists prepared and approved.

- Safety aspects of job evaluated, identified and workers informed.

- All worker certifications (welding, electrical, etc.) up-to-date.

- All vehicle licensing up-to-date.

- Scaffolding inspections signed.

- Check job-site for any confined spaces and insure compliance with entry.

- Check to insure any underground utilities have been located and identified.

- Check to insure any in-the-wall utilities have been located and identified.

- Check to insure all hazardous materials either stored or as a part of the facility, has been located and identified.

- Insure all personnel have been made aware of fire exit corridors and procedures.

- Establish acceptable laydown yard and/or office space allocations for contractors.

# APPENDIX J– PROJECT/ECM ACCEPTANCE CHECKLIST

SUPER ESPC

ECM INSTALLATION and PROJECT ACCEPTANCE

CHECKLIST FOR GOVERNMENT ACCEPTANCE

Date:

_________	All ECMs have been installed

_________	All ECMs have been through a Physical Installation Inspection to the requirements of all Drawings and Specifications _________	All physical installation inspection discrepancies noted have been corrected

_________	All Items on the Project construction Punch List are completed and accepted.

_________	Appropriate training on Operations and Maintenance was conducted for each ECM

_________	Operation and maintenance manuals and procedures have been provided and accepted.

_________	Recommended spare parts lists and spares have been provided and accepted.

_________	As built drawings have been received and approved.

_________	Post-installation measurement and verification set-up completed.

_________	Post-installation Performance Baseline established.

_________	Utility rebate inspections and paperwork approved and submitted

_________	Manufacturer warranty and registration paperwork submitted

_________	All Delivery Order data Submittals are complete and accepted.

_________	Project Commissioning completed to an approved Commissioning Plan and accepted.

_________	All ECMs have performed properly for 30 days as of ________

_________	Government final inspection and acceptance is confirmed as of _________

_____________________________		_

Project Technical Representative

______________

Date

# APPENDIX K – CONSTRUCTION COMPLETION DOCUMENT

| CONSTRUCTION COMPLETION DOCUMENT |
| --- |
| Project Title: (or ECM (s) Title) |
| Project No.: | Delivery Order No.: | Assigned Performer: (e.g. Major subcontractor) |
| Total Formal Construction Project Partial Formal construction Project (e.g. system or ECM) Minor Construction Activity |
| SECTION 1A. Completion of Construction and Construction Acceptance Testing. (Signature in Section1A document Completion of Physical Construction and Inspection) Describe the formal construction Project, Partial Project (e.g. system or ECM), or minor construction Activity being documented as Physical construction and Inspection complete: |
| No Exception List Exception List Attached |
| Assigned Performer Signature: (e.g. Major Subcontractor) | Agency Acceptance Inspection Signature: |
| SECTION 1B. Completion of Exceptions: (Signature in Section 1B document that the above Exceptions List, if any, has been completed and accepted and/or funds have been accrued to complete remaining minor exceptions and remaining project financial obligations) All exceptions resolved. ____Funds accrued for remaining exceptions (list attached) |
| Assigned Performer Signature: (e.g. Major Subcontractor) | Agency Acceptance Inspection Signature: |
| SECTION 2A Completion of Operation Testing, Commissioning and approval of Test results. (Signatures in Section 2A document Engineering approval of Operational and Commissioning Test results and operational acceptance and/or beneficial use of the completed system/project. |
| No Exception List (Section 2A NOT required) Exception List Attached |
| Assigned Performer Signature: (e.g. Major Subcontractor Engineering) | Agency Acceptance Inspection Signature: |
| Assigned Performer Signature: (e.g. Major Subcontractor Operations) |  |
| SECTION 2B Completion of Exceptions (signatures in Section 2B document that exceptions identified in Section 2A hve been completed) |
| Assigned Performer Signature: (e.g. Major Subcontractor) | Agency Acceptance Inspection Signature: |