4450.1 REV 1

__________________________________________________________________________

CHAPTER 1.  DATA

1-1   PURPOSE.  Fast, accurate cost estimates depend on valid

preassembled data.

A.   The Chief of the cost staff is responsible for seeing that

information is collected and recorded.

1) Identify and store for quick retrieval of particular

information.

2) File using the 16 trade divisions of the Uniform System

for Construction Specifications, Data Filing and Cost

Accounting.

B.   Review data annually or more often to update or remove

obsolete information.

C.   Field survey all data at least annually to obtain current

information from the construction industry.  Surveys may be

by interview, telephone or correspondence.

1) Sources are general contractors, subcontractors, material

suppliers, equipment lessors, developers, mortgagees,

architects and engineers, bonding companies, utility

companies, testing labs, local and state agencies, and

other Federal agencies.

2) Develop a wide range of information sources and establish

a working rapport to assure factual data.

a)  Use tact, judgment and common sense.

b)  Explain the purpose and use of the information and

the mutual benefit.

c)  Assure the source of information will be kept

confidential.

1-2   DATA BANKS.  Collect and maintain project cost data for later

use in making project cost estimates based on comparability.

A.   Use a numerical coding system for the Field Office to

describe the work in each trade item shown on Form FHA 2326,

Project Cost Estimate.  Base the code on the 16 trade divisions

of the Uniform System for Construction specifications, Data

Filing and Cost Accounting.

__________________________________________________________________________

1-1                                   5/88

_____________________________________________________________________

4450.1 REV 1

__________________________________________________________________________

(1-2)       1)  Assign code 00 for the most typical material, labor and

equipment composition of a trade item.

2)  Code significant variations from the most typical, 01

through 99.  Variations will frequently be combinations

of other coded descriptions.

3)  Example:

Division 11, Trade Item-Appliances

00 - Refrigerator, range and oven

01 - Garbage disposal plus 00

02 - Dishwasher plus 00

03 - Dishwasher plus 01

04 - Range hood plus 00

05 - Range hood plus 01

06 - Range hood plus 03

4)  Avoid elaborate and extensive codes or coding for minor

variations.

5)  A single coding system for each trade item is desirable,

but it may be necessary to establish separate coding

systems for certain project types and structural

systems to describe all data.

B.   Record data from accepted Form FHA 2328, Contractor's and/or

Mortgagor's Cost Breakdown, cost certifications, and

conventionally financed projects.

1)  Before entering a project, review the cost of all trade

items.  Purge any cost that is excessive according to

other verified data.  Do not record for data purposes

any cost that is not valid.

2)  Make entries on Form FHA 2326.  Use the numerical coding

system to describe the work in each trade item for the

project.

3)  File the Form FHA 2326 by:

a)  Conventional or Section of the Act (202, 207,

221(d)(4), etc.).

b)  Project type (Detached, semi-detached, row, two-story

walk-up, etc.).

c)  Structural system (wood, frame, masonry, concrete,

etc.).

__________________________________________________________________________

5/88

1-2

_____________________________________________________________________

4450.1 REV 1

__________________________________________________________________________

(1-2) C.  Review data banks

1)  Replace Form FHA 2328 costs with certified cost after

cost certification review.  Include the cost effect of

approved change orders in the certified data.

2)  Enter as the effective date of the data the month and

year of the actual construction start not the estimated

start.

3)  Remove data older than 4 years unless it is for a unique

project type or structural system and necessary to provide

comprehensive data banks.

1-3   BENCH MARKS.  Develop and record costs of trade item elements,

trade items, and building components typical in construction

in the Field Office jurisdiction for adjusting comparables,

preparation of supplemental estimates, and review of change

orders and cost certifications.

A.  Establish Bench Marks from data bank costs, commercial

building cost data (Means, Dodge, etc.), and quotations of

field sources.

1)  Prepare a worksheet for each bench mark describing the

item, data source, calculation of cost with basis of

measurement, and summary.

2)  In demolition bench marks, include the salvage value of

recoverable materials.

3)  Use typical units of measurement (i.e., square foot-gross

square foot, linear foot, cubic yard, lump sum).

The summary must be convertible to gross square-foot or

per-unit cost for use in cost estimation.

4)  Code each trade item in the bench mark.

5)  Identify the effective date of the costs.

B.  File bench marks alphabetically or by trade division.

C.  Review bench marks annually or as often as necessary to up-date

costs.  The bench mark is valid as long as the cost is

current.  Remove a bench mark only when it is no longer

useful or not current.

__________________________________________________________________________

5/88

1-3

_____________________________________________________________________

4450.1 REV 1

__________________________________________________________________________

1-4   ALLOWANCES AND FEES.  Collect information from data bank projects

and field sources on typical allowances and fees in the Field

Office jurisdiction.  Record as lump sum dollar amounts or a

percentage.

A. General Requirements is an allowance for the general

contractor's Job overhead for a specific project.

1)    Items will vary due to project type, location and site

conditions.  Include:

a) Supervision and Job site engineering.

b) Job office expenses including clerical wages, whether

on-site or offsite, if for the project.

c) Temporary buildings, tool sheds, shops and toilets.

d) Temporary heat, water, light and power for construction.

e) Temporary walkways, fences, roads, siding and

docking facilities, sidewalk and street rental.

f) Construction equipment rental not in trade item

costs.

g) Clean-up and disposal of construction debris.

h) Medical and first aid supplies and temporary

facilities.

i) Watchman's wages, security cost, and theft and

vandalism insurance.

2)   Salaries of owners, partners or officers of the general

contracting firm are not part of general requirements.

Actual work on the job in a trade or supervision is

allowable.

B.  Builder's Fee is the profit and overhead of the general

contractor.  Gather data on customary fee for various project

types, sizes and structural systems.

1)   General overhead is the cost of continuing operations of

a building construction firm.

2)   Profit is the return anticipated for providing building

construction services under competitive conditions.

For a specific project consider:

__________________________________________________________________________

5/88

1-4

_____________________________________________________________________

4450.1 REV 1

__________________________________________________________________________

(1-4)          a)  On-site construction time.

b)  Work performed by the general contractor.

c)  Number of subcontractors and extent of subcontract work.

d)  Risk and responsibility.

3)  In processing, estimate the builders fee from data as a

percentage.

a)   Always compute general overhead as 2 percent of the

total cost of land improvements, structures and general

requirements.

b)   Apply the remaining percentage to the same total

cost to determine profit.

4)  For projects with a Builder's and Sponsor's Profit and

Risk Allowance (BSPRA), compute only the 2 percent

general overhead as the builders fee.  Do not include

an amount for profit.

C.   Architect's Fees are the typical amounts paid professionals

for design and construction contract administration

(supervision).

1)  Include information on architectural, structural,

mechanical and other engineering and consultant services.

a)   Data must be convertible to a fixed fee (stipulated

sum) but may be on the basis of:  a percentage of

construction costs; stipulated sum; hourly billing;

fixed fee plus expenses; multiple of direct expenses;

or any other local practice.

b)   Separate data for design and supervision services.

2)  In estimating the architect's fees for a specific project

use data from projects similar in design and services

rendered.

a)   Determine the professional services from review of

the project's Owner-architect Agreement, AIA Document

B1 1.

b)   Consider all factors in the agreement that may

influence the fees--such as repetition, redesign,

design complexity, research, client identity, location.

__________________________________________________________________________

5/88

1-5

_____________________________________________________________________

4450.1 REV 1

__________________________________________________________________________

(1-4)           c)  Use the fees stated in the Agreement unless totally

unreasonable in comparison with data.

d)  Document the method of estimating the fees.

D.   Bond Premium is the typical cost for various bonds required

for building construction.

1)  Record data at the rate charged.

2)  Use the applicable rates to calculate the cost of the

bond premium for a specific project.

E.   Other Fees are the costs of various required items and

services.  Record data as typically a cost to either the

owner or contractor.

1)  Site and topographic surveys.

2)  Subsurface exploration (test borings).

3)  Soil tests, concrete tests, and other construction

testing.

4)  Fees for utility taps and connections.

5)  Building permits and licenses.

6)  Fees for cost certification.

1-5    CONSTRUCTION TYPE.  Record number of months required to construct

various types of projects.

A.   Categorize this data by:

1)  Project type.

2)  Structural system (A further breakdown between on-site

"stick built" and factory components or modules may be

made).

3)  Number of units.

B.  Plot the data on graphs.

1)  Develop a graph for each project type and structural

system.

__________________________________________________________________________

5/88

1-6

_____________________________________________________________________

4450.1 REV 1

__________________________________________________________________________

(1-4)      2)   Units are on the left, vertical, increasing in number

from the bottom.

3)   Months are on the bottom, horizontal, increasing in

number from the left.

4)   Each project's construction time is a dot opposite the

number of units and over the number of months for

construction.

5)   Draw a trend line interpolating the data.

6)   Example:    Two-Story Walk-up          Wood Frame

***********************************************************************

*       140                                                           *

*                                                                     *

*  U    130                                                           *

*                                                                     *

*       120                                                           *

*                                                                     *

*  N    110                                                           *

*                            GRAPHICS  MATERIAL                       *

*       100                                                           *

*                                    IN                               *

*  I     90                                                           *

*                                 ORIGINAL                            *

*        80                                                           *

*                                 DOCUMENT                            *

*  T     70                                                           *

*                                  OMITTED                            *

*        60                                                           *

*                                                                     *

*  S     50                                                           *

*                                                                     *

*        40                                                           *

*                                                                     *

*        30                                                           *

*                                                                     *

*        20                                                           *

*                                                                     *

*           6  7  8  9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24   *

*                                                                     *

*                                M O N T H S                          *

*                                                                     *

***********************************************************************

C.  Estimate the construction time for a project from the graph

for the applicable project type and structural system.

1)  Make any adjustments due to knowledge of the job, such

as location, contractor, or labor and material market.

2)  Document the method of estimating the construction time.

__________________________________________________________________________

1-7                               5/88