4450.1 REV 1

__________________________________________________________________________

CHAPTER 7.  COST ESTIMATION - SUBSTANTIAL REHABILITATION

7-1   General.  In developing the Cost Estimate for substantial

rehabilitation of a project follow the instructions of other

Chapters of this handbook except as modified by the following.

7-2   Processing Stages.  The Field Office may allow the sponsor to

combine the processing stages.  When stages are combined,

instructions will be combined as appropriate.

A.  Preapplication.  Cost personnel will attend the preapplication

conference where sponsor discusses the rehabilitation

proposal.

1)  Current physical characteristics and condition of

the project.

2)  The rehabilitation proposed.

3)  Tentative per unit cost.

B.  Feasibility.

1)  Exhibits:

a)  Application.

b)  Project location map and survey or site plan.

c)  Drawings or sketches of the existing buildings and

description of the proposed rehabilitation, including

any post-rehabilitation sketches.

d)  Sponsor's cost estimate for proposed rehabilitation.

2)  Participate in a joint inspection of the project to

compare the sponsor's exhibits with on-site conditions

to determine:

a)  Actual extent of rehabilitation.

b)  Character of structure and materials.

c)  Type of benchmark data necessary for estimate.

3)  Assist the Design Representative in preparing HUD work

write-up.

__________________________________________________________________________

5/88

7-1

_____________________________________________________________________

4450.1 REV 1

__________________________________________________________________________

(7-2)     4)  Prepare a preliminary estimate based on HUD work write-up.

a)  Include an amount for contingency reserve.

b)  Estimate the date of the start of rehabilitation

and length of the rehabilitation periods

C.  Conditional Commitment.

1)  Exhibits:

a)  Application.

b)  Preliminary drawings and/or specifications as

required by the HUD work write-up.

c)  Sponsor's detailed cost breakdown.

d)  Owner-Architect Agreement (if professional services

are required).

e)  Other cost exhibits required by the work write-up.

2)  Make the HUD estimate of rehabilitation cost.

a)  Estimate cost of land improvements and supplemental

estimates on Form FHA 2325.

b)  Estimate cost of the structural trade items on Form

FHA 2326-A.

c)  Summarize cost of land improvements, structures

and supplemental estimates on Form FHA 2326.

include applicable fees.

3)  Estimate the contingency reserve percentage and enter

in Section O of Form HUD-92264.

4)  Estimate starting date and length of the rehabilitation

period and enter the number of months in Section G of

Form HUD-92264.

D.  Firm Commitment.  Review the application, final drawings

and or specifications if required by HUD work write-up,

and the Form FHA 2328.

1)  Confirm previous cost conclusions.

__________________________________________________________________________

5/88

7-2

_____________________________________________________________________

4450.1 REV 1

__________________________________________________________________________

(7-2)      2)  Develop a new estimate if exhibits reveal significant

changes that affect cost.

3)  Combine all procedures in firm processing if conditional

commitment is skipped.

7-3   Bench Mark Costs.  Use bench mark data for trade items in

costing-out HUD work write-up.

A.   Project the cost of trade items to the estimated start of

rehabilitation.

B.   Consider in the trade items the cost of repair and/or

removal prior to rehabilitation.

7-4   Allowances and Fees.

A.   Use data that reflects the risk and responsibility inherent

in rehabilitation and considers the location of project.

B.   For projects entitled to a Builder's and Sponsor's Profit

and Risk Allowance, do not include profit.  Assume a normal

builder's profit in computing fees and bond premium.

7-5   Rehabilitation Time.  Estimate from a graph of available data

on the actual length of time required to rehabilitate projects.

Include adjustment of time for demolition as repair and

rehabilitation cannot begin until demolition is complete.

7-6   Demolition.  Estimate the cost of demolition in the work write-up

considering the salvage value of material or equipment.

A.   Include demolition cost directly related to refurbishing

structures and land improvements (site preparation) in

the applicable trade item cost.

B.   Show demolition costs for total interior removal (gut job)

within exterior walls in Division 13, Special Construction.

C.   For total removal of an existing structure (footings,

foundations, utilities, etc.), disposal of debris, fill

and compaction, describe and show the cost on Form FHA 2326

and enter in Section O of Form HUD-92264 and interline in

Section g, line 36, if part of construction contract.

1)  Include general requirements, overhead and the profit.

2)  Where demolition cost is a lump sum bid by a general

contractor or subcontractor, note in the file.

__________________________________________________________________________

5/88

7-3

_____________________________________________________________________

4450.1 REV 1

__________________________________________________________________________

(7-6)      3)  Keep worksheets describing all items and costs in the

project cost binder.

4)  Form FHA 2328 shall include a description and cost of

total demolition if part of construction contract.

7-7    Contingency Reserve.

A.  Estimate a percentage of 0 to 10 percent depending on:

1)  Existing condition of the project.

2)  Extent of rehabilitation.

3)  Experience and financial capacity of the sponsor and

contractor.

B.  Enter the recommended amount and percentage of the contingency

reserve in Section 0 of Form HUD-92264.

7-8    Rehabilitation Cost Not Attributable To Residential Use.  Use

the format In Figure 1, completing the mathematical computations

in items 1, 2, and 3, and send to Valuation.

__________________________________________________________________________

5/88

7-4

_____________________________________________________________________

4450.1 REV 1

__________________________________________________________________________

Figure 1

REHABILITATION COST NOT ATTRIBUTABLE TO RESIDENTIAL USE

1.  Total Rehab Cost

(Without fees -Lines G 36c. + G 41.)  **           $____________

2.  Rehab Cost Not Attributable

(Dollar amounts without fees)  **                  $____________

3.  Ratio of Not Attributable

Project Not Attributable Square Feet

__________ sq. ft. divided by Total

Project Gross Square Feet ________ sq. ft. ** =     ___________%

4.  "As-Is" Not Attributable

Total "As-Is" (Land and Structures)

$_________  X Ratio from #3 _________ %       =    $____________

5.  Total Cost Not Attributable

"As-Is" Not Attributable (#4) $_________

and Rehab Cost Not Attributable (#2)

$______________                               =    $____________

6.  Cost Without Fees

Total Rehab Cost Without Fees $__________

(From #1) + Total "As Is" Value $________

(From Line 73. of Form FHA 2264) = Total      =    $____________

7.  The Percentage Not Attributable

Divide Total Rehab Cost Not Attributable

(#5) $__________ by Total Cost Without

Fees (#6)                                           ___________%

8.  Line G 74.

Total Estimated Replacement Cost of

Project* $__________ X

Percentage Not Attributable (#7) _________%   =    $____________

*  The Total Estimated Replacement Cost must be that developed by

a Replacement Cost Formula.  Cost Not Attributable must not be

adjusted if the Total Estimated Replacement Cost later changes.

** From Cost Analyst

__________________________________________________________________________

5/88

7-5

*U.S. GOVERNMENT PRINTING OFFICE 1988-201-923:6O389