Draft Proposal
(For Internal Review Only)

Desert Tortoise Public Attitude and Public Outreach Effectiveness – Phase 1

Funding Source:	National Fish and Wildlife Foundation

Contact Person:	John Hamill
Department of Interior
California Desert Management Project
222 East Main St.
Suite 202
Barstow, CA 92311
760-252-6108
john_hamill@dmg.gov

Principle Investigators: 
Jerry J. Vaske
Professor
970-491-2360
jerryv@cnr.colostate.edu

Maureen P. Donnelly
Associate Professor
970-491-2023
maureend@cnr.colostate.edu

Colorado State University
Department of Natural Resource Recreation and Tourism
Human Dimensions in Natural Resources Unit
Fort Collins, CO 80523

Copies of the Co-PI’s curriculum vitae are available at the following web site:
http://www.cnr.colostate.edu/NRRT/people/faculty.htm#Faculty

Starting date:	April 1, 2005

Ending date:	April 1, 2006

Background

In 1990, the desert tortoise (Gopherus agassizii) was listed as a threatened species under the Endangered Species Act.  The U.S. Fish and Wildlife Service designated 6.4 million acres of the desert tortoises’ range as critical habitat in 1994.  About 75%, or 4.8 million acres of this habitat, is located in California primarily on Bureau of Land Management, National Park Service, and Department of Defense lands.  Decreases in the population of the desert tortoise have been attributed to human related impacts (e.g., unauthorized off-road-vehicle use in the desert, collection of tortoises as pets).

The “Desert Tortoise Public Attitude and Public Outreach Effectiveness” study is designed to obtain baseline information that will facilitate the development and implementation of an education program to build public support for and involvement in the desert tortoise recovery effort. This study has two phases.  Phase 1 will obtain baseline data on public knowledge, attitudes, and value orientations regarding the desert tortoise and conservation recovery efforts.  The information collected in phase 1 can be used by federal and state agencies to develop effective public outreach communication strategies.  Phase 2 involves a follow-up survey to evaluate the effectiveness of these communication efforts.

This proposal and requested funding focuses on phase 1 of the overall study.

Phase 1 Objectives:

The objectives of phase 1 are to obtain information on different stakeholder groups’:

1.	Knowledge regarding the desert tortoise, its habitat, and on-going recovery efforts.

2.	Value orientations toward threatened and endangered wildlife (e.g., the desert tortoise) and broader desert conservation issues.

3.	Attitudes and norms toward the desert tortoise and agency sponsored recovery efforts.

4.	Current behaviors (e.g., Off-High-Vehicle use and collection of desert tortoises).

The information collected in phase 1 will be used to make recommendations for developing effective public outreach messages.

Study Methods – Phase 1

Phase 1 of this study will use a mail survey to collect the information. The Colorado State University Human Dimensions in Natural Resources Unit will develop the survey in cooperation with representatives from the Department of Interior and selected stakeholder groups. Approval for conducting the survey will be obtained from the Office of Management and Budget (OMB) and the Colorado State University Office of Sponsored Programs.  The questionnaire will be pre-tested before conducting the full mailing. Data collection will involve: an initial mailing of the survey, a post card reminder, and two final survey mailings to non-respondents.

The sample will contain random samples of individuals representing three different strata:

- California general public

- California Off Road Vehicle Association (CORVA) members

- California Conservation Group members

Random samples of the California general public will be purchased from Survey Sampling Inc.  A random sample of CORVA members will be requested from that organization.  The specific conservation group included in the study will be determined in collaboration with representatives from the Department of Interior.  The desired sample size for each of the three strata is 300 respondents, which yields a confidence interval of 90% and a margin of error of + 5%. Based on previous experience, we anticipate a response rate of about 38% from the general public sample and 54% from each of the two special interest group samples (Table 1). A telephone survey of non-respondents will be conducted to test for non-response bias.  If the data from the phone survey indicate differences between respondents and non-respondents, the data will be weighted accordingly.

Table 1. Strata, projected response rate and desired sample size

| Strata | Sample | Projected Response Rate | Desired Sample Size |
| --- | --- | --- | --- |
| 1 | California general public | 38% | 300 |
| 2 | CORVA members | 54% | 300 |
| 3 | Conservation group members | 54% | 300 |
|  | Total sample size |  | 900 |

Timeframe and Deliverables:

| Task | Date |
| --- | --- |
| Survey development and pre-testing | April – June, 2005 |
| Sample selection | April – May, 2005 |
| OMB approval of survey | June, 2005 |
| 1st mailing of survey | July 11, 2005 |
| Postcard reminder | July 25, 2005 |
| 2nd mailing of survey | August 8, 2005 |
| 3rd mailing of survey | August 29, 2005 |
| Data entry | July – September, 2005 |
| Telephone non-response check | September, 2005 |
| Data analyses | October, 2005 |
| Develop draft report | November – December, 2005 |
| DOI review of draft report | January, 2006 |
| Conference call to discuss results | February, 2006 |
| Final report | March, 2006 |

Budget:

| Category | Amount |
| --- | --- |
| Principal Investigators |  |
| Jerry Vaske | $8,295.00 |
| Maureen Donnelly | $6,978.00 |
| Fringe (20.1%) | $3,069.87 |
| Graduate student salary: | $4,720.00 |
| Fringe (3.9%) | $174.64 |
| Salary subtotal | $23,237.51 |
| Mail survey |  |
| Purchase general public sample | $187.00 |
| Printing | $1,880.00 |
| Postage |  |
| Outgoing | $3,525.00 |
| Incoming | $2,425.00 |
| Postcard reminder (Printing & postage) | $788.00 |
| Telephone non-response check | $2,000.00 |
| Total direct | $34,042.51 |
| Indirect (17.5%) | $5,957.44 |
| Total (direct + indirect) | $39,999.95 |