4435.01 REV-1

___________________________________________________________________________

CHAPTER 2

CONSTRUCTION STAGE FOR INSURANCE UPON COMPLETION PROJECTS

2-1.   BASIC REQUIREMENTS for insurance upon completion projects

during the construction stage are generally the same as for

projects with insured advances.  However, because HUD does

not insure advances for the construction loan, HUD does not

monitor the mortgagee's disbursements.  Additionally,

because HUD has no risk exposure until final closing, HUD

does not become involved in the workout of problems per

Chapter 4.  Following are major variations during the

construction stage for insurance upon completion projects

from projects with insured advances.

2-2.   FIRM COMMITMENT TO INSURE UPON COMPLETION, Forms FHA-2453,

FHA-2453-MM (Section 207 pursuant to Section 223(f)) and

FHA-2453-NH (Section 232), must be valid and outstanding

until project closing, i.e., endorsement of the permanent

mortgage.

A.  No Initial Closing.  The construction stage starts with

the issuance of the Firm Commitment.  HUD does not

insure advances from the construction loan for

insurance upon completion projects, therefore, there is

no initial closing.

B.  Construction/Rehabilitation Must Start within the

period provided by the firm commitment.

C.  Extensions.  See Handbook 4425.1 for the extension of:

1.  The period within which construction/rehabilitation

must start, and

2.  The firm commitment expiration date, where required

to permit project completion and final closing.

2-3.   REQUIRED DOCUMENTS include:

A.  Construction Contract.  The HUD Form of Construction

Contract need not be used, however, the following must

be made a part of the contract used:

1.  General Conditions, AIA Document A201,

2.  Supplementary General Conditions, Form HUD-2554,

3.  Davis-Bacon Wage Rates,

___________________________________________________________________________

2-1                                6/93

_____________________________________________________________________

4435.01 REV-1

___________________________________________________________________________

(2-3)      4.  Amendment To The Construction Contract To Identify

Identities Of Interest Between

Owner/Contractor/Subcontractors/Architect, Appendix

8, Handbook 4430.1 REV-1, and

5.  Cost certification criteria from Form HUD-92442-A,

Article 10, where an identity of interest exists,

or a "cost plus" form of contract is used.

B.  A Complete Master Set of Drawings and Specifications

and two duplicate sets.

C.  The Agreement and Certification, Form HUD-3305A, or

HUD-3306A executed by the mortgagor, mortgagee, and

HUD.

D.  A Title Policy or title evidence showing:

1.  Insured property free of all encumbrances other

than said mortgage and acceptable reservations of

title.

2.  Proof that no unpaid obligations exist except as

previously approved by HUD.

3.  Title policy continued to date of credit instrument

endorsement.

E.  Survey and Surveyor's Certificate, Form HUD-92457.

F.  Contractor's Requisition Project Mortgages, Form

HUD-92448.  The Contractor's Prevailing Wage Certificate

must be submitted to HUD at the time the mortgage is

presented for insurance pursuant to a commitment to

insure upon completion.

G.  Assurance Of Funds To Meet Operating Deficit.  Complete

Forms FHA-2476, Agreement of Sponsors To Furnish

Additional Funds, FHA-2476-A, Escrow Agreement, and

FHA-2477, Bond Guaranteeing Sponsors, Performance, to

assure funds are available to carry the project to a

sustaining occupancy position after final closing.

H.  Assurance of Completion is not applicable to insurance

upon completion projects.

I.  Warranty Against Latent Defects, is required in

accordance with paragraph 2-21 below.

2-4.   THE PRECONSTRUCTION CONFERENCE must precede the initial

start of construction.  See paragraph 1-2.

___________________________________________________________________________

6/93                             2-2

_____________________________________________________________________

4435.01 REV-1

___________________________________________________________________________

2-5.  CONSTRUCTION MONITORING AND REPORTING must be performed in

accordance with paragraph 1-3 to assure that the completed

project provides an acceptable mortgage risk upon

endorsement of the permanent mortgage.

2-6.  LABOR AND FHEO LIAISON.  See paragraph 1-4.

2-7.  CONTRACTOR'S MONTHLY REQUISITIONS are not applicable for

projects insured upon completion.

2-8.  OFFSITE CONSTRUCTION.

A.   Monitoring is recorded by the construction

representative on Form HUD-5379.

B.   Advance Of Funds monitoring by HUD is not applicable

for insurance upon completion projects.

2-9.  CONSTRUCTION CONTRACT CHANGES AND ARCHITECT'S SUPPLEMENTAL

INSTRUCTION.  See paragraphs 1-8 and 1-9.  Construction

Changes, Form HUD-92437 (Change Orders) are processed the

same as in paragraph 1-8, except as modified below:

A.   An Escrow is not required for additive change orders,

because HUD has no risk exposure until final closing.

The mortgagor must be able to provide the additional

funds required and must not have any outstanding

obligation in connection with construction other than

the insured mortgage at the time the mortgage is

presented for insurance.

B.   Surety Approval is not required for the approval of

additive change orders regardless of the percentage of

contract increase.

2-10. PERMISSION TO OCCUPY applies as in paragraph 1-11.

2-11. FINAL HUD REPRESENTATIVE'S TRIP REPORT and items of delayed

completion apply as in paragraph 1-12.

2-12. GUARANTEE PERIOD applies as in paragraph 1-13.

2-13. APPLICATION FOR INSURED ADVANCES is not applicable for

projects insured upon completion.

2-14. WORKING CAPITAL DEPOSIT is not required for insurance upon

completion projects.

2-15. PROPERTY INSURANCE SCHEDULE AND REQUIREMENTS.  When on-site

construction is 80 percent complete, (before endorsement of

the credit instrument) HUD must prepare:

___________________________________________________________________________

2-3                                 6/93

_____________________________________________________________________

4435.01 REV-1

___________________________________________________________________________

(2-15)A.  Property Insurance Schedule, Form HUD-92329, that:

1.   Correctly shows the insurable value of the

completed structures.

2.   Reflects any changes in cost occurring after

issuance of firm commitment.

B.  Property Insurance Requirements, Form HUD-92447.

2-16. MIP is not charged until the project reaches final closing.

2-17. COST CERTIFICATION.  See Chapter 5.

2-18. CLOSING must occur within the period provided in the

commitment.

2-19. Extension of Firm Commitment instructions are in Handbook

4425.1.

2-20. BUILDER'S WARRANTY.  The general contractor must provide

one of the following at final closing to assure correction

of any latent defects.

A.  Cash Escrow Deposit of 2 1/2 percent of the principal

amount of the mortgage, to be retained in escrow by the

mortgagee for a period of 15 months, or

B.  Surety Bond in the amount of 10 percent of the cost of

construction or substantial rehabilitation (running for

2 years after substantial project completion).  The

bond must be on Form HUD 3259, Surety Bond Against

Defects Due To Defective Materials And/Or Faulty

Workmanship.

___________________________________________________________________________

6/93                              2-4