Computing and Physics PROJECT STATUS REPORT

REPORTING PERIOD

##### Q2 2003

January-March, 2003

1.	Project Manager’s Summary.  J. Shank (BU)	4

2.	WBS 2.1 Physics Manager’s Report (Ian Hinchliffe, LBNL)	6

3.	WBS 2.2  Software Manager’s Report (Srini Rajagopalan, BNL)	8

WBS 2.2.1: Core Services (D. Quarrie)	8

WBS 2.2.1.1: Framework	8

WBS 2.2.1.2: EDM Infrastructure	9

WBS 2.2.1.3: Detector Description Infrastructure	9

WBS 2.2.1.4: Graphics	10

WBS 2.2.1.5: Analysis Tools	10

WBS 2.2.1.6: Grid Integration	10

WBS 2.2.2, Databases and Data Management (D. Malon)	10

WBS 2.2.2.1  Database services and servers	10

WBS 2.2.2.2  Common data management software	10

WBS 2.2.2.3  Event store	10

WBS 2.2.2.4 Detector data management	11

WBS 2.2.2.5  Collections, catalogs, and metadata	11

WBS 2.2.3 Application Software (F. Luehring)	12

WBS 2.2.4 US ATLAS Software Support (A. Undrus)	12

WBS 2.2.4.2 Quality Assurance: (P. Nevski)	13

4.	WBS 2.3 US ATLAS Facility Manager’s Report (B. Gibbard, R. Baker, BNL)	14

WBS 2.3.1 Tier 1 Computing Facility at Brookhaven National Laboratory	14

WBS 2.3.1.1 Management and Administration	14

WBS 2.3.1.2 Tier 1 Fabric Infrastructure	14

WBS 2.3.1.3 Tier 1 Linux Systems	14

WBS 2.3.1.4 Tier 1 Storage Systems	15

WBS 2.3.1.5 Tier 1 Wide Area Services	15

WBS 2.3.1.6 Tier 1 Operations	15

Summary of Major Milestones and Deliverables	15

Forthcoming Milestones and Deliverables	16

WBS 2.3.2 Tier 2 Computing Facilities	16

WBS 2.3.3 Wide Area Network	16

WBS 2.3.4 Grid Tools and Services	16

Overview	16

Infrastructure	17

Packaging and Configuration	17

VO Management	18

Grid User Management System	18

VO Project with USCMS and iVDGL	18

WorldGrid Infrastructure	18

Distributed Developers Environment	19

Workflow Services	19

Chimera based workflow systems	19

Data Services	19

ATLAS Distributed Data Management – MAGDA	19

RLS Service	20

Monitoring	20

PPDG Monitoring Effort	20

iVDGL Monitoring Effort	21

Production Frameworks	21

ATLAS Simulation, Reconstruction Software and Run Scripts for Production	21

Production RLS	22

Chimera Simulation and Reconstruction Bundles	22

GRAT Integration	22

Analysis Applications, Interactive Grid Analysis, Portals	22

Grappa (Web Portal)	22

Ganga (Athena Grid Integration)	23

DIAL (Interactive Analysis Framework)	23

WBS 2.3.5 Grid Production	24

5.	Financial Report (Chuck Butehorn, BNL)	25

# Project Manager’s Summary.  J. Shank (BU)

A major reorganization of the US ATLAS Computing and Physics project took place during this quarter. This started after the Jan., 2003 DOE/NSF LHC Computing review at LBNL.  A new organization structure was formed as shown in figure 1.

Figure 1. The new US ATLAS Computing and Physics Organization Chart.

Major changes include: new roles for Shank/Huth. Shank is now the Executive Project Manager for Computing and Physics with responsibility for the day-to-day operations of the project. This includes allocation of project funds and planning for the project effort.

Huth retains his title of Associate Project Manager for Physics and Computing.  His new role deals with organization and issues which are larger than US ATLAS, such as the new ITR proposal DAWN, for which he is the PI.

S. Rajagopalan takes over as Software Manager from Torre Wenaus.

Under Facilities, we now include level 3 managers for Production (in charge of Data Challenge production) and Grid Tools and Services (GTS) for all grid related effort.

Though this new organizational structure has been in place for only a short time, we believe it is working well.

During this quarter, the new level 2 and 3 managers undertook a complete rewrite and scrubbing of the project WBS. The new WBS is reflected in this report. The scrubbing process allowed us to precisely define the project tasks, assign resources to carry out these tasks and o set priorities in case of funding shortfalls. We also took the opportunity to align the new WBS with the emerging new computing structure at CERN where Dario Barberis and  David Quarrie took over from Norman McCubbin.  A completely new ATLAS organization chart also went into effect during this quarter. This is shown in figure 2.

Figure 2. The new ATLAS Computing Organization Chart.

During this quarter the reconstruction jobs for Data Challenge 1 were started. This is being done on most of the facilities of the US testbed and will be completed in approximately 2 weeks, once the final version of the software is released (scheduled for  May, 2003). The data from this will be used for the soon to be completed High Level Trigger Technical Design Report  (HLT TDR, June, 2003).

Most of the software effort in this period went to adding features needed for the HLT TDR. This included Athena and Gaudi, the Event Data Model and Data Mangement software.  We also made major contributions to the LCG projects POOL and SEAL, which are crucial to our longer term ATLAS goal for Data Challenge 2 in 2004.

Under facilities, the new organization with Production and GTS was developed and plans for using existing grid tools for the next phase of production (the reconstruction for the HLT TDR) were deployed.

# WBS 2.1 Physics Manager’s Report (Ian Hinchliffe, LBNL)

Most of the work in this quarter focused on ensuring that the

generator tools needed for the Atlas physics meeting in Athens in

May 2003 and the High Level Trigger TDR are in place.  Effort was

focused on the integration of Tauola and Photos as manpower finally

became available from the physics groups to validate the code that has

been available for some time. (WBS 2.1.1.10 and 2.1.1.11). This code

is expected to be fully validated for use with Pythia and Herwig for

release 6.0.3. Users have begun to exploit the ability to run external

specialized event generators such as Comphep (WBS 2.1.1.13).

Additional changes were made to GenzModule (WBS 2.1.1.18) to provide

improved access to the truth information for the Geant-3 simulation

(atlsim) needed for the reconstruction phase of DC1. A new package,

GenAnalysisTools (WBS 2.1.1.19), was implemented using code originally part of

Reconstruction. This package provides Ntuples containing Monte Carlo

Truth information and helper packages to handle the truth in a form

that shields the users from the different conventions of the

individual physics generators.

Documentation for all the packages was brought up to date for release

6.0.0 on the web (www-theory.lbl.gov/~ianh/monte/Generators).

The new Athena random number service (WBS 2.1.1.17) was fully deployed

in release 6.0.0. The specific state of any event generator can be

dumped and is done so automatically should a job crash. This service

should ultimately be used by all athena algorithms so that specific

events can be debugged on demand.

Work also began on porting the code to gcc3.2 and redhat 7.3

which will be used for

atlas release 7.0.0. This has necessitated many technical changes to

overcome the more strict standards that are enforced by this compiler

and the loader distributed with red hat 7.x. Work also started in

preparation for the replacement of the package Simulation/HepMC in the

atlas releases with the CLHEP version of this code. This is expected

to be completed as soon as the next version of CLHEP is made

available in atlas.

# WBS 2.2  Software Manager’s Report (Srini Rajagopalan, BNL)

The ATLAS Computing was reorganized during this quarter, with a new   Computing Coordinator (Dario Barberis), and Software Project Leader

(David Quarrie, LBNL). This reorganization has resulted in a new management structure, with the software being structured into the following groups:

o Core Services

o Infrastructure Support

o Simulation

o Event Selection, Reconstruction and Analysis Tools

o Detector Subsystems

This restructuring has been reflected in a new organization structure for US-ATLAS software development.

The activity during the first quarter was geared toward providing the necessary support for the reconstruction phase of Data Challenge 1 and the studies in support of the High Level Trigger (HLT) Technical Design Report (TDR). The reconstruction of the Data Challenge 1 is scheduled to begin in May 2003 using Release 6.0.x. The HLT TDR is due in July 2003.

## WBS 2.2.1: Core Services (D. Quarrie)

The breakdown under Core Services was reorganized as well and is consistent between ATLAS and US ATLAS structure. The primary focus of the US ATLAS effort remain in the Framework and Event Data Model.

### WBS 2.2.1.1: Framework

The main activities in this area were:

- A CLIDSvc service is available that provides centralized management of class-ids (the mechanism by which persistent objects are coupled with their transient representation). Currently this is operating in "spy" mode to detect conflicts, and will transition into full operation during the next reporting period (C. Tull).

- Development of the core component infrastructure for the SEAL LCG project. This includes plug-in management supporting dynamic loading and unloading of components (M. Marino).

- W. Widenmann (Wisconsin, ATLAS) provided a prototype of event level multi-threading for Athena/Gaudi. This has been productized and integrated into the code repository (P. Calafiura).

- Major re-write of GaudiPython. Changes introduced to convert the package to new version of Boost.Python 2.0. Added the capability of setting and getting properties of Algorithms and Services before they are created by the Application Manager. (W. Lavrijsen)

- New version of the Athena Reconstruction tutorial. Changes to the material to reflect the evolution of StoreGate API. New enhanced version of ASK, the Athena Software Kit (P. Calafiura, W. Lavrijsen, M. Marino)

- The Interval of Validity service (IOVSvc) has been integrated with the detector description of the Pixels inner detector and a testbed ASCII conversion service to demonstrate support for time-varying mis-alignments. (C. Leggett)

- An enhanced Message service (MessageSvc) has been provided that supports the use of color to highlight messages of different severity levels (debug, informational, warning, etc.) (C. Leggett)

- Preparation for porting of the ATLAS software to gcc 3.2 was begun. The focus for this will be release 6.1.0, scheduled for the beginning of May, but essentially groundwork has been put in place in order to accelerate the porting of higher level software such as reconstruction. This has involved changes to several of the core Gaudi/Athena packages (P. Calafiura, W. Lavrijsen, C. Leggett)

### WBS 2.2.1.2: EDM Infrastructure

- The StoreGate package has been reorganized into three collaborating packages in order to reduce couplings and dependencies and to improve the modularity. (P. Calafiura, S. Rajagopalan)

- The Proxy Provider Service has been deployed that handles the loading of data object addresses from persistency. The loading of addresses can be done at the beginning of the job, beginning of the event or on-demand. Note that the data object is itself loaded only on-demand from persistency using these addresses. This establishes a communication channel between client requests for data objects in transient memory and the persistency services. (P. Calafiura, S. Rajagopalan)

- A prototype pile-up framework has been developed based on the Liquid Argon detector. This supports optimized pile-up based on the detector characteristics, and can be used as the basis for the development of support for the other detector subsystems (P. Calafiura).

### WBS 2.2.1.3: Detector Description Infrastructure

- A major emphasis has been to establish a common materials definition that can be used by all detector subsystems. This is now in place, although a few additional material definitions are required. The ability to generate a Geant4 geometry from a GeoModel geometry has been demonstrated, although there are some optimization issues that need to be resolved. Integration with the NOVA service for primary numbers has begun. (J. Boudreau, D. Costanzo).

### WBS 2.2.1.4: Graphics

There was no development in this area from US-ATLAS in this quarter.

### WBS 2.2.1.5: Analysis Tools

There was no development in this area from US-ATLAS in this quarter.

### WBS 2.2.1.6: Grid Integration

## WBS 2.2.2, Databases and Data Management (D. Malon)

### WBS 2.2.2.1  Database services and servers

(Vaniachine)

MySQL server support, cleanup and archiving of data in legacy Objectivity/DB databases, external package support for both ATLAS and LCG, and updating of server-side software were all part of U.S. database service/server support in this reporting quarter.

New developments included a web interface for access to conditions data, and database replication infrastructure for the tag database (the latter jointly with Grenoble).

### WBS 2.2.2.2  Common data management software

(Fine, Adams, Perevoztchikov)

While continued support of the AthenaRoot conversion service required some effort in this reporting quarter, U.S. development efforts in this WBS area have been aimed primarily at delivery of a prototype conversion service based upon the LHC-wide LCG POOL persistence software currently under development.  Design has been completed, and a limited implementation was delivered to specialists.  A prototype will not be delivered for general use by software developers until the coming quarter (ATLAS Release 6.3.0), when insufficiencies in the underlying software upon which this work depends (particularly the dictionary coming from the LCG SEAL project) and non-database LCG/Athena (and cmt/scram) integration issues have been resolved.

### WBS 2.2.2.3  Event store

(Adams)

A plan for integration of dataset and POOL event collections was developed.  Work in this area is targeted primarily for the second half of this year in preparation for Data Challenge 2, after POOL-based common data management software (WBS 2.2.2.2) becomes available, and the underlying components (POOL and SEAL in particular) are more functional and more stable.

### WBS 2.2.2.4 Detector data management

(Vaniachine, Eckmann)

The Nova database was extended to support several additional kinds of data, including liquid argonne calorimeter sagging parameters, new tile calorimeter primary numbers, and test beam simulations.  The database was reorganized to support hierarchical organization of digitization parameters for the muon system.

Several enhancements were made to support access to data in Nova mediated by an interval-of-validity database service under development at Orsay.

At the request of the detector description group, work was begun on support for a materials service.

An automatic converter generation mechanism was delivered; it will be integrated into nightly builds in the coming quarter.

### WBS 2.2.2.5  Collections, catalogs, and metadata

(Eckmann)

A prototype relational database implementation of explicit collections

(roughly, event lists with associated "tag" data) was delivered as a U.S. ATLAS contribution to the LCG POOL project.  Interfaces and infrastructure in support of typesafe collections was also delivered; implementation will be handled by CERN-based POOL project members.

Kristo Karr will replace Steve Eckmann in the coming reporting quarter in this WBS reporting area.

----------------------------------------------------------------------

Status of database milestones mentioned in the previous quarterly

report:

- Athena conversion service prototype based upon POOL Release 0.3.0 (February 2003);

  - Status: limited prototype, late along with all of ATLAS release 6.1.0 (mitigating factors:  introduction of new compiler (gcc3.2), problems in AtlasSEAL integration package on which this milestone depends)

  - New milestone:  prototype based upon POOL Release 1.0.0 in ATLAS Release 6.3.0 (June 2003);

- Extensions to NOVA to support interval-of-validity services (February 2003);

  - Status:  DONE

- Explicit collections instantiated in ROOT, and higher-level collection services 				              (March 2003);

  - Status: CERN-based effort has been identified to offload the ROOT implementations--no longer a U.S. responsibility (though overall coordination remains a U.S. job)

- ATLAS workshop on conditions and other time-varying data     (February 2003)

  - Status:  DONE

## WBS 2.2.3 Application Software (F. Luehring)

Geant3 Simulation Support: (P. Nevski)

The schema to simulate the complete pile-up in the ATLAS detector (including the cavern neutron background componen and minimum bias collisions in ± 750 ns gates) have been optimised. This allowed production to run on standard machines in a dual processor production mode.

The calorimeter pile-up code was instrumented to control the quality of event mixing and the calorimeter digitization on demand.

Two new event generators have been interfaced to ATLSIM and the relevant geometry elements added to DICE. The cosmic muons generators integrated in the ATLAS environment will provide muon fluxes in the experimental cavern. The interface to the machine background calculations using MARS codes will alow to estimate the rates of halo particles and beam-gas collision in the ATLAS cavern.

## WBS 2.2.4 US ATLAS Software Support (A. Undrus)

- Maintenance of the ATLAS nightly build system:

The ATLAS nightly build facilities at CERN and BNL were monitored and improved. The special branch of nightly builds with new compiler gcc-3.2 was started at CERN. As a result ATLAS software developers got immediate feedback on compliance of their new submissions with new compiler standards.

- Participation in the ATLAS Software Infrastructure Team:

U.S. Atlas Software Librarian (A. Undrus, BNL) actively worked in ATLAS software infrastructure and testing (SIT) team on software release management, quality assurance and testing. He proposed to create a document on ATLAS software testing standards and methods and will provide a prototype for the SIT testing meeting scheduled in April 2003.

- Deployment of the nightly control system tools used by LCG:

The nightly control system tool, NICOS, was developed based on the experience and software created for ATLAS nightly builds. This flexible tool for coordination of software development manages the multi-platform nightly builds based on the recent versions of software packages, tests newly built software, identifies possible problems and make results immediately available to developers spread over different institutions and countries. The NICOS tool was accepted for use by SPI group of LHC Computing Grid (LCG) Project at CERN. The experimental NICOS builds of LCG software are started. The talk about NICOS was presented at CHEP 2003, San Diego, CA.

- Deployment of LCG related software at the Tier 1 facility:

The work on integrating POOL (the persistency framework being developed by the LCG) into Athena (the ATLAS offline software framework) has started. In the first quarter POOL was installed at BNL and the bridge package, AtlasPOOL, that provides the access to POOL in the ATLAS software release was developed.

- Tests of ATLAS software using Redhat 7.3 in preparation for upgrade:

In cooperation with ACF staff, the upgrade of operating system to Red Hat 7.3 in the Tier I Linux Farm nodes has been scheduled for April, 2003. In preparation, a single node on the farm was upgraded to the new OS where the ATLAS software was successfully built and tested. This upgrade is performed in synchronization with the analogous upgrade at CERN with the purpose of creating identical working environment on Atlas computer farms.

- Deployment of new ATLAS software at BNL:

New ATLAS software continues to be promptly installed at the BNL Tier I Center, usually in one to three days after the corresponding CERN installation (typically once every three weeks). The BNL software support page is updated in a timely way.

- Maintenance of the US ATLAS MySQL web server:

The U.S. Atlas MySQL database, web server, and cvs pserver were maintained and administered. The U.S. Atlas community actively used these services.

### WBS 2.2.4.2 Quality Assurance: (P. Nevski)

A procedure for verification of the reconstruction results used for the ATRECON has been modified for the reconstruction running in ATHENA. A number of limitations implied by the ouput event size have been removed. This procedure will be later used for the DC1 reconstruction validation.

# WBS 2.3 US ATLAS Facility Manager’s Report (B. Gibbard, R. Baker, BNL)

During the second quarter of FY ’03, the Facility project under WBS 2.3 was reorganized to reflect the increasing importance of both Grid projects and Production activities.  Most of the work that was previously included under the “Distributed IT Infrastructure” WBS item 2.3.2 has been moved into the new level 3 area 2.3.4, Grid Tools and Services.  An entirely new level 3 WBS item, 2.3.5, US ATLAS Production, has been created to focus on the very significant effort required to prepare and execute ATLAS Data Challenges in addition to configuring and running the production Grid infrastructure for US ATLAS.

## WBS 2.3.1 Tier 1 Computing Facility at Brookhaven National Laboratory

This report reflects a modified WBS breakdown for the Tier 1 facility based on functional areas (CPU, Storage, etc.) which more clearly reflect the way work is organized and managed.  During the first quarter of FY ’03, Tier 1 facility staffing was maintained at the level of 4.5 FTE on project.  An additional 0.5 FTE for ATLAS Grid support funded via PPDG which was previously accounted for under the Tier 1 WBS item has been shifted to WBS 2.3.4.

The focus of Tier 1 activity during the second quarter was the successful execution of Data Challenge 1 Phase 2 and preparation for the subsequent reconstruction and analysis phase scheduled for the third quarter.

### WBS 2.3.1.1 Management and Administration

This new level 4 WBS item includes management and support of the facility staff, Global planning and reporting and liaison between the Tier 1 facility and external groups.  In previous reports, most of this effort was reported under WBS item 2.3.1.3, Facility Administration and Support.

In addition to the day-to-day oversight of the Tier 1 facility, the reorganization of WBS area 2.3 was a significant task during the second quarter.

The level of effort directed to WBS 2.3.1.1 during this quarter was constant at 1.4 FTE.

### WBS 2.3.1.2 Tier 1 Fabric Infrastructure

This new level 4 WBS item includes both physical infrastructure (power, A/C) and the basic elements of the local computing infrastructure including security, local area network components and backup systems.

The level of effort for WBS 2.3.1.2 continued at a constant 0.7 FTE during the quarter.

### WBS 2.3.1.3 Tier 1 Linux Systems

This new level 4 WBS item consolidates all of the items related to Linux Systems that were previously split between separate level 4 entries for hardware and software.

The Tier 1 Linux Farm was used heavily during the quarter for ATLAS Data Challenge activities, and most of the effort in this WBS area was dedicated to maintaining and optimizing the environment (particularly batch queues) needed to support this effort.  A significant upgrade of the operating system and compiler was also completed during the quarter.

.

The level of effort for WBS 2.3.1.3 was at the planned 0.3 FTE during the quarter.

### WBS 2.3.1.4 Tier 1 Storage Systems

This new level 4 WBS item consolidates all of the items related to disk and tape storage that were previously split between separate level 4 entries for hardware and software.

During the quarter, both the disk and tape storage systems were heavily used to handle the large volume of data produced by ATLAS Data Challenge 1, Phase 2.  The storage systems performed extremely well and were a key factor in the success of the Data Challenge.

The level of effort for WBS 2.3.1.3 was 0.5 FTE

### WBS 2.3.1.5 Tier 1 Wide Area Services

This new level 4 WBS item includes Wide Area Network support and Grid Middleware deployment and support.

The major effort in this area during the quarter was to support Phase 1 of the Data Challenge, which relied heavily on Grid protocols and services.

The level of effort for WBS 2.3.1.5 was 1.0 FTE

### WBS 2.3.1.6 Tier 1 Operations

This new level 4 WBS item focuses primarily on Facility support and monitoring.

The level of effort for WBS 2.3.1.6 was 0.6 FTE

## Summary of Major Milestones and Deliverables

During the quarter, the Tier 1 facility contributed significantly to the execution of ATLAS Data Challenge 1 which is an important project milestone.

There were no significant facility-specific milestones scheduled or completed during the quarter.

## Forthcoming Milestones and Deliverables

During the quarter, work was started on deployment of the LCG pilot release in preparation for full LCG pilot operation in the third and fourth quarters.

The next major facility hardware upgrade is planned for FY ’04 in preparation for ATLAS DC 2.  Pre-production for DC 2 is expected to begin in the second quarter of FY’04.

### WBS 2.3.2 Tier 2 Computing Facilities

### WBS 2.3.3 Wide Area Network

### WBS 2.3.4 Grid Tools and Services

# Overview

This quarterly report covers the period January 1-March 31, 2003.   During this time the US ATLAS Software and Computing project was reorganized, with Grid Tools and Services (WBS 2.3.4) becoming a new area in the Facilities subproject.  GTS is responsible for development, evaluation, and creation of integrated grid-based systems for distributed production processing and user analysis within the US ATLAS software and computing project.   The initial organization of the project is given in the table below.   Work has begun to develop a WBS dictionary, schedule, milestones, and resource assignments.

| WBS Number 2.3.4.x (level 4) | Name | Technology Areas |
| --- | --- | --- |
| 1 | Infrastructure | Packaging, configuration, testing and certification harnesses, security, VO management, distributed systems developer environment (grid component libraries, hosting environment, R&D testbed). |
| 2 | Workflow Services | Execution and data placement; planners, resource brokers, scheduling systems, resource prediction; computing model and architecture. |
| 3 | Data Services | Replica location services, virtual data and provenance, metadata management services, knowledge management frameworks. |
| 4 | Monitoring Services | Directories for resource discovery (MDS, grid service registries), resource monitoring (status level, historical), performance, accounting, and archival systems. |
| 5 | Production Frameworks | Production frameworks for data challenges; ATLAS software packaging and run time environments. |
| 6 | Analysis Applications | Distributed interactive analysis, grid user interfaces and portals, advanced workspace environments and venues. |

# Infrastructure

Development of the necessary infrastructure for middleware services, as related to US ATLAS, is covered in this work area.  Below we describe activities and progress during the work period.

## Packaging and Configuration

Work continued on development of the Pacman packaging and configuration tool developed by US ATLAS.  This work is being performed by Saul Youssef of Boston University, as part of the iVDGL project.   The project homepage is at http://physics.bu.edu/~youssef/pacman.  Development included:

- Improved support for Pacman software updates

- New caches: University of Chicago (UCHEP) for ATLAS software releases and the University of Southern California Information Sciences Institute (ISI) to support RLS (Replica Location Service).

- Participation in metapackaging discussion forums.

Under the auspices of the HIJTB, which is the intergrid joint technical board co-chaired by Ruth Pordes (Fermilab, PPDG Coordinator) and Ian Bird (LCG Grid Deployment Manager) a group was formed to address packaging, installation, and configuration of grid middleware.  A document was produced which was addressed to grid middleware developers and distributors such as the NSF Middleware Initiative (NMI), the Virtual Data Toolkit group of GriPhyN and iVDGL (VDT), the European DataGrid project (EDG), the LCG certification group, and to organizational entities HICB (HENP Intergrid Collaboration Board) and the LCG Grid Deployment Board (GDB).   A collaborative effort between LCG, EDG, and iVDGL has been organized (GLUE Metapackaging Group) to address development and future directions.

A number of recommendations have been made for software developers, metapacking developers, and site administrators.  Consideration has been given to supporting LCG installations for various types of sites: large farms, medium-sized clusters, and desktops or mini-clusters, and for manual and automatic installations.  Keeping in mind that to establish a uniform service, the functionality of the resulting setup must be the same regardless of the site.

The group is collaborating closely with the core technology groups (Globus, Condor) and the NSF NMI project which provides distributions in RPM format, ideal for LCG installations, or EDG installations which use LCFG.

## VO Management

### Grid User Management System

This effort is led by Dantong Yu of Brookhaven National Laboratory.

We developed the Grid User Management System (GUMS). The particular  problem that we intend to address is the need for strong pre-registration  of users, and we believe that this builds nicely on the existing  grid VO management software. Our focus has been on developing a  user account management system and tools to allow sites to keep  track of users.  We intend all of these developments to be compatible  with whatever VO management tools are adopted for LCG. GUMS downloads  certificates from VO server, then stores the certificates in the  local MYSQL database. The local account manager maps the newly discovered Distinguish Name to a grid account and groups based on  local policy. The mapping information will be stored in MYSQL database  also. A simple Python script scans the MYSQL database and creates the gridmap file. The software package can be obtained from Web site: http://www.atlasgrid.bnl.gov/testbed/gums. The presentation is  available at http://chep03.ucsd.edu/files/363.ppt. The paper is in the writing processing. It will be published in CHEP03.

### VO Project with USCMS and iVDGL

During this period US ATLAS has joined a new project with iVDGL and USCMS to develop VO management solutions appropriate to large sites such as Brookhaven National Laboratory and university Tier 2 and Tier 3 centers.

## WorldGrid Infrastructure

This effort is being led by Professor Saul Youssef of Boston University.

WorldGrid is an iVDGL project and includes participation from US ATLAS, US CMS, LIGO, and the Sloan Digital Sky Survey project.  The WorldGrid project is aimed to develop software to provide simple, complete grid solution for sites wishing to participate in various grid computing projects.  The focus for SC2002 was ease of installation, interoperability with EDG software, and controlled use of shared resources.

During this work period the WorldGrid team redesigned the Pacman cache structure, removing EDG components and ScienceGrid applications.   Designs for a new WorldGrid application which facilitates site management and the packaging and distribution of applications into “projects” were started.  A joint iVDGL and DataTAG talk on WorldGrid was given at CHEP:

http://chep03.ucsd.edu/files/199.ppt.

The WorldGrid package has been installed and is being used on the Tier 1 facility at Brookhaven, and at both US ATLAS prototype Tier 2 centers at Indiana University and Boston University, and a number of other US ATLAS Testbed sites.

## Distributed Developers Environment

In order to facilitate integration of components from many different software packages, a new Pacman cache containing “templates” required for interfaces and adapters was created.  This library is called “Grid Component Library”, or GCL, and adapters to components are being placed there for Chimera development.   Available packages and documentation for the library is available at:  http://grid.uchicago.edu/gcl.

# Workflow Services

## Chimera based workflow systems

As a part of US ATLAS collaboration with the GriPhyN project, we have been developing workflow systems based on the Chimera/Pegasus virtual data system.  The effort comes from Dan Engh and Yuri Smirnov of the University of Chicago, and Edward May and Jerry Gieraltowski of Argonne National Laboratory.  During the work period, the following were accomplished:

- ATLSIM scripts reconfigured into suitable format for grid-based execution

- ATLSIM transformations defined in VDL (Virtual Data Language)

- An RLS service provided by Argonne was evaluated

- Script to generate “abstract” DAG (directed acyclic graph) for Condor execution written

- Script to create and update a virtual data catalog written and tested

- Script to create “concrete” DAG corresponding to DC1 partition (file) creation

- Script to execute dataset creation on a number of US ATLAS testbed sites

- Configuration software written to allow use of opportunistic use of shared resources – the case tested was the new Jazz cluster at Argonne National Laboratory

- Utility scripts to list, cleanup, monitor the RLS service

Results from the development effort were presented at the March ATLAS software workshop.  The ATLAS Chimera project homepage provides more detailed information: http://grid.uchicago.edu/atlaschimera.

# Data Services

This work are contains development efforts for replicas, distributed replica environments, metadata and advanced metadata management systems and interfaces.

## ATLAS Distributed Data Management – MAGDA

The MAGDA effort is led by Wensheng Deng of Brookhaven National Laboratory.

MAGDA has been adopted by the International ATLAS Collaboration as the primary metadata and replication service for ATLAS (data challenges and user interface).  The system is based on an SQL (MySQL) database at the core of the system.  DB interactions occur via perl, C++, java and cgi (perl) scripts.  A web interface for browsing files resulting from the current data challenge for the high level trigger has been implemented, along with command line tools (magda_findfile, magda_getfile, magda_putfile, and magda_validate).

For the current high level trigger data challenge for international ATLAS, data are cataloged from the entire US ATLAS Grid Testbed, Alberta, CERN, Lyon, INFN (CNAF, Milan), FZK, IFIC, NorduGrid, and RAL, and made available to the Collaboration.   So far, 264k files have been cataloged, representing 65.5 TB of data.  The system has now been tested for scalability up to 1.5M files.

MAGDA has now been in stable operation since May 2001.  It is now being employed by the Phoenix experiment at RHIC and is being evaluated by other collaborations.

Current and near term work includes an implementation of Magda as an option for a catalog back-end to the LCG POOL persistency framework.  It is being tested by the EDG testbed.  Further details can be found in a talk presented by Dr. Deng at the CHEP2003 conference:

http://www.atlasgrid.bnl.gov/magdadoc/magda_chep2003.ppt.

## RLS Service

In support of Chimera development, and for evaluation of EDG and LCG software environments, two new RLS instances were created – one at Chicago by Ed May, the other at BNL by Jason Smith.  They are currently under evaluation and being used in support of production framework development for Chimera, which at the moment requires it.

# Monitoring

Two major monitoring development efforts are underway in US ATLAS.   Both use the popular Ganglia monitoring package developed at UC Berkeley to provide the basic resource monitoring infrastructure for cluster resources.  The first effort, working under the auspices of PPDG, focuses on publication of resource availability and load using MDS (the Globus Metacomputing Directory Service) and the GLUE Schema.   The second, working in collaboration with GriPhyN and iVDGL,  focuses on “Grid Level” monitoring for research into policy-driven scheduling and usage.

## PPDG Monitoring Effort

This PPDG related effort is being led by Dantong Yu of Brookhaven National Laboratory.   In the last quarter, there was work to integrate Ganglia  with the Globus Monitoring and Discovery Service. Here, we implemented the Ganglia information provider which publishes the data from the collector daemon  of Ganglia (gmetad) into MDS. The existing Ganglia information provider  only works with individual daemons and it does not support hierarchical  monitoring while ours does. The front-end of our information provider  uses GLUE schema (http://www.cnaf.Infn.It/~sergio/datatag/glue/), and  its back-end uses XML.

The work will be published by CHEP03: “GridMonitoring: Integration of Large Scale Facility Monitoring  with Meta Data Service in Grid Environment”.  This abstract and full version of paper  describe a Grid Monitoring  Architecture that captures and makes available the most important  information from a large computing facility. The presentation can be downloaded at: http://chep03.ucsd.edu/files/321.ppt.

## iVDGL Monitoring Effort

In addition to the above work, development continued on the VO-Ganglia software demonstrated at Super Computing 2002 in Baltimore.   This work complements the PPDG monitoring work by focusing on collecting information required for policy-driven scheduling.  The project is being developed by Catalin Dumatrescu (University of Chicago, GriPhyN) with supervision from Rob Gardner (University of Chicago) and Mike Wilde (Argonne).  The goals of the project are to develop systems to monitor grid-level resource activity, utilization, and performance; to provide VO-level resource activity and resource utilization monitoring; to create customized views of monitoring data include those target for hardware resources (clusters, sites, grids) and VO usage: jobs and workflow types.  Extended requirements and goals of the project are to provide a policy-driven steering mechanism for grid-resource scheduling.   The design goals are to provide for scalability over large number of resources and networks, and to be fault-tolerant.

# Production Frameworks

Production frameworks are required to support ATLAS data challenges.  During the work period development for DC1 pileup simulation was pursued with the GRAT toolkit.   In parallel, development began using the Chimera (GriPhyN) libraries.

A simple production framework based on the Chimera workflow system was developed.  The framework is useful for small scale datasets (requiring submissions for input ranges of partitions which can be done by hand with limited user intervention and monitoring.  The system was used by Dan Engh and Ed May to produce a 10,000 event data sample for the SUSY group.  The work was done in close collaboration with ATLAS physicists at Chicago (Ambreesh Gupta and Jim Pilcher) and with Ian Hinchliffe of LBNL.

## ATLAS Simulation, Reconstruction Software and Run Scripts for Production

During the work period we began a new approach to Pacmanizing and distributing ATLAS releases for grid-based production, taking advantage of release preparation by our ATLAS colleagues working on the Nordugrid project.

Yuri Smirnov of the University of Chicago has sucessfully Pacmanized and tested several ATLAS releases based on Nordugrid rpms starting with release 5.3.0.   He recently completed 6.0.2, which has been tested by Yuri Fisyak at Brookhaven and by Ed May, as well as by Yuri himself at LBL. The package consists of the release itself, plus a test package which comes with a sample input Zebra data file consisting of 5 events to be reconstucted for testing. These are available in the UCHEP Pacman cache, with instructions given at:  http://grid.uchicago.edu/Atlas-nordugrid/.

It its currently being installed into official US ATLAS testbed installation areas.  Fred Luehring at IU has installed and tested this at the IU Tier 2 center.

Future US ATLAS software packaging activities will use common packaging, installation, and configuration adopted by international ATLAS.  At present, no single, official solution exists.  A new working group is being formed to address a CMT to Pacman packaging solution.

## Production RLS

As discussed earlier, an RLS (a local replica catalog and replica location index server) is required by the curent release of Chimera.  Ed May has installed, configured, and tested an RLS instance on grid02.uchicago.edu which uses a MySQL database as a backend.  The RLS is being used in an auxillary fashion: LFNs (logical file names) in the abstract DAGs are mapped to PFNs (physical file names).  The RLS installation method has been Pacmanized by iVDGL, and the BNL team of Jason Smith and Dantong Yu installed a second RLS service there.

## Chimera Simulation and Reconstruction Bundles

Based on early work of Dan Engh, Jerry Gieraltowski of Argonne has created a set of Pacman packages which create the appropriate submission environment for Chimera for simulation and reconstruction production.  These packages are being deposited for general use ATLAS users with complete instructions in the Grid Component Library cache (GCL): http://grid.uchicago.edu/gcl/.

## GRAT Integration

Future work on production frameworks will integrate with components from the GRAT toolkit which have been developed for DC1 production.  The initial plan is to:

- Create an input staging system which reserves LFNs from available DC1 partitions to be reconstructed; this will use the production database, MAGDA,  GRAT modules, and RLS.

- A system to direct Chimera and Pegasus workflow, which automates preparation of the Condor DAGs.

- A submission layer to US ATLAS grid resources

- A validation and monitoring system

# Analysis Applications, Interactive Grid Analysis, Portals

In parallel with the production framework development, a number of grid user interface, interactive analysis, and grid portal frameworks are under development in US ATLAS.   To track developments in this field, US ATLAS continues to participate and lead development forums such as the PPDG CS-11 working group, http://www.ppdg.net/pa/ppdg-pa/idat/.  The goal of this group is “interfacing and integrating interactive data analysis tools with the Grid and identifying common components and services”.

Three ATLAS projects have been under development, each working on different aspects of the grid/user/application interface problem.

## Grappa (Web Portal)

The Grappa project is being developed by Dan Engh of the University of Chicago.   Two weeks of development time was given to the project during the work period.

Grappa was an early (web-based) grid portal designed to provide a simple point of grid access for Athena applications running on the grid.  The project originally was developed at Indiana University under the auspices of the GriPhyN project, and used significant leveraged resources in the form of a full-time CS developer (Shava Smallen) for one year, with extended support through SC2002.    The project utilized the Common Component Architecture notebook software developed by the computer science department at Indiana University.

Work during FY03 Q2 focused on a feasibility study to evaluate Grappa using the Jetspeed portal framework.   A new grid portal was built, providing basic job submission functionality for Athena ATLFAST simulations on the US ATLAS testbed, including:

- support for distributed grid proxies

- specification of input and output locations for grid-resident data

- input of Pythia and/or Isajet physics generation parameters

- selection of grid computational resources

- job execution monitoring using Globus protocols

- invocation and display of pre-sampled PAW histograms produced by Athena jobs executing on the grid

- recording of job “sessions” allowing archival of grid interactive sessions

The feasibility study using Jetspeed was performed for two reasons: before leaving IU, Smallen had completed a port of the underlying Grappa notebook component technology, and so many of the previous problems and shortcomings had been fixed;  second, Jetspeed, a web-based portal framework, has been receiving increasing attention in the grid user environment community and was selected as the base technology by the HEP collaborative tools ITR “GECR”.    A presentation describing the Grappa Jetspeed development was given at CHEP:

http://hep.uchicago.edu/chanl/grappa/grappa_chep03.html

## Ganga (Athena Grid Integration)

Ganga is a user interface for configuring applications that use the Gaudi/Athena software framework of ATLAS and LHCb, and for performing the tasks necessary to run jobs either locally or on the Grid.  It is being funded by the GridPP project in the UK.  In US ATLAS, Craig Tull of LBNL coordinates design and architecture, and specific Python interfaces to Athena.  The interface work is fully described in the Software WBS.   Future grid integration work and testing within US ATLAS grid development environments will be described in this WBS.  The details of the Ganga design and implementation, and report on the first use of Ganga to run ATLAS applications were given at a CHEP presentation: http://chep03.ucsd.edu/files/175.ppt

In contrast to Grappa, Ganga provides a rich, native interface to be integrated with the users desktop.

## DIAL (Interactive Analysis Framework)

DIAL (Distributed Interactive Analysis of Large datasets) is a project to investigate HEP distributed interactive analysis. It has three primary goals:

- Demonstrate the feasibility of distributed analysis of large datasets

- Set corresponding requirements for grid components and services

- Provide the ATLAS experiment with a useful distributed analysis environment

DIAL is being developed by David Adams of Brookhaven National Laboratory as a part of PPDG, to understand the requirements that interactive analysis places on the grid.   Within ATLAS the goal is to enable distributed interactive analysis of event data.   DIAL will enable users to analyze very large, event-based datasets using an application that is natural to the data format. Both the dataset and the processing may be distributed over a farm, a site (collection of farms) or a grid (collection of sites).  The system has been described in a CHEP paper:

http://www.usatlas.bnl.gov/~dladams/dial/talks/dial_chep2003.doc

### WBS 2.3.5 Grid Production

During Q2 of FY03, the U.S. ATLAS facilities played a major role in ATLAS Data Challenge (DC) production.  Large samples of events were processed through the entire event generation and pile-up chains using ATLSIM.  We also started testing ATHENA reconstruction production on small test samples.  During this reporting period, the U.S. continued to provide the largest grid-based production system in all of ATLAS, through participation in the U.S. ATLAS Grid Testbed.

The U.S. Testbed supports a diverse range of activities.  Many of the grid applications and tools developed in the U.S. (reported in W.B.S. 2.3.4) were tested and validated using the testbed.  The production team also wrote scripts to integrate and adapt some of these tools for large scale production.

Our first production target this quarter was to finish up generation of the 2500 minimum bias files using the LSF batch system at BNL.  Over 600GB of these files were produced.

Our second production target in Q2 was to re-generate 50k supersymmetry events using the grid testbed.  The sample consisted of 500 output zebra files and occupied ~200GB disk space.  400 files were done using the GRAT framework based on Globus middleware, and 100 files were generated using the Chimera framework.

A major task this quarter was to set up pile-up production.  During this process, the 2500 minimum bias files were mixed in randomly with all the GEANT simulation files generated in DC1 Phase 1.  We wrote a set of scripts, using the GRAT framework, to start this complex process on the grid.  All file transfers, including software, were done using grid based tools.

MAGDA was used to move and catalogue every file instance on the grid, including all input files.  Many new features were added to MAGDA as needed for our grid based production system.  A MySQL production database was developed to manage the production.  Automated scripts were developed for validation of the generated data.

First, low luminosity pile-up was done for ~500 input files.  Each grid site was pre-staged with 40 minimum bias files (~10GB), which were mixed in with up to 100 input files.  A new minimum bias set was pre-staged when necessary.  The system worked well.

Second, we started high luminosity pile-up, where 100 minimum bias files were mixed in with each input file.  Our primary target was to process the 2000 di-jet events for trigger studies.  This sample contained one million events with pT greater than 25 GeV.  Because of maximum file size limitations, each input file was split into 3 output files.

The high luminosity pile-up became a major 6 week long exercise on the grid.  We used five sites including BNL, LBNL, Boston U., Indiana U., and U.T. Arlington, each with large amounts of scratch disk space.  10TB disk was available at the BNL Tier 1 center for final file staging.  Over 5000 CPU days was used to produce this ~10TB sample, fully using Globus and MAGDA.

We learned about various bottle-necks and failure modes on the Grid.  Better data management tools are necessary to do future production at this or larger scale.  More automation of production is also needed.  The middleware needs to be more fault tolerant and fault resistant.

Simultaneously with pile-up production, the smaller sites like Oklahoma and SMU continued to produce simulation files.  Overall, this quarter was a great success in demonstrating the use of the grid for data production.

# Financial Report (Chuck Butehorn, BNL)

The total of funding for the U.S. ATLAS Computing Project is expected to reach $11,009,000 dollars during Fiscal Year 2003.  The Project is supported by DOE and NSF.

DOE program funding includes allocations from Fiscal Year 2000 through 2003, in the amount of $8,357,000.  The remaining Undistributed Budget of $1,422,000 will be allocated soon.

- The NSF total funding will reach 2,652,000.  As of the end of this quarter, $575,000 was pending allocation.

Appendix Table 1:  The details of the reported costs and reported obligations.

Appendix Table 2:  Summary of Agency funding Profile

Appendix Table 3:  Summary of Allocation of Funding to Institutions

| U.S. ATLAS Computing Program |
| --- |
| Summary of Funds Authorized |
| and |
| Total Costs and Commitments to Date |
| March 31, 2003 |
| (AY$ x 1,000) |
|  |  | Funds | Expenses + Commitments |  |  | Balance of |
| WBS No. | Description | Authorized Thru FY03 | Expenses to Date | Open Commit | Total to Date | Authorized Funds |
| 2.1 | Physics | 175 | 103 | - | 103 | 72 |
| 2.2 | Software Projects | 6,474 | 6,432 | 168 | 6,600 | (126) |
| 2.3 | Computing Facilities | 2,244 | 2,116 | - | 2,116 | 128 |
| 2.9 | Project Support * | 119 | 102 | - | 102 | 17 |
|  | Subtotal | 9,012 | 8,753 | 168 | 8,921 | 91 |
|  | Anticipated NSF Additional Funds | 575 | - | - | - | 575 |
|  | Anticipated DOE Additional Funds | 1,422 | - | - | - | 1,422 |
| 2 | U.S. ATLAS Computing Total AY$ | 11,009 | 8,753 | 168 | 8,921 | 2,088 |

Table 1: Reported costs and commitments

|  |  | Planned Funding (k$) |  |
| --- | --- | --- | --- |
|  | Agency | FY 00 | FY 01 | FY02 | FY03 | Total |  |
|  | DOE | 1,266 | 1,785 | 2,441 | 2,865 | 8,357 |  |
|  | NSF | 655 | 434 | 988 | 575 | 2,652 |  |
|  | Total | 1,921 | 2,219 | 3,429 | 3,440 | 11,009 |  |

Table 2: Summary Agency Funding Profile

Table 3  Summary of Allocation to Institutions.

# Footnotes

http://www.nsf-middleware.org/

http://www.lcfg.org/