4567.1

___________________________________________________________________________

CHAPTER 6.  PROJECTS WITH REPAIRS

6-1.  CRITICAL AND NONCRITICAL REPAIRS.  Critical repairs must be

completed, inspected and approved by the Field Office

before endorsement.  However, noncritical repairs may be

deferred until after endorsement in accordance with the

procedures in this chapter.  Noncritical repairs are those

that will not:

- endanger the safety and well-being of tenants, visitors

and passersby,

- adversely affect ingress or egress, or

- prevent the project from reaching sustaining occupancy.

6-2.  REPAIR ESCROW.  When repairs are proposed that will be

completed using mortgage proceeds after endorsement, a

repair escrow must be established similar to that used in

the Section 223(f) program.  Repairs must begin immediately

after endorsement and be completed within 12 months.

6-3.  ESCROW AGREEMENT (Form FHA-2476-A).

A.  The mortgagor must establish an escrow with the

mortgagee equal to at least 150 percent of the

estimated cost of the repairs to completed after

endorsement.  The escrow shall be funded as follows:

1.  Costs of the deferred repairs (including materials,

labor, permits, profits, etc., trended to the start

of repairs) must be estimated and withheld in cash

from mortgage proceeds and placed in escrow.  A

letter of credit may not be substituted for this

100 percent escrow.

2.  An additional cash amount (or letter of credit, at

option of the mortgagee) of not less than 50

percent of the repair cost estimate will also be

placed in escrow.

___________________________________________________________________________

6-1                              4/93

_____________________________________________________________________

4567.1

___________________________________________________________________________

(6-3)  B.  The mortgagee may release funds from the escrow as work

is completed, releasing funds first from the mortgage

proceeds portion of the escrow.

C.  Funds remaining in the escrow account, including the 50

percent portion provided by cash or letter of credit,

may be released when:  (1) all repairs have been

satisfactorily completed, (2) a supplemental cost

certification (see paragraph 6-5) has been approved by

the Field Office; and (3) latent defects assurances

have been provided (if required; see paragraph D.

below).

The supplemental cost certification must indicate that

there are no further amounts owed by the mortgagor in

connection with the repairs.  The updated title search

must indicate that no liens have been placed on the

project as a result of the repairs.

D.  Latent defects assurances are not required where the

repairs relate only to deferred maintenance items and

minor cosmetic repairs such as painting.  When repairs

and replacements are more significant, see latent

defects requirements in paragraph 6-4C below.

6-4.   COMPLETION OF DEFERRED REPAIRS.

A.  All deferred repairs must be completed by the mortgagor

within 12 months of endorsement (or such shorter period

as HUD and the mortgagee may specify).

B.  If the mortgagor has not completed all repairs by the

end of the repair period (including any extensions

approved by the Director of the Housing Development

Division), the mortgagee will complete the repairs

using the escrowed funds.  The mortgagee will provide

the mortgagor with a breakdown of these repairs and the

cost(s) of completion (including administrative

expenses).  The mortgagor will use this breakdown in

preparing the supplemental cost certification required

by paragraph 6-5 below.  Funds remaining in the escrow

account after completion and after the supplemental

cost certification has been approved by the Field

Office will be returned to the mortgagor less

reasonable administrative costs incurred in completing

the repairs.

___________________________________________________________________________

4/93                            6-2

_____________________________________________________________________

4567.1

___________________________________________________________________________

(6-4) C.  When required, assurance against latent defects for 1

year from completion of repairs must be provided by one

of the following:

1.  An escrow in cash, or letter of credit at the

option of the mortgagee, equal to 2-1/2 percent (or

greater percentage as warranted) of the repair cost

maintained for 15 months from completion of repairs

to cover situations where the defect is discovered

in the twelfth month and additional time is

necessary to correct it.

2.  A Surety Bond covered by Form FHA-3259 from a

surety on the accredited list of the U. S. Treasury

for at least 10 percent of the repair cost.  (The

Bond runs for a period of 2 years from the date of

completion of repairs.)

6-5.  REQUIREMENTS AFTER COMPLETION OF DEFERRED REPAIRS.

A.  The mortgagor must submit a supplemental cost

certification of the actual costs of the deferred

repairs.

B.  In cases where actual costs are less than estimated,

the maximum insurable loan amount must be recalculated.

If the maximum insurable mortgage is reduced due to

lower actual costs, the mortgagor must prepay the

mortgage in one of two ways:

1.  Remit the required prepayment, or

2.  Have the required prepayment amount deducted from

the balance of the repair escrow.

6-6.  INSPECTIONS.  Inspections for repair cases may be performed

by HUD Architectural and Engineering staff or under

contract.  Although the Technical Disciplines Contracts do

not specifically reference Section 223(a)(7), the Statement

of Work has procedures for "special inspections," including

Section 223(f) and guarantee inspections.  The procedures

are based on a single fixed price per inspection for all

such inspections.  Section 223(a)(7) repair inspections are

identical to those done under Section 223(f) projects or

for guarantee inspections.

___________________________________________________________________________

6-3                              4/93

_____________________________________________________________________

4567.1

___________________________________________________________________________

(6-6) A.  If repairs will be completed before endorsement, use

the instructions in Chapter 3 of Handbook 4565.1 for

inspections under the Section 223(f) program.

B.  When the Field Office has permitted the project owner

to defer noncritical repairs until after endorsement,

the owner will notify the Architectural, Engineering,

and Cost (A&E) Branch Chief when repairs are underway

in accordance with Firm Commitment requirements.  While

Section 223(a)(7) are likely to require only a final

inspection of the work, interim inspections may be made

where A&E finds such inspections warranted.

6-7.  COST CERTIFICATION.  Since the level of repairs is expected

to be limited, use the simplified cost certification

procedures for Section 223(f) in Handbook 4565.1 when the

transaction includes repair work.

___________________________________________________________________________

4/93                              6-4