Contract Number C1105050001

Order Number ______________

Page 1

1.         BACKGROUND

Featured in the park are petrified logs composed of multicolored quartz; shortgrass prairie; art of the Painted Desert; and archeological, paleontological, historic, and cultural resources.

2.	PURPOSE

The purpose of this contract is to provide production ready films and three porcelain wayside exhibit panels for Petrified Forest National Park, Petrified Forest, Arizona.

3.	SCOPE OF WORK

In accordance with the terms and conditions of the above-referenced contract, the Contractor shall provide the National Park Service with all labor, materials, equipment, facilities, and travel necessary to generate production ready films and produce three porcelain wayside exhibit panels with one duplicate of each as follows:

Exhibit Number and Title	Nominal Trim Size	Quantity

Ex 24, Welcome to Petrified Forest	36” x 48”	2

Ex 25, Blue Mesa Trail		36” x 24”	2

Ex 26, Whispers from the Past		36” x 24”	2

The Contractor shall provide the following to the Contracting Officer’s Representative (COR) for review and approval:

A.	An 11x17 color proof for each unique panel and porcelain color chips of background colors, halftone/duotone (other than black) colors and all spot colors;

- Exhibit panels; and

- Production ready films.

The Contractor shall refer to Attachment B for color specifications.

Contract Number C1105050001

Order Number ______________

Page 2

4.	TIME FOR COMPLETION

All work, including Review and Approval specified in Paragraph 5 below, shall be completed on or before July 12, 2007, in accordance with the following schedule:

DESCRIPTION					NOT LATER THAN

A.	Submission of color proofs and porcelain color chips	March 29, 2007

B.	Submission of the production schedule			 April 19, 2007

C.	Submission of the exhibit panels 		           		 June 7, 2007

D.	Completion of punch list deficiencies, return of all	June 28, 2007

Government-Furnished Property, submission of the

production ready films and final acceptance of the

work

5.	REVIEW AND APPROVAL

The COR will notify the Contractor, in writing, of approval or rejection of the work in accordance with the following schedule:

APPROVAL TIME

DESCRIPTION	(CALENDAR DAYS)

A.	Review and inspection of color proofs and				14 Days

porcelain color chips

B.	Review and inspection of the production schedule			7 Days

C.	Review and inspection of the exhibit panels  				14 Days

D.	Completion of punch list deficiencies, return of all			14 Days

Government-Furnished Property, submission of the

production ready” films and final acceptance of the

work

The COR will notify the Contractor, in writing, of approval or rejection citing any additions, corrections, or suggestions within 14 calendar days.  Any additions or corrections shall be completed and submitted to the government within 14 calendar days.  In the event the government delays comments beyond the period specified, the Contractor will be entitled to a day-to-day extension in the completion date.

Contract Number C1105050001

Order Number ______________

Page 3

6.	CONTRACTING OFFICER’S REPRESENTATIVE

The Contracting Officer’s Representative (COR) for the purpose of this contract is:

Susan Haines, Program Manager

National Park Service

Harpers Ferry Center

67 Mather Place, 3rd Floor

Harpers Ferry, West Virginia  25425-0050

Phone: (304) 535-6033

E-Mail: susan_haines@nps.gov

7.	POINT OF CONTACT FOR DELIVERY

Seven calendar days prior to delivery, the Contractor shall contact the COR and advise of exact dates and arrangements made for delivery.

8.	DESTINATION POINT

Upon completion of the work, the Contractor shall send the deliverables to the following destinations:

A.		The color proofs, porcelain color chips, production schedule and Government-Furnished Property shall be sent to the following address:

National Park Service

Harpers Ferry Center

67 Mather Place, 3rd Floor

Harpers Ferry, West Virginia  25425-0050

Attention:  Susan Haines, COR

Phone: (304) 535-6033

E-Mail: susan_haines@nps.gov

B.		The exhibit panels and production ready films shall be sent to the following address:

National Park Service

Harpers Ferry Center

Central Receiving

401 West Washington Street

Charles Town, West Virginia  25414

Attention: Susan Haines, COR

Phone: (304) 535-6033

E-Mail: susan_haines@nps.gov

Contract Number C1105050001

Order Number ______________

Page 4

9.	GOVERNMENT-FURNISHED PROPERTY

The Contractor shall be responsible for the security and protection of Government-Furnished Property (GFP) furnished to the Contractor in connection with this contract.  Following acceptance of all work by the government, the Contractor shall return, to the COR, all GFP not incorporated into the exhibit(s).

10.	ATTACHMENTS

The following items are incorporated into this contract as follows:

A.	One CD-Rom of Production Ready Digital Files, Dated January 11, 2007

B.	Scaled Layouts and Production Notes entitled, “Petrified Forest National Park,” consisting of 25 pages, Dated January 1, 2007

11.	PAYMENT SCHEDULE

Upon completion and acceptance of all work and receipt of a proper invoice, the Contractor will be paid a firm-fixed-price of $______________ in accordance with the following schedule:

A.		Upon inspection and acceptance of the color proofs and the porcelain color chips

$____ 10%______

B.		Upon inspection and acceptance of the exhibit panels

$	80%

C.		Upon completion and acceptance completion of punch list deficiencies, return of all			14 Days

GFP, submission of the production ready films and final acceptance of the work

$	10%

# Text boxes

P.O. Box 50

67 Mather Place

Harpers Ferry, WV

25425-0050

304-535-6033 Phone

304-535-6176 Fax

Petrified Forest National Park

National Park Service

U.S. Department of the Interior

Harpers Ferry Center

Petrified Forest, Arizona