Safety and Health Services Division

Self-Assessment Plan

FY 2005

Revision 1

Prepared by

R. Travis 	K. Krasner

Approved by 							Date:

P. Williams, Division Manager

1.0	Purpose/Scope:

This document presents the self-assessment program for the Safety and Health Services Division (SHSD).  This self-assessment plan addresses those elements of the Laboratory’s Critical Outcomes, Objectives, and Performance Measures for which SHSD has responsibility.   In addition, the plan addresses activities for monitoring organizational processes and providing information to the Division managers, and the Assistant Laboratory Director (ALD) for ESH&Q that is relevant to ensuring continuous improvement in the operation of the division and the projects and programs under its stewardship.  The approach of the self-assessment program includes both vertical and horizontal components:

- Vertical (within the scope of SHSD line responsibilities)

- Horizontal (across all BNL organizations with operations that have Safety Engineering, Industrial Hygiene or Safety Management Systems Integration aspects)

This plan meets the planning requirements associated with the Integrated Assessment Program (IAP) and considers each of the following BNL self-assessment framework criteria:

- Leadership Commitment and Involvement

- Human Resource Development and Management

- Customer Focus and Satisfaction (customer value)

- Process Management

- Business and Operational Results

6.   Compliance with Laws, Regulations and Contractual Requirements

Unforeseen events or issues that arise during the year may result in the need to perform additional focused assessment(s).  Performance of any unscheduled assessments will be acknowledged in the quarterly self-assessment reports and/or management briefings.

Specific objectives, strategies and indicators for each assessment criteria are presented in attachments I – VI, along with the responsible individual and schedule.  The relation of a strategy to BSA/BNL Critical Outcome Measures, Directorate Objectives or SHSD Strategic Initiatives is identified within the attachment tables.

2.0	Responsibilities

  - The Division Manager for SHSD has overall responsibility for ensuring that this Self-Assessment Plan is implemented and that resources are appropriate to conduct the delineated activities.  Specifically, these responsibilities are:

2.1.1	Ensuring that a self-assessment program exists, self-assessment plans are prepared, implemented and documented.

Ensuring that the R2A2s and individual performance goals of direct reports reflect expectations regarding self-assessment activities and are aligned with achieving organizational and institutional objectives and measures.

    - Ensuring assessments and corrective actions are tracked.

    - Planning and implementing assessments to ensure that the SHSD requirements and procedures (e.g. Subject Areas, ESH Standards etc.) are being implemented as expected, are achieving desired results, and are continually improved.

    - Reporting results, at regularly scheduled ESH&Q Management Team meetings, of self-assessment activities that may have Directorate level implications.

  - The SHSD Self-Assessment Coordinator is responsible for:

    - Developing the self-assessment plan by interacting with the applicable subject matter experts (SME) and program managers.

    - Tracking implementation of the plan by producing periodic (quarterly) self-assessment reports.

    - Presenting self- assessment plan updates quarterly at the periodic S&HSD Management Team staff meetings.

    - Maintaining this self-assessment program plan.

    - Keeping DOE-BHSO informed as to the status of the self-assessment activities.

2.3	Individuals responsible for coordinating or conducting the assessment activities (Such as Subject Matter Experts, Section/Program Managers, QA Representatives, etc.) have the following responsibilities:

    - Provide input to self-assessment planning.

    - Perform and document assessments in accordance with schedule.

    - Upon completing the assessment, entering status and assessment results/corrective actions into the Family Assessment Tracking System (FATS) or institutional level ATS (programmatic assessments).

    - Participate in assessments led by others, as appropriate.

    - Evaluate assessment results, recommend corrective actions and present the assessment results to the SHSD Management Team.

    - Forward documentation of self-assessment to the Self-Assessment Coordinator, or attach to FATS closeout.

    - Implementing corrective actions, as appropriate.

- Assessment Schedules, Tracking & Documentation

  - Most assessment activities are entered into the SHSD Family Activity Tracking System (FATS) to assign responsibility, schedule, track, and document closeout.  Actions not entered into the FATS for tracking may include routine activities where other means of documentation have been identified.

  - Individuals assigned to coordinate or conduct an assessment are responsible to complete the action in accordance with the schedule or obtain a supervisor’s approval to revise the due date.

  - Individuals are encouraged to utilize existing forms of documentation, such as routine reports, meeting minutes, etc. as validation of activity completion.  The specific means of documentation should be filed with assessment records or electronically attached through FATS.

- Review and Evaluation of Assessment Results

  - Individuals responsible for coordinating or conducting the assessment activities shall present the results and make recommendations to the SHSD Management Team, usually through the distribution of the Assessment Report or at the SHSD Management Team Meetings.  The management team shall review the information and recommendations and determine:

- Appropriate corrective and improvement actions.

- The need to submit identified strengths and issues in the Lab-wide Lessons Learned program.

- The need to report issues identified to the Laboratory Price Anderson Amendments Act Coordinator.

An assigned individual is then responsible for implementing the corrective actions.

4.2	Accomplishments against the objectives and measures of this plan are reviewed through development of a quarterly self-assessment report.  The report is developed by the self-assessment coordinator and electronically distributed to the SHSD Management team, the ALD for ESH&Q, and individuals responsible for coordinating assessments.

4.3	The results of the previous year’s assessments and annual evaluation serve as input for improvement actions and assessment activities for the subsequent year.

- Corrective Action Management

5.1	Corrective and improvement actions identified through assessment activities shall be managed in accordance with ESH Standard 1.2.1, Corrective Action Management and Tracking for Internal and External Assessments.

5.2	Corrective Actions associated with lab-wide programmatic assessments shall be entered and tracked in the Institutional level Assessment Tracking System (ATS).  Internal SHSD corrective actions should be tracked to closure through the Family Assessment Tracking System (FATS).

- Approval and Change Control

  - The SHSD Division Manager, following electronic review and comment by the SHSD management team and other individuals, as appropriate, formally approves this plan.

  - Revisions to the plan shall be identified through the Revision Number and date.

| SHSD Strategic Initiatives |
| --- |
| Initiative | Priority1 | Description/Objectives | Target(s) | Status |
| 1. Customer Satisfaction | 1 | Improve Customer Perception of SHSD Response to Their Needs This Initiative is in response to ESH&Q Draft IA&O Report SA 04-03 Recommendation: Managers of named organizations should ensure that solicitation of customer feedback is included among scheduled assessment activities in their SA Plans. | Develop SHSD Customer Service Action Plan P. Williams 9/30/05 |  |
| 2. Safety | 1 | Implementation & Sustaining Worker Safety Improvements: (Supports FY’04 Institutional Imperative #1) SHSD supplies the subject matter experts to develop and implement programs that are required to shape the culture of the BNL workforce that will lead to sustainable improvement in the safety culture and resulting indicators. | Deliver Laboratory Comprehensive Safety Plan to ESHQ ALD by 7/1/04 (S. Hoey – 7/1/04) Assure ALD finalizes the SIP (P. Williams – 4/11/05) | COMPLETED – Draft document sent to Jim Tarpinian 6/25/04. |
| 3 Cost Effective Safety and Health Services FATS 2511 | 2 | Integration of field Services: (Supports FY’04 Directorate Imperatives #1 & 3) As indicated in Directorate imperatives 1 and 3 the current business model for ESHQ does not adequately provide the necessary support of trained and qualified personnel to the field. Business models have built in a level of competition rather than cooperation. Multiple business models are confusing, redundant and perceived by the customer as an indicator of an unresponsive service provider. | Decision will be made by ESHQ&T Management Team at 3/11/05 meeting (J. Tarpinian, P. Williams, G. Goode, and C. Schaefer – 3/11/05) |  |
| 4. ESH&Q Integration FATS 2511 | 2 | Integrating ESH&Q into new scientific facilities/missions: (Supports Directorate Imperatives 1 and 3) The ESHQ organization needs to improve its integration of ESHQ requirements earlier into the design phase. This in the operational phase of the facility will reduce the number of incidents and occurrences and provide a more efficient facility. | SOP developed on SHSD support of design review J. Durnan 4/20/05 |  |
| 5. Maintain SHSD Core Competency | 1 | Maintain “core” competencies (Professional qualification/certification and field proficiency): (Supports Institutional Level Imperative #1) It is critical to the future success of the organization to maintain trained and certified subject matter experts. The entire SBMS system while migrating to a performance-based model is still very much an expert based model. Some level of expert based is required for it to function well. | See 2.A.3 | See 2.A.3 |
| 6. Provide ESH Data to the Lab | 1 | Data Delivery: (Supports FY’04 Directorate Imperative #2) Accurate and timely data is important to be able to track and trend incidents without this type of information the ability to identify deficiencies and implement improvements is ineffective. | See 3.A.4 | See 3.A.4 |

Attachment I

| ASSESSMENT CRITERIA: 1.0 Leadership Commitment and Involvement |
| --- |
| OBJECTIVES: A. To set direction and monitor an effective leadership system B. To effectively communicate information throughout the Division C. To maintain routine management field presence |
| Strategy | Priority 1 | Indicators (Measures/Assessments) | Responsibility | Schedule/Due Date | Status |
| 1.A.1. Establish FY’05 SHSD Priorities SHSD FATS: 2511. | 1 | Communicate FY2005 SHSD Priorities via SHSD Staff Meetings, Group Meetings and the ESHQ All Hands Meeting scheduled for early June. | P. Williams | SHSD All-hands Staff Meeting P. Williams – 6/7/05 | Rescheduled for July 13, 2005 |
| 1.B.1. Senior Staff Meetings, Section Staff Meetings, and Division Meetings SHSD FATS: 2511. | 2 | Meetings scheduled: Targets: Senior Staff Meetings – Biweekly Group Meetings – Bimonthly (Document in meeting minutes, agendas or personal logs.) | P. Williams, J. Ellerkamp, R. Selvey | (Not formally tracked) Conduct bi-weekly staff meetings |  |
| 1.C.1. Management Participation in Tier I Inspections SHSD FATS: 2511. | 2 | Perform periodic walkthroughs. Targets: IH Lab quarterly. Building 120 once per year. (Document in meeting minutes, agendas or personal logs.) | P. Williams, J. Ellerkamp, R. Selvey | Quarterly SAP Status Report |  |

Attachment II

| ASSESSMENT CRITERIA: 2.0 Human Resource Development and Management |
| --- |
| OBJECTIVES: A. To maintain an effective and empowered employee work staff B. To provide a safe and healthful workplace |
| Strategy | Priority 1 | Indicators (Measures/Assessments) | Responsibility | Schedule/Due Date | Status |
| 2.A.1. Performance Appraisals | 1 | Completed & conducted per BNL schedule. | Appropriate Managers (Reporting – S. Wiley) | Annual Per HR Directive |  |
| 2.A.2. R2A2 and Goal Planning | 1 | R2A2s revised as necessary & FY’05 goals developed/approved by scheduled BNL date. | All employees (Reporting – S. Wiley) | Annual Per HR Directive |  |
| 2.A.3. Provide professional development opportunities (Supports SHSD Strategic Initiative #5) | 1 | Target: Each employee has opportunity to attend one Professional Development Opportunity, if funding is available. | All employees (Reporting – S. Wiley) | Quarterly Status Report |  |
| 2.A.4. Succession Plan Maintained Current | 2 | Succession Plan revised as necessary. | P. Williams | Semi-annual (March/Sept) |  |
| 2.A.5. Employee Recognition | 2 | Awards & recognition received. | Appropriate Managers (Reporting – S. Wiley) | At the semi annual Directorate “All Hands” Meetings |  |
| 2.B.1. Target Safety & Health Measures (BSA/BNL Critical Outcome Measure 3.4) | 1 | Targets: 1. Days Away, Restricted, or Transferred Rate = 0.5 | All employees Reporting – ES&H Coordinator (K. Conkling) | Reporting of performance via Quarterly Status Report |  |
|  |  | 2. Total Recordable Case Rate = 1.10 |  |  |  |
| 2.B.2. Conduct Tier 1 Safety Surveys & Disposition actions. (See also 1.C.1) | 2 | 1. Tier 1’s performed as scheduled | K. Conkling | 9/30/05 |  |
|  |  | 2. Target: Disposition Tier I findings within 90 days |  |  |  |

Attachment III

| ASSESSMENT CRITERIA: 3.0 Customer Focus and Satisfaction |
| --- |
| OBJECTIVES: A. To provide high quality Safety Engineering, Industrial Hygiene and Safety Management Systems Integration services in support of BNL’s scientific mission. |
| Strategy | Priority 1 | Indicators (Measures/Assessments) | Responsibility | Schedule/Due Date | Status |
| 3.A.1 Manage Phase II and III of OHSAS-18001 Implementation | 1 | Targets Recertification of Pilot Group Onsite readiness review for Phase II Kick-off of Phase III | R. Selvey | June 2005 August 2005 August 2005 |  |
| 3.A.2 | 1 | See Initiative #1 |  |  |  |
| 3.A.3 Director’s Safety Committee Will Develop and Conduct a Review Process to Determine Improvements in the BNL Safety Programs Against the Comprehensive Safety Plan. Addresses 3.4.4.1, “Safety Implementation Path Forward” for which SHSD has the lead. Supports SHSD Strategic Initiative 2 (above). | 1 | Review the SHSD process to assess the current status of the BNL Safety Programs against the Comprehensive Safety Plan improvements that serve as the Appendix B measure. Need to address FATS 2308.4.1 from the FY’04 SAP which is open | P. Williams | 9/30/05 |  |
| 3.A.4 Continue roll-out of the Safety Information Data Base to; allow organizations to track and trend their data; ALD to perform periodic Status/Trending Presentations to the Management Council. | 1 | Develop procedure to document the flow of accident/injury data Development team is Ellerkamp, Erickson, Blydenburgh, and Piper. | Ellerkamp, Erickson | 4/4/05 | This is covered in the Injury Management Subject Area which is in the review cycle at the SBMS Office. |  |  |  |  |
|  | 1 | Accurate date supplied to ALD | Williams | Monthly |  |
| 3.A.5 Timely SHSD Design Review, ORE and BORE Support for Critical Projects (Supports Environmental Management Performance Measure 2.1.1, “Project Completions and Other Key Milestones” and EP measures 3.5.1 “Alternative Financing” and 3.5.2, “Project Management”.) SHSD FATS: 2511. | 2 | Conformance to SHSD Review Coordinator goals for Design Review turnaround and ORE/BORE/ERE draft report issuance for these high priority projects. | R. Travis/ J. Durnan | As required |  |
| 3.A.6 Optimize the Field Presence of Safety and Health Professionals (Supports: paragraph 6.4.2, “Safety and Health” of the Draft BNL Institutional Plan FY04 – 08”, dated 9/03 and Directorate Imperatives #1, #3)Health” of the Draft BNL Institutional Plan FY04 – 08”, dated 9/03 and Directorate Imperatives #1, #3) | 3 | Track FY’05 field presence for activities such as: Tier I support ORE/BORE/ERE SME special requests by Dept./Div. | J. Ellerkamp R. Selvey S. Hoey (Quarterly Reporting – S. Wiley) | Weekly activity reporting by Group Leaders |  |

Attachment IV

| ASSESSMENT CRITERIA: 4.0 Process Management |
| --- |
| OBJECTIVES: A. Refine BNL Management Systems that SHSD is responsible for. B. Develop/Refine SHSD Subject Areas |
| Strategy | Priority 1 | Indicators (Measures/Assessments) | Responsibility | Schedule/Due Date | Status |
| 4.A.1 Management System Maturity Determination – Hazardous Material Transportation Safety Supports Performance Measure 3.3.1, “ Management System Maturity Determinations” | 1 | Support formal consensus based user/peer review Maturity Determination of the Management System. Provide management analysis of the results. Document any necessary appropriate action plans for the management system. | S. Hoey | 9/30/05 |  |
| 4.B.1 SBMS Endstate for the Worker Safety and Health Management System |  | Draft Document transmitted to SBMS on schedule for the following: |  |  | Tracking to be accomplished as part of the SHSD SAP reporting |
|  | 1 | 1. Radiofrequency and Microwave Radiation SA (Legacy Document Conversion) | R. Selvey | 12/31/04 | Complete – 12/04 |
|  | 2 | 2. Investigation of Incidents, Accidents and Injuries SA (New Subject Area, requires electronic A/I form) | J. Ellerkamp | 4/1/05 | Complete Submitted to SBMS 2/10/05 |
|  | 1 | 3. Lifting Safety SA (Update per ISM and R Occurrence Report) | J. Ellerkamp | 5/22/05 | Adding fork lift requirements |
|  | 3 | 4. ODH Classification and Controls SA (Triennial Review) ODH and Cryogen safety SAs probably will be combined | J. Durnan | 6/30/05 |  |
|  | 3 | 5. Excavation Safety SA (Legacy Document Conversion) | K. Krasner | 12/31/04 | Complete – 12/04 |
|  | 3 | 6. Aviation Safety SA (Legacy Document Conversion) | D. Robbins | 2/28/05 | Complete – 2/28/05 |
|  | 3 | 7. Marine Safety/Diving SA (Legacy Document Conversion) | D. Robbins | 6/30/05 | Draft Submitted to SBMS 6/30/05 |
|  | 1 | 8. Electrical Safety and Design Criteria for Electrical Equipment SA (Legacy Document Conversion) | J. Durnan/J. Curtiss | 9/30/05 | Delayed until 9/30/05 due to attention required by sequence of OSHA, 70E, NRTL (listed/labeled) issue, updated training, and local AHJ program initiatives, and due to unavailability of requested SBMS editor support. |
|  | 1 | 9. LOTO and Interlock Safety SA (Legacy Document Conversion) | J. Durnan/J. Curtiss | 9/30/05 | Delayed until 9/30/05 due to attention required by sequence of OSHA, 70E, NRTL (listed/labeled) issue, updated training, and local AHJ program initiatives, and due to unavailability of requested SBMS editor support. |
|  | 2 | 10 Machine Shop Safety SA (New Subject Area) | K. Krasner/A. Piper | 3/31/05 | This has been delayed until the issuance of the joint BHSO/BSA machine shop assessment. |
|  | 1 | 11. Injury Management SA (New Subject Area) | J. Ellerkamp | 3/31/05 | Subject Area is in the review cycle. |
|  | 3 | 12. Identification of Piping Systems SA (Legacy Document Conversion) (To be incorporated as an exhibit to the Engineering Design SA) | J. Ellerkamp | 4/30/05 | Review complete. Waiting F&O to incorporate into Engineering Design Subject Area |
| 4.B.2 SBMS Endstate for the Facility Safety Management System | 3 | 1. Facility Authorization Basis Program Description (Triennial review) | G. Shepherd | 9/30/05 |  |
|  | 1 | 2. Accelerator Safety | G. Shepherd | 5/30/05 | Complete |
|  | 3 | 3. Facility Hazard Categorization SA (Triennial Review) | G. Shepherd | 9/30/05 |  |
|  | 2 | 4. Hazard Analysis SA (OHSAS and Hazard Identification Tool) | S. Hoey | 6/8/05 |  |
|  | 3 | 5. Operational Readiness Evaluation SA (Triennial Review) | R. Travis | 6/30/05 |  |
|  | 2 | 6. Nuclear/Criticality Safety SA | S. Moss | 3/31/05 | Complete Subject Area published 3/17/05 Completed and issued on SBMS as of 3/17/05. Lesson Plan for Criticality Safety Awareness Training revised to reflect new Subject Area. |
|  | 3 | 7. Traffic Safety SA (Update to incorporate bicycle safety and other legacy items.) | J. Ellerkamp | 6/15/05 | Complete |
|  | 2 | 8. Cryogenic Safety SA (Legacy Document Conversion) | J. Durnan | 4/30/05 |  |
|  | 2 | 9. Pressure Safety SA (Legacy Document Conversion) | J. Durnan | 6/30/05 |  |
|  | Low | 10. Fire Safety | J. Levesque | 6/30/05 |  |
|  | Low | 11. Working with Chemicals Revision – Adding content related to fire safety with respect to chemicals | J. Levesque | 7/30/05 |  |
| 4.B.3 SBMS Endstate for the Hazardous Material Transportation Safety Management System | 2 | Draft document transmitted to SBMS on schedule for the following: Four Subject Areas combined into two Material Transportation Subject Area (2 Subject Areas) | S. Hoey | 3/31/05 Schedule per SBMS Endstate Program and associated Notices of Intent |  |
| 4.B.4 SBMS Endstate for the Occupational Safety and Health Management System 4.B.4 SBMS Endstate for the Occupational Safety and Health Management System | 2 | 1. OSHAS 18001 Program Description | S. Hoey | 5/1/05 |  |
|  | 2 | 2. OSHAS 18001 Management System Description | S. Hoey | 5/15/05 |  |
|  | 2 | Draft ROD Document transmitted to SBMS on schedule. | S. Hoey | 9/30/05 |  |
| 4.B.5 Industrial Hygiene - Subject Area Triennial Updates | 3 | 1. Respiratory Protection SA | R. Selvey | 3/31/05 | Submitted to SBMS 02/22/05 |
|  | 3 | 2. Asbestos SA | R. Selvey | 6/31/05 | Team has met, submission is being drafted Review completed 6/31/05 |
|  | 3 | 3. Lead SA | R. Selvey | 6/31/05 Ken/rich: This date is wrong, my original submission in 10/4/04 was for end of 3rd Q, and that is the ATS tacking commitment. | Team has met, submission is being drafted Review completed 6/31/05 |

Attachment V

| ASSESSMENT CRITERIA: 5.0 Business and Operational Results |
| --- |
| OBJECTIVES: A. Financial management: To operate SHSD within its financial and operational objectives and measures |
| Strategy | Priority 1 | Indicators (Measures/Assessments) | Responsibility | Schedule/Due Date | Status |
| 5.A.1. Budget Performance Assessment | 3 | Review of budget. | P. Williams | Monthly (not tracked in SA Report) |  |
| 5.A.2. Annual Lab Budget Review | 2 | Attend the Meeting | P. Williams | Annual (Not tracked in SA report) |  |
| 5.A.3. Credit Card Reconciliation | 2 | Monthly review. | P. Williams | Monthly (not tracked in SA Report) |  |

Attachment VI

| ASSESSMENT CRITERIA: 6.0 Compliance with Laws, Regulations and Contractual Requirements |
| --- |
| OBJECTIVES: A. To assess Lab-wide compliance with specific regulatory requirements B. To perform SHSD operations in accordance with applicable laws, regulations and contractual requirements |
| Strategy | Priority 1 | Indicators (Measures/Assessments) | Responsibility | Schedule/Due Date | Status |
| 6.A.1 | 1 | OSHA Compliance Verification | Hoey | Quarterly Status Reports Summary will be provided by the SAP quarterly status report Tracked in ATS |  |
|  | 1 | NRTL Tracking | Curtiss |  | Will be implemented by 6/30 when local AHJ program is implemented |
|  | 1 | ISM Tracking | Williams |  |  |
|  | 1 | Injury/Accident Reduction Statistics | Ellerkamp |  |  |
| 6.A.2. Industrial Hygiene scheduled Assessments |  | Draft Assessment Reports Completed on Schedule |  |  |  |
|  |  | 1. IH Annual Multitopic Assessment (Asbestos, Beryllium, Noise & Hearing Conservation, Confined Space Permit Review, Chemical Hygiene, HEPA Surveillance, Respirators | R. Selvey | 12/31/04 | Complete Report dated 2/10/05 |
|  |  | 2. Laser Assessment | R. Selvey | 9/30/05 |  |
| 6.A.3 Safety Engineering Scheduled Assessments |  | 1. Draft Assessment Reports Completed on Schedule |  |  |  |
|  |  | 2. BNL Injury Prevention and Post-Injury Management Process (Joint with Liberty Mutual) | J. Ellerkamp | 3/15/05 | Liberty Mutual is working on the draft report. Due date revised to 3/15/05 |
|  |  | 3. Machine Shop Safety Assessment of the Central Fabrication Services Division (Joint with BHSO and Liberty Mutual) | K. Krasner/ A. Piper | 3/31/05 |  |
|  |  | 4. Lockout/Tagout Assessment (limited in scope to interaction with ESH Coordinators, no field observations, due to attention required in developing local AHJ program during same time frame | J. Curtiss/ J. Durnan | 6/30/05 |  |
|  |  | 5. Fleet Vehicle and Traffic Safety Assessment | J. Ellerkamp/ A. Piper | 9/30/05 |  |
|  |  | 6. BNL Incident Investigation Process Assessment | J. Ellerkamp/ A.Piper | TBD |  |
| 6.B.1. Training & Qualification | 3 | Track completion of required courses (%) & JTAs Targets: Employees = 95%, Guest/Contractors = 80% | T. Blydenburgh | Quarterly Status Report | SHSD Employees have consistently kept a 97% training completion rate for March, April and May. SHSD had no guests/contractors for this time period. |
| 6.B.2 EMS 14001 Compliance Status | 1 | Develop FY’05 EMS Goals Conduct Self Evaluation of EMS Compliance | R. Selvey | 12/31/04 9/30/05 | Complete – 12/15/04 |
| 6.B.3 FY 2005 required assessments (as required by the Integrated Assessment Subject Area) Additional assessments may be added to the Integrated Assessment Subject ARea | 3 | Shelter in Place – Required Assessment Aid | K. Krasner | 9/30/05 |  |
| 6.B.4 Timely completion of all ATS/FATS items | High | All ATS/FATS items completed on schedule and verified complete. Based upon recommendation in IA&O Report SA 04-03. Owners should routinely verify that actions are completed prior to closing an assessment in ATS and should determine whether or not validation of effectiveness of completed actions should be conducted at some future time. | P. Williams | Tracked by S. Wiley Reported bi-weekly staff meetings |  |