# ANNEX H

# USAID/Caucasus

# SO 2.2  Legal Systems that Better Support Implementation of Democratic Processes and Market Reform

This SO supports the overall Mission objectives by empowering citizens through public awareness of their legal rights and supporting legal access mechanisms to enable them to pursue these rights.  Also, increasing the capacity of legal institutions for the effective, transparent, and fair implementation and enforcement of laws and regulations will lead to a more prosperous market-oriented democracy.  The strategy entails both supply and demand approaches.  The rule of law (ROL) approach to date has focused on the supply side by working with government reformers.  This approach will continue at a slower pace, to meet a still existing need and to maintain influence and consolidate investments made at the national level.  But, demand side activities will increase as private sector capacity grows.  This will entail a delicate balance, so as not to create unmet demands.  To ensure the public directly benefits from reform laws, the strategy also targets regions outside of Tbilisi.

| Activity Description and Contractor | Activity LOP Goal and Period | Results/Impact as of 12/31/99 [What Results? What Impact on Georgian society/Government] | Assessment of Potential for Future Impact/Change During Remainder of Program |
| --- | --- | --- | --- |
| NDI, ABA, ARD/Checci, AMEX | Technical assistance to draft, adopt and implement select reform laws. Drafting, enacting and implementing laws is an integrated continuum of activity that, by its nature, includes assisting the development of those institutions, state and non-state, critical to implementation. 1995-2003 | A substantial number of reform laws have been passed, that improve the legal basis for human rights protection, business development, an independent judiciary, more transparent government, decentralization of power, etc. These laws include Civil and Civil Procedure Codes, Criminal and Criminal Procedure Codes, Administrative and Administrative Procedure Codes, Law on Common Courts, Law on Local Self-Governance, etc. | These laws provide the legal framework for major reforms. Following the implementation many of these legal acts will require reevaluation. A number of amendments are already planned. USAID will continue to support the Legal Affairs Committee’s efforts to refine major legislation. |

| NDI, AMEX and TBD | Technical assistance to draft, adopt, review and implement Constitution 1995-2000 | A progressive Constitution enacted in 1995 supports democracy and free markets, through protection of human rights and the separation of powers. The law “On the Structure and Activities of the Executive Authorities” was amended 12/00 to increase the authority of the State Minister. This action was taken in lieu of amending the Constitution to provide for a Prime Ministerial system, thus providing a simpler solution. | A series of workshops, begun in December 1999, will examine how the constitution works in real life; its successful concepts/articles; required developments and clarifications; the implementation progress and impediments. This will conclude with a large conference to celebrate the 5th anniversary of the Constitution on August 24, 2000. |
| --- | --- | --- | --- |
| ARD/Checci AMEX and TBD | Technical assistance to draft, adopt and implement Civil Code and Civil Procedure Code, and provide training on both 1997-2002 | Civil Code was enacted 06/26/97 and the Civil Procedure Code was enacted 10/14/97. The commentaries on the Codes, which serve as practical guides, are available for legal professionals. Attorneys and judges, trained on the Civil Code are better able to apply the concepts into practice. | USAID will support a high quality English translation, which will become available to individuals and businesses. As a result of the Civil Code translation, a Georgian/English legal glossary will be prepared. |
| AMEX and TBD | Technical assistance to draft, adopt, implement and revise the Administrative Code (FPP) 1997-2003 | The Administrative Code was passed 06/99. It contains a Freedom of Information (FOI) section. In 12/99 USAID sponsored a FOI conference for high-level representatives of GOG, media and NGOs. Participants produced recommendations for implementing Administrative Code. | Administrative Code went into force on 01/01/00. The Code will strengthen individuals and businesses in their dealing with the government by providing a point of entry for challenging over-intrusive laws and regulations and minimizing opportunities for corrupt government actions. In 03/00 USAID will sponsor Training of Trainers activity for requesters and providers of information. |
|  |  | Based on the conference recommendations, on 12/28/99 the GOG established a Council headed by the State Minister w/ representatives from GOG, media, NGOs and USG to provide assistance and oversee the implementation of the Administrative Code. This is an excellent model of GOG and civil society working together. | USAID will provide targeted assistance for selected government agencies to develop model processes and procedures that other agencies could adopt. |
| AMEX | Technical assistance to draft, adopt, implement and revise Criminal Code and Criminal Procedure Code (FPP) | Criminal Procedure Code was passed in 1998 and Criminal Code was passed in 1999. | Amendments to both are needed. The Legal Affairs Committee is developing drafts. A modern Criminal Code and Criminal Procedure Code will help prevent human rights violations. |
| AMEX | Licensing Law (FPP) | Licensing Law was passed in May 1999, reducing the number of licenses from 50 to 12 and agencies involved down to 11. This reduces the burden on business and limits opportunities for corruption | The public education campaigns will raise the awareness of legal rights in the business and communities. The program will be co-funded by the World Bank. |
| AMEX | Law on Enforcement of Judgements (FPP) | The Law was enacted on 04/16/99. It establishes an operating unit and mechanisms for ensuring the proper and timely enforcement of Court decisions. An assessment was completed of the draft law and its implementing regulations. | The World Bank will have a leading role in the technical assistance for implementing instructions. |
| AMEX and TBD | Provision of computer and peripheral equipment for Courts and MOJ | In 1999 USAID provided 7 computers, 2 fax machines and a copier to the Supreme Court, enabling it to produce and publish written decisions on a timely basis. In 1999 USAID provided 10 computer packages to appellate court system to enable it to function, since World Bank assistance for court administration was not yet available. In 1999 USAID provided 13 computers to the Ministry of Justice; and supported the installation of a LAN system for all computers. This increased the Ministry of Justice’s capacity to make normative acts available on a more timely basis. USAID paid for internet connection of Constitutional Court, which is also used by the Supreme Court. | The new ROL project will provide additional equipment support for targets of opportunity. |
| ABA/CEELI | Technical assistance for the preparation and administration of judicial qualification exams and other legal professional exams. 1998-2001 | 6 judicial qualification exams have been held since May 1998. The exams administered on 10/99 and 03/00 were prepared entirely in Georgia. The author of the exams was named Minister of Justice in 08/98 and Chairman of the Supreme Court in 07/99. The Council of Justice has developed the sustainable capacity to prepare and administer exams. On 05/15/99 176 newly qualified judges were appointed to the courts. 14 new judges were appointed to the Supreme Court on 16/07/99 and 02/17/00. AMEX has provided Training of Trainers and specialized training to both groups of certified judges. Competent judges are now on the bench deciding cases. A larger number of civil cases are being heard (87.17 % of total caseload) and anecdotal reports from private attorneys indicate many judges are considering cases more carefully. The exams received widespread media coverage and demonstrated that an honest and transparent process could be administered in Georgia. The Georgian Council of Justice has provided technical assistance to other NIS countries, e.g., Tajikistan and Moldova, seeking to implement qualification exams. The OSCE/ODIHR report on October 1999 Parliamentary Elections singled out the Supreme Courts’ handling of election-related cases, which resulted in 67 candidates being restored to party lists. | The lessons learned and capacity developed will prove valuable for other legal professional exams such as bar exams and procurator exams. USDOJ will fund ABA’s assistance, if any, for the procuracy exams. Qualification exams will produce a higher caliber of legal professionals. The public will have increased confidence in using the judicial system to resolve disputes. In March 2000, IFES will provide training to judges from the administrative chamber and district courts on election complaint adjudication. |
| ABA/CEELI | Technical assistance to legal advocacy NGOs 1998- 2002 | 2 legal clinics are operating in Tbilisi. Since 04/98, 108 cases have been resolved. These cases involve clients who otherwise would not have had access to justice. A cadre of 59 young attorneys has been trained. In light of the lack of political will for law school reform, alternative forms of legal education prove necessary. | This program will be expanded to include a newly created city attorney program in Tbilisi. Lawyers will be available on a 24-hour basis at pre-trial detention centers. |
| ABA/CEELI | Creation of Judges’ Association | A private judges’ association was established in 06/99. The association is already serving as an advocacy organization for the judges to ensure judicial independence and timely salary payments and provision of other benefits. | USAID will continue to support the institutional strengthening of the Judges’ Association. |
| ABA/CEELI | Law on the Bar | Little progress was made on this law until late in 1999 when a new ABA liaison arrived and organized a working group of practicing attorneys to prepare a draft law. | Once passed, the Law on the Bar will improve quality of law schools since licensing would address problem of poor law schools from the demand side through market forces. Future lawyers knowing that they will face a bar exam will demand a higher quality legal education. |
| ABA/CEELI | Judicial Disciplinary Law | Progress was slow in 1999. However, the law was adopted on 02/23/00 Adoption of the Judicial Disciplinary Law is essential for the completion of the legal framework for the judicial reform | Implementation of this law will increase the accountability of judges and influence the introduction of transparent practices in courts. |
| ABA/CEELI | Gender | USAID has been providing support for the Women’s Center to prepare and publish a series of brochures on laws affecting Georgian women. | Increased awareness of the laws protecting women’s rights should lead to better protection of them. |
| ABA/CEELI | Conference of Judges | Little progress has been made to date, but the first organizational meeting for the Conference is tentatively scheduled for April 2000. | A Conference of Judges will help the judges administer the court system and discipline judges. Such authority will bolster judicial independence. |
| NDI | Technical assistance to the Parliament 1994 – 2002 | Seminars, conferences and town hall meetings helped inform Parliament’s legislative drafting and spur enactment of such laws as Conflict of Interest, Local Self-Governance, etc. Committee system was strengthened and was recently expanded to include and Interfaction Coordinating Committee to promote multi-partisan approaches to legislation. | USAID will continue to support a Parliamentary development program to strengthen the capacity of committees, factions and departments, promote public input in lawmaking, and support parliamentary oversight. |
| NAPA | Management information system and legal data base for Parliament | Parliament has streamlined functions and uses e-mail and intranet to communicate with those members that have access to the systems. | Once security firewalls are in place, the public and legal professionals will have electronic access to the 745 laws passed by the last Parliament. The system and equipment will be expanded under a new ROL project. |
| Eurasia Foundation | Rule of Law Grant Competition 2000-2001 | TBD | Grants will support efforts by NGOs and the media to increase government transparency and reduce opportunities for abuse of authority. |