Federal Aviation Administration

Runway Status Lights

Section C: Statement of Work

Federal Aviation Administration

800 Independence Avenue, SW

Washington, DC 20591

C.1	Introduction	1

C.1.1	Background	1

C.1.2	Scope	2

C.2	Applicable Documents	2

C.2.1	Obtaining Copies of Documents	6

C.3	System Requirements	7

C.3.1	Program Management	7

C.3.1.1	Program Management Planning and Status Reporting	7

C.3.1.2	Program Metrics	7

C.3.1.3	Contract Work Breakdown Structure	8

C.3.1.4	Risk Management	8

C.3.1.5	Earned Value Management	8

C.3.1.6	Integrated Master Schedule	9

C.3.1.7	Program Reviews	9

C.3.1.8	System Safety Program	16

C.3.1.9	Configuration Management Program	18

C.3.1.10	Quality Management	23

C.3.2	Systems Engineering and Design Development	23

C.3.2.1	Systems Engineering Documentation	23

C.3.2.2	System/Subsystem Design Description	23

C.3.2.3	Interface Control Documentation	24

C.3.2.4	Human Engineering Design	24

C.3.2.5	Engineering Services	25

C.3.3	Software Development	26

C.3.3.1	System Software Design	26

C.3.4	System Test and Evaluation	31

C.3.4.1	Development Test and Evaluation	32

C.3.4.2	Operational Test and Evaluation	40

C.3.4.3	Regression Tests	40

C.3.4.4	Production Acceptance Test and Evaluation (PAT&E)	41

C.3.5	Construction, Delivery, Installation and Checkout	41

C.3.5.1	Implementation Management	42

C.3.5.2	Construction	44

C.3.5.3	System Installation	48

C.3.6	Integrated Logistics Support	51

C.3.6.1	ILS Program Management	51

C.3.6.2	Integrated Support Plan	52

C.3.6.3	RWSL Maintenance Concept	52

C.3.6.4	Logistics Management Information	53

C.3.6.5	Supply Support	53

C.3.6.6	Technical Data	54

C.3.6.7	Technical Operations Specialists Training	59

C.3.6.8	Air Traffic Training	66

C.3.6.9	Second Level Engineering Training	67

C.3.6.10	Contractor Support and Services	68

C.3.6.11	Interim Contractor Depot Logistics Support Requirements	70

C.3.6.12	Post-Commissioning Technical Site Support	72

C.3.6.13	System Support Equipment/Facilities Services	72

C.3.6.14	Contractor Support Services	74

C.4	Full Production and Deployment Requirements	75

C.4.1	Depot Setup	75

C.4.2	Interim Contractor Depot Level Support Transition Plan (ICDLSTP)	75

C.4.2.1	Tools and Test Equipment List	75

C.4.2.2	Depot Test Equipment Manuals	76

C.4.2.3	Depot Test Procedures	76

C.4.2.4	Depot Repair/Support Training	76

C.4.3	FAA Academy Training Support System	77

C.5	Acronyms	78

## Introduction

This Statement of Work (SOW) describes the work required for the Contractor to design, develop, produce, test, construct, install, and provide support for the implementation of the Runway Status Lights (RWSL) system at up to 35 airports, plus options for an additional three (3) support systems.  The RWSL system consists of the RWSL processor and the Field Lighting System (FLS). This SOW states the requirements for:

- First Article (FA/pre-production) (1 each) of RWSL System at the Designated Key Site.

- Software design, integration, systems logistics support for the production (post FA acceptance), construction and installation of the RWSL processor and FLS (20 each)

- FLS installation and integration of the RWSL processor with the FLS (same 20 sites referenced in B)

- Depot Level Support

- Options for construction and installation of the FLS for up to 14 additional sites, plus up to three support systems

- Options for integration of the RWSL processor with the FLS  for up to 14 additional sites, plus up to three support systems

- The items above (a-f) include the use of Commercial-off-the-Shelf (COTS) equipment where applicable and modified COTS for the FLS

### Background

The Federal Aviation Administration (FAA) is dedicated to the goal of enhancing runway safety while maximizing operational efficiency and ensuring airport capacity. The reduction of runway incursions is one of the most important aviation safety initiatives and is crucial for the improvement of runway safety.

RWSL offer a means of reducing runway incursions and preventing runway accidents. They do so by indicating to pilots and vehicle operators that a runway is unsafe for entry or crossing or that a runway is unsafe for departure, thereby increasing situational awareness. Direct pilot and vehicle operator notification is required because surface surveillance and air traffic controller tools alone cannot prevent some types of runway incursions and accidents that are time critical.  The RWSL display critical, time-sensitive safety status information directly to pilots and vehicle operators reducing the time it takes to alert them of potentially unsafe situations. This need is identified in the National Transportation Safety Board (NTSB) most wanted transportation safety improvements. The NTSB action recommends that the FAA “Implement a safety system for ground movement that will ensure the safe movement of airplanes on the ground and provides direct warning capability to the flight crews”.  This is a new capability and does not replace any existing National Airspace System (NAS) assets.

The RWSL software detects the presence and motion of aircraft and surface vehicles on or near the runways, assesses any possible conflicts with other surface traffic, illuminates red runway-entrance lights (RELs) if the runway is unsafe for entry or crossing, and illuminates red takeoff-hold lights (THLs) if the runway is unsafe for departure. The system turns the lights off automatically as appropriate when the runway is no longer unsafe.

The RWSL system consists of an RWSL processor and an FLS. The RWSL processor receives surveillance data of aircraft and vehicles on or near the airport surface from the Airport Surface Detection Equipment Model – X (ASDE-X) surface surveillance system. The RWSL processor uses this surveillance data to determine when to activate and deactivate the RELs and THLs. These light commands are sent to the RWSL FLS. The FLS includes a Light Computer, in-pavement light fixtures, and all light system circuitry. The FLS receives the light commands and illuminates and extinguishes the lights as commanded by the RWSL processor. The system will automatically determine runway configurations and will adjust the activation and deactivation of RELs and THLs accordingly. The system will automatically adjust light intensity according to time of day. The intended service life for RWSL is a minimum of 20 years.

RWSL does not significantly increase air traffic controller workload, nor decrease airport capacity, but rather works in concert with existing and new procedures to enhance runway safety.  Controllers are not required to monitor RWSL light illumination and extinguishing.  The ground surveillance system safety logic hold bars are independent of the RWSL lights.  The lights are driven automatically using computer processing of integrated surface and terminal surveillance information.

### Scope

This SOW defines the requirements for the Contractor development, production, construction, installation, checkout, test and support for implementation of the RWSL system across designated FAA airports.  The RWSL system includes all hardware, software, firmware, interfaces, commercial and non-commercial licenses, special support and test equipment necessary to meet the requirements of the RWSL System Specification FAA-E-3001, FLS Specification FAA-E-3002, and this SOW.

This SOW encompasses the requirements for all resources required of the Contractor to produce, deliver, install, test and provide support for additional RWSL systems beyond the first article system.

## Applicable Documents

The following specifications, handbooks, orders, standards, and drawings form a part of this SOW and are applicable to the extent specified herein. The latest version of these documents as of the contract date shall apply. In the event of conflict between this SOW and any of the applicable documents cited below, the provisions of this SOW shall apply.

Table 1: Applicable Documents

| Document Number | Title |
| --- | --- |
| FAA Specifications: |
| FAA-C-1391B | Installation and Splicing of Underground Cables |
| FAA-E-3001 | Performance Specification, RWSL System |
| FAA-E-3002 | Performance Specification, Field Lighting System (FLS) |
| FAA-E-2761A | Cable, Fiber Optic, Multimode, Multifiber |
| FAA-E-2942 | ASDE-X System Specification, |
|  | Interface Requirements Document, ASDE-X to RWSL |
|  | Interface Design Document for the ASDE-X Program, Version 11, August 10, 2007. |
|  | Interface Control Document; RWSL Processor to Field Lighting System (FLS) Interface |
| FAA-C-1217F | Electrical Work, Interior |
| FAA-G-2100H | Electronic Equipment, General Requirements |
| FAA-D-2494B | Technical Instruction Book Manuscripts: Electronic, Electrical, and Mechanical Equipment, Requirements for Preparation of Manuscript and Production of Book |
| FAA Standards: |
| FAA-STD-002F | Standard Engineering Drawing Preparation and Support |
| FAA-STD-019E | Lightning Protection, Grounding, Bonding, and Shielding Requirements for Facilities |
| FAA-STD-025F | Preparation of Interface Documentation |
| FAA-STD-026A | Software Development for the National Airspace System (NAS) |
| FAA-STD-028C | Contract Training Programs |
| FAA-STD-032 | Design Standards for National Airspace Facilities |
| FAA-STD-39C | National Airspace System (NAS) Open System Architecture and Protocols |
| FAA-STD-057 | Airport Fiber Optic Communications System (FOCS) Standards |
| FAA Advisory Circulars |
| FAA Advisory Circular AC 150/5210-20 | Ground Vehicle Operations on Airports |
| FAA Advisory Circular AC 150/5300-13 | Airport Design Standards |
| FAA Advisory Circular AC 150/5320-6D | Airport Pavement Design and Evaluation |
| FAA Advisory Circular AC 150/5320-12C | Measurement, Construction and Maintenance of Skid Resistant Airport Pavement Surfaces |
| FAA Advisory Circular AC 150/5320-17 | Pavement Surface Evaluation and Rating Manuals |
| FAA Advisory Circular AC 150/5335-5A | Standardized Method of Reporting Airport Pavement Strength |
| FAA Advisory Circular AC 150/5340-30C | Design and Installation of Airport Visual Aids |
| FAA Advisory Circular AC 150/5345-1V | Approved Airport Equipment |
| FAA Advisory Circular AC 150/5345-3F | Specification for L-821, Panels for the Control of Airport Lighting |
| FAA Advisory Circular AC 150/5345-5B | Circuit Selector Switch |
| FAA Advisory Circular AC 150/5345-7E | Specification for L-824 Underground Electrical Cable for Airport Lighting Circuits |
| FAA Advisory Circular AC 150/5345-10F | Specification for Constant Current Regulators and Regulator Monitors |
| FAA Advisory Circular AC 150/5345-26C | FAA Specification for L-823 Plug and Receptacle, Cable Connectors |
| FAA Advisory Circular AC 150/5345-42F | Specification for Airport Lighting Bases, Transformer Housings, Junction Boxes, and Accessories |
| FAA Advisory Circular AC 150/5345-46C | Specification for Runway and Taxiway Light Fixtures |
| FAA Advisory Circular AC 150/5345-47B | Specification for Series to Series Isolation Transformers for Airport Lighting Systems |
| FAA Advisory Circular AC 150/5345-53C | Airport Lighting Equipment Certification Program |
| FAA Advisory Circular AC 150/5370-2E | Operational Safety on Airports During Construction |
| FAA Advisory Circular AC 150/5370-10C | Standards for Specifying Construction of Airports |
| FAA Advisory Circular AC 150/5370-11A | Use of Nondestructive Testing Devices in the Evaluation of Airport Pavement |
| FAA Advisory Circular AC 150/5370-12A | Quality Control of Construction for Airport Grant Projects |
| FAA Advisory Circular AC 150/5370-13A | Off-Peak Construction of Airport Pavements Using Hot-Mix Asphalt |
| FAA Advisory Circular AC 150/5370-14A | Hot-Mix Asphalt Paving Handbook |
| FAA Advisory Circular AC 150/5370-16 | Rapid Construction of Rigid (Portland Cement Concrete) Airfield Pavements |
| Military Standards & Handbooks |
| MIL-HDBK-61A | Configuration Management Guidance |
| MIL-STD-129P | Military Marking |
| MIL-HDBK-470A | Designing and Developing Maintainable Products and Systems Volume I |
| MIL-HDBK-781A | Reliability Test Methods, Plans, and Environments for Engineering Development, Qualification, and Production |
| MIL-PRF-28000B | Digital Representation for Communication of Product Definition Data: IGES Application Subsets and IGES Application Protocols |
| MIL-DTL-31000C | Technical Data Package |
| MIL-HDBK-46855A | Human Engineering Program Process and Procedures |
| MIL-PRF-49506 | Performance Specification, Logistics Management Information |
| Federal Documents |
| Executive Order 12699 | Seismic Safety of Federal and Federally Assisted or Regulated New Building Construction |
| Executive Order 12941 | Seismic Safety of Existing Federally Owned or Leased Buildings |
| Executive Order 13423 | Strengthening Federal Environmental, Energy and Transportation Management |
| 10 CFR 435 | Energy Efficiency Standards for New Federal Low-Rise Residential Buildings |
| 14 CFR Part 77 | Objects Affecting Navigable Airspace |
| 29 CFR 1910 | Occupational Safety and Health Standards |
| 29 CFR 1926 | Safety and Health Regulations for Construction |
| 29 CFR 1960.17 | Alternate Standards |
| 29 CFR 1960.8 | Agency Responsibilities |
| 47 CFR 2 | Frequency Allocations and Radio Treaty Matters; General Rules and Regulations |
| 47 CFR 15 | Radio Frequency Devices |
|  | Federal Information Security Management Act of 2002 (FISMA) |
|  | Federal Emergency Management Administration (FEMA) Handbook 224, ICSSC RP-4 |
|  | National Environmental Policy Act (NEPA) of 1969 |
|  | Environmental Protections Agency (EPA) National and Local Building Codes |
|  | Occupational Safety and Health Administration (OSHA) Standards national and Local Building Codes |
|  | National Energy Conservation Policy Act |
| NFPA No. 70 | National Fire Protection Association, National Electrical Code (NFPA) 70 |
| NFPA No. 78 | National Fire Protection Association, Lightning Protection Code |
| DOT/FAA/CT03/05 (HF-STD-001) | Human Factors Design Standard for Acquisition of Commercial-off-the-Shelf Subsystems, Non-Developmental Items, and Developmental Systems |
| Other FAA Documents |
| FAA Order 1050.1E | Policies and Procedures for Considering Environmental Impacts |
| FAA Order 1050.10C | Prevention, Control, and Abatement of Environmental Pollution at FAA Facilities |
| FAA Order 1050.14A | Polychlorinated Biphenyls (PCBs) in the NAS |
| FAA Order 1050.18 | Chlorofluorocarbons and Halon Use at FAA Facilities |
| FAA Order 1050.19B | Environmental Due Diligence Audits in the Conduct of FAA Real Property Transactions |
| FAA Order 1053.1A | Energy and Water Management Program for FAA Buildings and Facilities |
| FAA Order 1370.82A | Information Systems Security Program |
| FAA Order 1600.1E | Personnel Security Program |
| FAA Order 1600.2E | Safeguarding Classified National Security Information |
| FAA Order 1600.6E | Facility Security Policy |
| FAA Order 1600.69B | FAA Facility Security Management Program |
| FAA Order 1600.72A | Contractor and Industrial Security Program |
| FAA Order 1600.73 | Contractor and Industrial Security Program Operating Procedures |
| FAA Order 1600.75 | Protecting Sensitive Unclassified Information (SUI) |
| FAA Order 1800.66 | Configuration Management Policy |
| FAA Order 3000.22 | Air Traffic Services Training |
| FAA Orders 3120.4L | Air Traffic Technical Training |
| FAA Order 3900.19B | FAA Occupational Safety And Health Program |
| FAA Order 3900.57 | FAA Pre-Construction and Maintenance Project Safety and Health Checklist |
| FAA Order 4800.8A | Utilization and Disposal of Excess and Surplus Personal Property |
| FAA Order 6000.30D | National Airspace System Maintenance Policy |
| FAA Order 6000.36A | Communications Diversity |
| FAA Order 6000.53B | Remote Maintenance Monitoring Interface Development and Implementation |
| FAA Order 6200.4F | Test Equipment Management |
| FAA Order 6950.22 | Maintenance of Electrical Power and Control Cables |
| FAA Order 6950.27 | Short Circuit Analysis and Protective Device Coordination |
| FAA Order 6950.2D | Electrical Power Policy Implementation at National Airspace System Facilities |
| FAA Order 6970.3A | Maintenance of Environmental Systems |
| FAA Order 8040.4 | Safety Risk Management |
| FAA Order 9550.8 | Human Factors Policy |
| ATO-S 2006-1 Version 1.4a | Safety Risk Management Guidance for System Acquisitions |
| SMS Manual | FAA Safety Management System (SMS) Manual (version 1.1) dated May 21, 2004. |
| Non-Government Documents |
| ANSI/AIM-BC1 | Uniform Symbology Specification Code 39 |
| ANSI/EIA-649-A 2004 | National Consensus Standard for Configuration Management |
| ANSI/EIA-748B | Earned Value Management System (Published June 2007) |
| ASTM-D3951-98 (2004) | “Standard Practice for Commercial Packaging |
| ANSI/ISO/ASQ Q9001-2000 | AMERICAN NATIONAL STANDARD, Quality management system – Requirements |
| ISO/IEC 90003-2004 | Software engineering – Guidelines for the Application of ISO 9001-2000 to the development of computer software |
| IEEE/EIA 12207.0 | Industry Implementation of International Standard ISO/IEC 12207:1995 – Software Life Cycle Processes (ISO/IEC 12207:1995, MOD) |
| ISO 10007:2003 | Quality Management Systems – Guidelines for Configuration Management |
| RTCA DO-278 | Guidelines for Communication, Navigation, Surveillance, and Air Traffic Management (CNS/ATM) Systems Software Integrity Assurance |

### Obtaining Copies of Documents

a.	Copies of FAA specifications and interface documents may be obtained from the Federal Aviation Administration, Headquarters Public Inquiry Center APA-230, 800 Independence Avenue SW, Washington, DC 20591, 202-267-3484. Requests should fully identify material desired and cite the solicitation or contract number.

b. 	Requests for copies of documents not covered in the preceding paragraph should be addressed to the Contracting Officer. Requests should fully identify material desired and cite the solicitation or contract number.

c. Copies of Military Standards and Specifications may be obtained via the following website, http://dodssp.daps.dla.mil/.

d. 	Copies of ISO/ASQ Q9001-2000 and ISO/IEC 90003-2004 can be obtained from the following source: American Society for Quality Control 600 North Plankinton Avenue P.O. Box 3005; Milwaukee, Wisconsin 53201-3005. Phones: (414) 272-8575 or (800) 248-1946. The fax is: (414) 272-1734.

e. 	Copies of the Acquisition Management System Test and Evaluation Process Guidelines are available in the FAA Acquisition System Toolset (FAST). The on-line internet address of FAST is: http://fast.faa.gov/.

## System Requirements

### Program Management

#### Program Management Planning and Status Reporting

The Contractor shall provide the necessary program management, including but not limited to, project management, risk management, data management, configuration management, subcontract management, financial, cost, and earned value management, schedule management, and resource management, to accomplish the requirements of this SOW.  The Contractor shall submit a Program Management Plan (PMP) in accordance with CDRL PM01.

The Contractor shall assign a designated Program Manager (PM) to manage this effort.   The PM shall be the point of contact between the FAA and the Contractor in the execution of this program and shall be prepared at all times, given reasonable notice, to present and discuss with the FAA the status of contract activities.

The Contractor shall continuously monitor the performance of this contract, and of all subcontracts, to provide the Government with a timely assessment of program progress or problems, and to control the contract activities as well as subcontractor and vendor activities. The Contractor shall establish a schedule designed to accomplish the tasks described in this contract. The schedule shall be maintained in an Integrated Master Schedule (IMS) (3.1.6), and shall include both planned dates and actual completion dates.

The contractor shall submit monthly Program Status Reports (PSR) in accordance with the CDRL PM02.

CDRL  PM01 	Program Management Plan

CDRL  PM02 	Program Status Report

#### Program Metrics

The Contractor shall track and report program metrics. These metrics shall include the following:

- Program Software Cost and Schedule (Contract Performance Measurement)

- Program Staffing (Software Effort)

- Program Requirements (Stability Measure)

- Program Quality (Software Errors)

- Software Program Size (Source Lines of Code)

- Construction and implementation metrics

- Technical Performance Measures

For the Software Program Size (Source Lines of Code) metric, the Contractor shall prepare two sub-metrics (including charts). One sub-metric is for tracking Contractor-developed code only. The second sub-metric is for total non-COTS software in RWSL.

CDRL  PM03  Program Metrics Report

#### Contract Work Breakdown Structure

The Contractor shall develop and maintain a Contract Work Breakdown Structure (CWBS) and dictionary based on the Acquisition Management System (AMS) Work Breakdown Structure (WBS), particularly in Sections 3 and 4 located at http://fast.faa.gov/wbs/wbssec.htm.  The Contractor shall not change the CWBS or associated definitions without Government approval.  Major elements that are sub-contracted shall be identified in the CWBS.

CDRL  PM04  Contractor Work Breakdown Structure

#### Risk Management

The Contractor shall establish, implement and maintain a Risk Management (RM) program that provides for an overall strategy and approach for effectively managing cost, schedule, and technical performance risks throughout the performance of the contract.  The Contractor shall prepare and submit a Risk Management Plan (RMP), in accordance with CDRL PM05, that describes how the team intends to perform timely risk identification, accurate risk assessment, determination and implementation of mitigation plans, monitoring, tracking, and reporting of risks items and risk management activities.  The Contractor shall include risk items identified by the Government and the subcontractors.  The risk item information (risk description, assessment and mitigation plans) shall be reported on a monthly basis to the government in the Risk Assessment Report (RAR) in accordance with CDRL PM06.  The Contractor shall provide the status of, and mitigation actions for, identified medium and high program risks, with the exception of security risks, at Program Management Reviews (PMRs) (3.1.7.2).

The Contractor shall also complete the following requirements:

- Identify and quantify risks with respect to the impact on development, integration, manufacturing, test, installation, performance, schedule, and cost.

- Develop and maintain a list identifying, analyzing, and classifying program risks.  Program risks shall be classified as low, medium, or high priority.

- Propose risk management techniques and define risk mitigation plans for medium and high priority risks.

- Provide updates to the risk analysis status and risk mitigation plans through the Risk Assessment Reports and in the Program Management Reviews (PMR).

CDRL  PM05  Risk Management Plan

CDRL  PM06  Risk Assessment Report

#### Earned Value Management

The Contractor shall establish, maintain, and use in the performance of this contract, an integrated performance management system.  Central to this integrated system shall be a validated Earned Value Management System (EVMS) in accordance with the guidelines for an EVMS contained in ANSI/EIA-748-B.  To establish the integrated performance management system, the EVMS shall be linked to and supported by the Contractor’s management processes and systems to include the integrated master schedule, contract work breakdown structure, change management, material management, procurement, cost estimating, and accounting.  The correlation and integration of these systems and processes shall provide for early indication of cost and schedule problems, and their relation to technical achievement.

The Contractor shall provide a quarterly Contract Funds Status Report (CFSR), in accordance with CDRL PM07, clearly delineating the contract commitments and expenditures at the CLIN and appropriate CWBS level, as well as forecast funding expenditures.   The CFSR shall be included in the Program Status Report. The Contractor shall provide a monthly Contract Performance Report (CPR), in accordance with CDRL PM08, clearly stating the contract cost baseline, actual and estimates.

CDRL  PM07  Contract Funds Status Report

CDRL  PM08  Contract Performance Report

#### Integrated Master Schedule

The Contractor shall establish an IMS in accordance with CDRL PM 09.

CDRL  PM09  Integrated Master Schedule

#### Program Reviews

The Contractor shall conduct meetings and program reviews in accordance with the Government approved PMP and this SOW.  For each meeting and management review, the Contractor shall:

- Create and provide an agenda and overall strategy for conducting each meeting in accordance with CDRL PM10

- Present material for meeting the objectives of the meeting

- Provide backup data regarding assumptions made and methodologies used in arriving at recommendations or conclusions

- Provide minutes, action items and presentation materials in accordance with CDRL PM11

Designated management and formal reviews and audits shall not be considered complete until Government approval.

Support provided by the Contractor shall include, but is not limited to, facilities, materials, office equipment, clerical personnel, mockups, technical data, and subcontractor participation (when requested by the Government).

##### Post Award Conference

The Contractor shall plan for, host, and support a post award conference to be held at the Contractor's site within one month after contract award. The Government will determine the actual date within 2 weeks after contract award. At this conference, the Contractor shall address the plans, cost, schedule and risks for the RWSL work efforts.

##### Program Management Reviews

The Contractor shall convene PMRs to demonstrate the successful completion, or progress toward completion, of project milestones.  PMRs shall be provided monthly during the period of performance of this contract.  The PMRs will normally be conducted at the Contractor's facility; however other sites may be selected by mutual agreement between the Government and Contractor. During the PMRs, the Contractor shall present plans for accomplishing project milestones and activities, an overview of system engineering, hardware and software development, test, logistics and installation issues and analyses, and status as reported in the PSR. The Contractor shall provide evidence that all criteria that may be requested by the Government are satisfied to receive approval.

The Contractor shall submit agendas and meeting minutes in accordance with CDRL PM 10 and PM 11. Presentation materials shall be prepared and included with the agenda.

CDRL  PM10  Agenda

CDRL  PM11  Meeting Minutes

##### Integrated Baseline Review

The purpose of the Integrated Baseline Review (IBR) is to:

- Ensure that the Government and Contractor mutually understand program scope, schedule, resources, inherent risk, and management approach

- Ensure early and adequate planning

- Identify risk items for incorporation into the risk management plan

- Ensure appropriate reporting levels have been identified and variance thresholds agreed to by the Government and Contractor

The Contractor shall provide ongoing access during contract performance to pertinent records and data, which underlie and support the cost and schedule data reported. The Contractor shall provide an agenda, presentation materials, and meeting minutes in accordance with CDRLs PM10 and PM 11. The IBR shall be conducted as a separate review until such time as the Government determines that it can be integrated into PMRs.

##### System Engineering Reviews and Technical Interchange Meetings

The purpose of Technical Interchange Meetings (TIMs) is to ensure continued Government visibility into the technical progress of the contract. The Contractor shall plan and participate in bi-monthly TIMs between the Government and the Contractor at the Contractor's facility and sites selected by the Government. The TIMs will be conducted to discuss the status of technical activities, including, but not limited to: studies, test plans and results, design issues, and cost, schedule, performance, implementation, logistics, and technical guidance.

The Contractor shall support the following planned technical interchange meetings to manage the evolving RWSL design and program control activities:

- System Requirements Review (SRR)

- Preliminary Design Review (PDR)

- Critical Design Review (CDR)

- Final Design Review (FDR)

The Contractor shall prepare and submit to the Government an agenda, presentation materials, and minutes for all technical reviews in accordance with CDRLs PM10 and PM 11. Presentations shall be based upon the Contractor’s system/subsystem engineering efforts and related documentation. Minutes shall contain copies of all presentation material, results of discussions and any decisions, a list of all actions, and a plan for each action item resulting from the review.  The formal minutes shall be used to document the meeting and will be used by the government in the approval process for the technical reviews and audits

At each review, the Contractor shall be prepared to provide back-up data on assumptions made and methodologies used in arriving at specific recommendations/conclusions for the design approach. Key Contractor personnel shall be available to respond to Government questions.

The Contractor shall make available for reference and inspection at the reviews applicable engineering data, specifications, drawings, schematics, design and test documentation, software development files, schedules, and working papers and results of studies and analyses.

The Contractor shall notify the contracting officer of readiness for a review at least 20 calendar days in advance of the planned start of each review.  If the previous technical review has not been approved by the Government, or if documents required for a review have not been delivered to the Government as scheduled, the Government shall have the option of postponement without prejudice to other contractual requirements. Formal reviews shall not be considered complete until approval by the Government is granted in writing.

The following instructions apply to all technical reviews and audits:

- Presentations shall be conducted by Contractor personnel, although the Government reserves the right to revise the agenda and/or make presentations.

- The location of the reviews may be changed by mutual agreement between the Government/Contractor.

- The Contractor shall record all action items identified.

- Response to all assigned action items by either closure or a plan for closure shall be made by the Contractor to the Government in the minutes of the meeting/reviews.  The status of all action items shall be tracked at the PMRs and TIMs and provided in writing as part of the minutes until the action item has been resolved as mutually agreed by the Government/Contractor.

- Ten working days after receipt of the review/audit minutes, the Government will formally notify the Contractor of the results of the subject review/audit by:

- Approval - to indicate that the review/audit was completed satisfactorily.

- Contingent Approval - to indicate that the review/audit is not considered complete until completion of specific action items to the Government's satisfaction.

- Disapproval - to indicate that the review/audit was not satisfactory, and to identify those areas that were deficient.  The Contractor shall have 15 working days to respond to the Government and provide a plan to complete the review/audit and maintain the program schedule.

##### System Requirements Review

The Contractor shall conduct a System Requirements Review (SRR).  The objective of this review is to ascertain the adequacy of the Contractor’s efforts in defining system design requirements and to initiate the functional system requirements baseline.

During the SRR, the Contractor shall present results of functional flow analysis, system interface studies, cost effectiveness analysis, and program risk analysis.  The Contractor shall present detailed requirement definitions of the system under development.  The Contractor shall prove their full understanding of the operational concepts and problems that the system is designed to solve.  As part of the SRR, the Contractor shall present and review the following documents with the Government:

- Deliverables, with overview of the following documents:

  - Software Development Plan (SDP)

  - Draft System/Subsystem Design Description (SSDD)

  - Draft Software Requirements Specification (SRS)

  - Draft Contractor’s Master Test Plan (CMTP)

- Flows and system requirements definitions

- Critical Task Analysis

- Functional External System Interfaces

- System Safety Program safety considerations

- Security considerations and identification of security related requirements

- Human Engineering considerations

- Maintainability and Reliability requirements

- Plans for Key activities such as Testing or Site visits

- Integrated Master Schedule

- Identification of design-driving/cost-driving requirements

- Program risk analysis, including assumptions, trade-offs and alternative approaches

- Technical performance metrics and measures

- Logistic Support overview

- Manpower Requirements/Personnel analysis

SRR Acceptance Criteria

The SRR acceptance criteria are as follows:

- Demonstration of analysis and a thorough understanding of the requirements in the RWSL System Specification FAA-E-3001, FLS Specification FAA-E-3002, and the SOW.

- Initiation of the system and external interface functional requirements baseline fully traceable to the requirements in the RWSL System and FLS Specifications, SOW, and other related documents approved by the Government.

- Resolution of all action items.

          - Preliminary Design Review

The Contractor shall conduct a Preliminary Design Review (PDR).  This review shall be conducted for an aggregation of configuration items.  This review shall evaluate software and hardware requirements definitions.  This review shall evaluate design of each Hardware Configuration Item (HWCI) and Computer Software Configuration Item (CSCI).  The objective of this review is to establish the software and hardware requirements baseline, and to approve the high-level design of each configuration item.  The SRR must be approved by the Government before a PDR may be conducted, and all SRR action items must be closed prior to conducting the PDR, unless the Government has given permission to proceed.

During the PDR, the Contractor shall present data flow and control flow diagrams describing design solutions for each configuration item. During the PDR, the Contractor shall present software and hardware requirements defined and recorded for each CSCI and HWCI, the methods to be used to ensure that each requirement has been met, and the traceability between the CSCI/HWCI requirements and system requirements.

For items that are not Contractor-developed, the Contractor shall provide a functional/physical description and define technical requirements and interfaces with other system components.  For these non-developmental items, the Contractor shall provide the results of the analysis that verifies the item will meet the associated technical requirements and the methods used to ensure that each requirement has been met. The Contractor shall describe its plans for acquiring and developing the required software to meet contract requirements. During the PDR, the Contractor shall present CSCI/HWCI-wide design decisions (i.e., decisions about the CSCI/HWCI's behavioral design and other decisions affecting the selection and design of the software components comprising the CSCI) defined and recorded for each CSCI/HWCI, and the traceability between design requirements and software/hardware requirements for each CSCI/HWCI. At the PDR, the Contractor shall describe the products, processes, methodologies, milestones, and measurements to be used in conducting software development activities. Overall technical program risks shall be reviewed on a technical, cost, and schedule basis.

As part of the PDR, the Contractor shall present and review the following documents with the Government:

- Deliverables, with overview of the following documents:

  - Draft Software Requirements Specification (SRS)

  - Draft Software Design Description (SDD)

  - Contractor Master Test Plan (CMTP)

  - Human Engineering Design Approach for Operators (HEDA-O)

  - Human Engineering Design Approach for Maintainers (HEDA-M)

  - Risk Assessment Report (RAR)

- System overview and software/hardware requirements definitions.

- Basic design approach for each configuration item, including CI to CI interfaces (HWCIs and CSCIs) and CI to external system interfaces.

- Functional flow, requirements allocation and schematic diagrams.

- CI development schedule.

- Preliminary processing algorithms description.

- Physical description including preliminary lists of materials, parts, manufacturing flow processes, and equipment layout.

- Power consumption goals.

- Preliminary power distribution and grounding design.

- Producibility analysis.

- Identification of design-driving/cost driving requirements.

- Security considerations including how interfaces will be protected, how system access will be controlled, availability and integrity of data.

- Vulnerability Assessment.

- Results of contractor system safety assessments and status of support to FAA.

- Reliability/maintainability/availability data such as analysis, including system, subsystem, and Line Replaceable Unit (LRU) component level reliability and maintainability predictions.

- Installation requirements for Air Traffic Control Tower (ATCT), vault, airfield equipment and cabling.

- Design concerns such as environmental control, electromagnetic compatibility/interoperability.

- Program and technical risks.

- Documentation status and availability.

            - PDR Acceptance Criteria

The PDR acceptance criteria are as follows.  To successfully complete the PDR, the Contractor shall:

- Define and baseline high-level software/hardware requirements for all CSCIs/HWCIs.

- Provide a traceability of the requirements baseline to the system requirements.

- Define high-level design requirements for each CSCI.

- Provide traceability of the design requirements to the CSCI/HWCI requirements.

- Document interfaces between computer software components within each CSCI and with external configuration items.

- Define test resources, test requirements and test schedule for the formal qualification testing of CSCIs under review.

- For each HWCI and CSCI, identify which requirements are satisfied by COTS, which requirements are already implemented but require modification, and which requirements require development.

- Present a preliminary design that shows how COTS, modified COTS, and new development will work together to satisfy the requirements baseline.

- Provide a draft SRS and SDD, and final CMTP, HEDA-O, HEDA-M and RAR  that are acceptable to the Government.

- Resolution, or an acceptable plan for resolution, of all action items.

##### Critical Design Review

The Contractor shall conduct a Critical Design Review (CDR). This review shall be conducted for each configuration item when detailed design is essentially complete.  The PDR must be approved by the Government before a CDR may be conducted, and all PDR action items must be closed prior to conducting the CDR, unless the Government has given permission to proceed.  The CDR is intended to ensure that detailed design solutions, as reflected in the draft CSCI design description, satisfy performance requirements established by the baselined requirements documents. The CDR is also performed for the purpose of establishing the integrity of computer program design at the detailed level prior to coding and testing.  The objective of this review is to establish an allocated baseline of low–level design requirements, which becomes an input to the coding process.

The purpose of this review will be to:

- Ensure that technical, performance, safety, security and human interface requirements are correctly reflected in design.

- Ensure that architectural means in software design are correctly identified as derived requirements.

- Confirm that all derived requirements are defined and have undergone the system safety assessment process.

- Review all change requests generated by the software design process.

- Ensure that the computer software interfaces are documented and are congruent with high-level interfaces.

- Ensure that test plans and test procedures provide complete coverage of software requirements.

- Determine that the detailed design of the configuration item under review satisfies the performance and engineering specialty requirements of the HWCI development specifications

- Establish the detailed design compatibility among the configuration item and other items of equipment, facilities, computer software and personnel.

- Assess configuration item risk areas (on a technical, cost, and schedule basis).

- Assess the results of the producibility analyses conducted on system hardware.

- Review the hardware product specifications.  For CSCIs, this review will focus on the determination of the acceptability of the detailed design, performance, and test characteristics of the design solution, and on the adequacy of the operation and support documents.

The CDR shall cover the detailed design of all Contractor-developed hardware and computer software configuration items. For items that are not Contractor-developed, the Contractor shall provide a detailed functional/physical description of the item, any additional results since the PDR of the analysis that verifies the item will meet the associated technical requirements, and a detailed description of the interfaces with other configuration items.

The Contractor shall provide further details than were presented at PDR of its plans for acquiring and developing the required hardware and software to meet contract requirements.  Overall technical program risks shall be reviewed on a technical, cost, and schedule basis.

As part of the CDR, the Contractor shall present and review in detail the following documents with the Government in detail:

- Deliverables, with overview of the following documents:

  - Final SSDD

  - Final SRS

  - Final SDD

  - Draft Software Product Specification (SPS)

  - Software Version Description(s) (SVD)

  - RAR

  - Draft Software Transition Plan (STP)

- System and CIs overview

- System interface and schematic diagrams

- All CI to CI interfaces

- Processing algorithm descriptions

- Design analysis results

- Results of contractor system safety assessments and status of support to FAA

- Information Security considerations and status of support to FAA

- Human Engineering Design

- Reliability and Maintainability Analysis and Predictions

- Data recording formats

- Operator controls and displays, and maintenance features overview including mockups and simulations

- Design concerns such as environmental control, electromagnetic compatibility/interoperability

- Program and technical risks

- Identification of design-driving/cost driving requirements

- Development and test schedule

- Installation requirements for ATCT, vault, cabling and airfield equipment.

- Producibility analysis

            - CDR Acceptance Criteria

To successfully complete CDR, the Contractor shall present objective evidence of meeting the following requirements:

- Update a traceability of the design requirements to the CSCI/HWCI requirements

- Present a detailed design that shows how COTS, modified COTS, and new development will work together to satisfy the requirements baseline

- Present sufficient test data, analysis and detail to show that requirements of the SOW, RWSL System Specification FAA-E-3001, and RWSL FLS Specification FAA-E-3002 will be met.

- Provide a draft SPS and STP, and final SSDD, SRS, SPD and RAR that are acceptable to the Government.

- Resolution, or an acceptable plan for resolution, of all action items

##### Final Design Review

The Contractor shall conduct a FDR. The FDR is intended to ensure that the first article configuration is ready for operational testing. As part of the FDR, the Contractor shall present and review in detail the following items with the Government:

- Deliverables, with overview of the following documents:

  - Final SPS

  - SVD

  - Final STP

  - Software User Manual (SUM)

- Final software configuration and hardware configuration of the system for Operational Test.

- The proposed software builds to resolve any open issues .

- List of open SPRs and closure plans.

- List of outstanding waivers and any resolution on waivers.

- List of outstanding deviations and closure plans.

- Results of test and closure plans for handling test failures.

- List of any remaining technical problems not covered in items 3 through 6.

- Results of the SAT testing and the Contractor Acceptance Inspection.

To successfully complete FDR, the Contractor shall present objective evidence of meeting the requirements of items 1 through 8 and Government approval of the documents in item 1 above.

#### System Safety Program

The Contractor shall establish and implement a System Safety Program in accordance with the FAA’s Safety Risk Management Guidance for System Acquisitions (SRMGSA). The Contractor shall develop a System Safety Program Plan (SSPP) in support of the program and provide the Government with the information, analysis and assessments to support the Government development of System Safety documentation (i.e., Preliminary Hazard Analysis (PHA), Sub-System Hazard Analysis (SSHA), (Safety Hazard Analysis (SHA), Operating and Support Hazard Analysis (O&SHA), and System Safety Assessment Report (SSAR)).

The Contractor shall identify a system safety point of contact to provide the engineering services described in this section.

Guidelines for the SSPP are contained in   DID SA-001 and Appendix B of the FAA’s Program Safety Plan Template.  In addition to these guidelines, the Contractor shall document their and their subcontractors’ software system safety and design assurance processes in the SSPP.  RTCA DO-278 Guidelines for Communication, Navigation, Surveillance, and Air Traffic Management (CNS/ATM) Systems Software Integrity Assurance may be used as guidance in describing software design assurance processes in the SSPP.  Furthermore, the Contractor may reference Standard Operating Procedures (SOPs), quality assurance processes, and/or any other standards for software system safety and design assurance employed by the prime Contractor and its subcontractors.

Safety tasks and activities shall be documented in the SSPP.  The FAA’s SRMGSA and the Safety Management System (SMS) Manual may be used for reference in preparing the SSPP.  The Contractor system safety point of contact shall complete FAA SMS training and act as a primary point of contact for all communication on safety-related issues.

The Contractor shall participate in the RWSL Safety Risk Management Panel (SRMP), as needed, to assist the FAA in developing safety hazard analyses, identifying risk mitigation strategies, and tracking the validation and verification status of system safety requirements.

The Contractor shall work collaboratively with the FAA to identify system safety hazards, prepare risk assessments, and recommend cost-effective risk mitigation strategies.  The Contractor shall prepare system functional analyses, fault tree analyses, reliability analyses, and other engineering analyses as required to identify and analyze system safety hazards.

The Contractor shall assist the FAA in preparing a SSHA.  The SSHA is accomplished once the system design is more mature and examines the interfaces between the sub-elements of the system.  The Contractor shall work collaboratively with the FAA to verify subsystem compliance with system safety requirements defined in the PHA, identify previously unidentified hazards associated with each subsystem, assess the risk of each subsystem design, and recommend cost-effective risk mitigation strategies.

The Contractor shall assist the FAA in preparing a SHA.  The purpose of the SHA is to perform a detailed safety risk assessment of a system; in particular the interfaces of that system with external systems and the interfaces between sub-systems.  The Contractor shall work collaboratively with the FAA to verify system compliance with safety requirements, identify previously unidentified hazards associated with the system interfaces, system functional faults, and system operation in the specified environment, assess the risk of the total system design, and identify existing safety hazard controls.

The Contractor shall assist the FAA in preparing an O&SHA.  The purpose of the O&SHA is to perform a detailed safety risk assessment of a system’s operational and support (e.g., maintenance and certification) procedures.  The Contractor shall work collaboratively with the FAA to (1) evaluate system operating and support procedures, (2) identify hazards associated with those procedures, (3) assess the risk associated with those hazards, (4) identify existing safety hazard controls, and (5) develop alternative controls and/or procedures to eliminate or control the hazards.

The Contractor shall assist the FAA in conducting safety reviews and preparing a final SSAR.  Safety reviews are periodically conducted in part to (1) collect and document supporting evidence that safety requirements are validated and verified and (2) recommend closure of identified hazards based on verification of safety requirements.  The SSAR summarizes the results of the safety risk management program, identifies all hazards and safety features in the program, and assesses system readiness based on the cumulative safety risk to the NAS.  The final safety review and associated SSAR will trace hazards from the PHA through the SHA to determine that hazards identified at various stages of the program have been adequately addressed and resolved.  The Contractor shall provide system requirements, design, test, training, and maintenance documentation needed to support each safety review.  When practical, safety reviews may be combined with TIMs, out-briefings following formal test conduct, and functional and physical configuration audits.

CDRL  SA01   System Safety Program Plan

#### Configuration Management Program

The Contractor shall use an internal Configuration Management (CM) system for the control of all elements of the RWSL system, including hardware, software and firmware, documentation, test equipment, space, physical media, and physical parts. The detailed requirements are included in these subparagraphs.

##### Contractor's Configuration Management Plan

The Contractor shall develop and submit a Configuration Management Plan (CMP). The CMP shall describe the Contractor’s CM Program including responsibilities, methodology and procedures for baseline identification, configuration control and audit and status accounting of software and hardware, documentation, support equipment, firmware, and data bases.  Configuration items shall be recommended using the guidelines provided in MIL-HDBK-61A, section 5.3.  Upon approval by the Government of the CMP, the Contractor shall use this plan to establish, implement and maintain a Configuration Management Program as specified herein, using FAA Order 1800.66 and MIL-HDBK-61A as guidance. This program shall be used for the control of all configuration items (e.g., software, physical media and parts, documentation, space, and power) and to maintain the integrity and traceability of its configuration. The Contractor shall specify a single authority to serve as a focal point for all CM related issues.

A Configuration Control Board (CCB) shall be established to review and approve any changes to the configuration of the system(s) and ensure that documentation associated with an approved change to the RWSL is updated to reflect the appropriate baseline. Affected documentation may include training material, courseware, and other Integrated Logistics Support documentation.  The Government shall be provided access to the process and be apprised of all proposed changes that affect the baseline system and/or documentation.  Proposed Changes that could affect the interface to an existing NAS system (e.g., ASDE-X) shall be raised to the Government’s CCB.

CDRL  CM01  Configuration Management Plan

##### Configuration Identification and Baseline

The Contractor shall use and maintain a definitive basis for control and status accounting for a Configuration Item (CI) throughout the RWSL system life cycle.  A CI is an aggregation of hardware and associated software/firmware that satisfies an end-user function and is designated by the Government for separate CM.  The Contractor shall use an internal developmental CM system. The documentation and repositories for this developmental configuration shall remain the Contractor's responsibility until the RWSL system is accepted by the Government. The Contractor shall use and maintain configuration baselines and their documentation. Incremental product baselines shall be permitted if proposed and approved via an Engineering Change Proposal (ECP) (3.1.9.2.4).

##### Part/Item Identification Numbers

The Contractor shall assign a discrete part/item identification number at the LRU level until such time as either an interim or final product baseline is established. At that point, parts shall be re-identified only upon Government approval whenever a non-interchangeable condition is created.  The Contractor shall assign a discrete part/item identification number to each software medium (e.g., magnetic tape, disk) containing RWSL system release- or build-type software executables. The medium thus identified shall be inclusive and contain all software segments, thereby providing easy identification of software releases after the product baseline is established.

##### FAA Type Designations

The Contractor shall request unique FAA equipment-type designations based upon an engineering and logistical review of structural or hardware items that could be identified by means of an FAA type number as soon as practical, but no later than nine months after contract award. FAA designations normally consist of two alpha characters in combination with five numerals (e.g., FA-85000) which shall be affixed to the unit on the nameplate in a location where it is readable, if practical, in accordance with FAA-G-2100H. FAA type designations shall not be assigned nor affixed to equipment that has been procured to specifications of other Government agencies or previous FAA procurements and that have already been assigned their own type designations or model numbers, unless a "major modification" is applied to the equipment based upon the RWSL system design. FAA type designations are applicable to developmental and COTS items. The FAA type designation nameplate shall not invalidate any warranty or equipment operation. Consideration shall be given to adhesive attachment of the FAA type number nameplate for COTS items.

##### Configuration Control

The Contractor shall maintain change control of the engineering design and production after Functional Configuration Audit/Physical Configuration Audit (FCA/PCA) in accordance with the guidance contained in MIL-HDBK-61A and the baseline requirements established at the PDR and CDR.

##### Engineering Change Proposal

The Contractor shall submit ECPs, in accordance with the guidance in MIL-HDBK-61A for approval prior to implementation and incorporation of a change to baselined requirements or design.  The Contractor shall submit, attached to each ECP, a change description for each document that would be changed if that ECP were approved.  Each change description shall include the exact proposed changes by citing the words/information to be changed in “From/To” format, or other means to easily distinguish proposed changes from approved documentation contents. (Proposed changes affecting systems or interfaces with systems external to RWSL (e.g., ASDE-X) shall be submitted to the Government for review and approval, as an NAS Change Proposals (NCP) in accordance with FAA Order 1800.66.)

The Contractor shall submit, with each ECP, as necessary, a Notice of Revision (NOR) to drawings that are not controlled by the ECP originator.  The NOR shall be developed in accordance with the guidance contained in MIL-HDBK-61A.

CDRL  CM02	  Engineering Change Proposal

            - System Enhancement ECPs

The Contractor shall provide the design, development, installation, checkout, test and validation of specific system enhancements as identified in requests by the Government.  The CO may request that the Contractor submit an ECP for Government identified system enhancements. Once the ECP is approved, the Contractor shall be responsible for full, development, implementation and documentation.  Some potential system enhancements are LED light fixtures in lieu of existing light fixtures, Runway Intersection Lights (RILs) and Final Approach Runway Occupancy Signal (FAROS) systems.

##### Requests for Deviation

The Contractor shall submit a request for deviation prior to departing from the approved baseline for a specific number of units and a specified period of time in accordance with the guidance contained in MIL-HDBK-61A. Deviations shall be submitted only for temporary departures from baseline, shall be for less than the production quantity of the item, and shall not involve changes to any RWSL baseline documentation.

CDRL  CM03	  Request for Deviation

##### Requests for Waiver

The Contractor shall submit waiver requests after the manufacture of a hardware or software item that contains a departure from known requirements and the Contractor proposes that the Government accept the item "as is". Waivers shall be submitted only for specifically identified items of less than the production quantity of that item, and shall not involve changes to any RWSL baseline documentation.

CDRL  CM04  Request for Waiver

##### Parts Substitution

The Contractor shall maintain parts substitution control.

##### Configuration Status Accounting

The Contractor shall generate Configuration Status Accounting Reports (CSAR’s) to ensure the configuration of development and implemented systems and that delivered documentation accurately describes the hardware configuration.  The Contractor shall record and report the following information:

- Current approved configuration documentation associated with each configuration item.

- Status of proposed engineering changes and requests for deviation or waiver from initiation to approval and status of implementation.

- Results of configuration audits including disposition of actions.

- Traceability of changes.

- Status of the implementation of changes at all locations.

- Identifiers of electronic documentation and software that have been delivered.

The Contractor shall use the CSAR’s to provide traceability of any change through the change control process.  The Contractor shall present status at PMR’s as updates occur.

CDRL  CM05  Configuration Status Accounting Report

##### System Problem Reporting

The Contractor shall use a system problem reporting system as part of the Contractor's CM program. The Contractor shall identify all system level discrepancies or problems identified during development, testing, production or installation and shall submit an SPR along with corrective action plans. During each PMR, the Contractor shall report on any outstanding discrepancies or problems, and the planned resolution. The Government will have the right to witness or review the documentation regarding the closure of any discrepancy item.

SPRs identified during testing shall be identified, along with correction plans and status in the Test Reports submitted to the Government.

CDRL  CM06  System Problem Report

##### Configuration Audits

##### Configuration Audit Plan

The Contractor shall support configuration audits using ANSI/EIA-649-A 2004: National Consensus Standard for Configuration Management as guidance. The Contractor shall be responsible for ensuring that subcontractors, vendors, and suppliers participate, as required.

CDRL  CM07  Configuration Audit Plan

##### Configuration Audit Summary Report

The Contractor shall prepare for and support configuration audits to be performed by the Government using MIL-HDBK-61A as guidance.  The Contractor shall be responsible for ensuring that subcontractors, vendors, and suppliers participate in Government configuration audits.  The Contractor shall provide facilities, access to documentation and equipment, security protocols, and shall ensure readiness for conduct of the audits.

The Contractor shall support a Functional Configuration Audit (FCA) of the RWSL system.  Each individual requirement, irrespective of the test guidance provided from any requirements or verification test matrix, may be audited.  The intent is to audit the attainment of all functional requirements and to validate their attainment during the FCA.

FCA entrance criteria shall include:

- Successful completion of developmental testing including closure of SPRs and incorporation of any approved ECPs and required retest.

- Approval of all DT test reports.

FCA exit criteria shall include validation by the Government that all requirements have been verified successfully.

The Contractor shall support a PCA of the RWSL system.  The Contractor shall provide support for subcontractor, vendor, and supplier PCAs for CIs developed for the RWSL procurement or modified for use by other than the RWSL prime Contractor.

PCA entrance criteria shall include:

- Fulfillment of FCA entrance criteria .

- Completion of requirements, design and product documentation including incorporation of all design changes and ECPs.

PCA exit criteria shall include:

- Verification by the Government that the documented product conforms with specified requirements.

- Verification by the Government that the documentation conforms to the physical RWSL system

- Successful completion of FCA .

- Government approval of as-built documentation to establish the RWSL Product Baseline.

CDRL  CM07  Functional and Physical Configuration Audit Summary Report

##### Data Management

The Contractor shall establish a data management program to maintain all contractually required and supporting documentation and correspondence related to schedule, development, design, test, implementation, management of equipment, and production documentation. Details of the data management process shall be documented in the CMP. This shall also include a process for monitoring, reporting, status accounting, and cross-matrixing of changes, additions, or deletions of data item deliverable contents.  All data items shall be configuration-managed by the Contractor. The Contractor shall control the generation, receipt, approval, storage, and delivery of subcontractor data. The Contractor shall also ensure that the subcontractor data meets requirements of the contract and is integrated into contract deliverables.

The Contractor shall use an automated status accounting system for data logging, recording, status reports, tracking, follow-up, record keeping, and audit trails for contract data items. Status shall be documented in the PSR.

#### Quality Management

The Contractor shall provide and maintain a documented quality system as a means of assuring compliance with the hardware and software requirements of the contract.  The contractor shall provide and maintain a quality control program which fulfills the requirements of ANSI/ISO/ASQ Q9001-2000 AMERICAN NATIONAL STANDARD, Quality management system – Requirements, and ISO/IEC 90003-2004, Software engineering – Guidelines for the Application of ISO 9001-2000 to the development of computer software.  A Quality System Plan (QSP) shall be prepared and submitted to the FAA for approval in accordance with CDRL QA01. The Contractor shall ensure quality control and assurance of services and supplies provided by all subcontractors and suppliers.  All spare parts shall be inspected and tested at the plant using the same procedures as the primary equipment components.

Third party registration to ISO standards is not required nor does such registration relieve the Offeror of the requirement of submitting a QSP.

CDRL  QA01 Quality System Plan

### Systems Engineering and Design Development

The Contractor shall execute a systems engineering program for the definition, development, verification, integration, and testing of the RWSL system requirements as allocated to RWSL processor and RWSL FLS CSCIs and HWCIs as defined by the RWSL system specifications. System engineering efforts shall consider all aspects of performance, quality, life cycle cost, maintainability, reliability, schedule, data processing reserves, and future growth requirements. Under this SOW, the Contractor shall perform hardware prototyping as necessary to support system design development, and shall designate and purchase, prior to CDR, long lead-time hardware items necessary to implement the system design.

The Contractor shall provide a system design for all the requirements in the RWSL System and RWSL FLS specifications and all applicable interfaces.  Where applicable, the Contractor shall follow DOT/FAA/CT03/05 (HF-STD-001) Human Factors Design Standard for Acquisition of Commercial-off-the-Shelf Subsystems, Non-Developmental Items, and Developmental Systems.  Specifically, Chapter 8 shall be used as guidance for Contractor designed Graphical User Interfaces (GUI) and user-computer interfaces.

The Contractor shall maintain effective control over the system engineering and design development process, including subcontract items and services, to ensure that cost, performance, and schedule are met, to provide early detection and resolution of problems, and to reduce risk. The Contractor shall specify a single authority who will serve as a Point of Contact (POC) for systems engineering issues.

#### Systems Engineering Documentation

The Contractor shall provide the engineering documents identified in the following sections.

#### System/Subsystem Design Description

The Contractor shall provide a SSDD for the entire RWSL System including the RWSL processor, RWSL FLS, and all applicable interfaces in accordance with DID-FAA-026-06.

CDRL  SE01	 System/Subsystem Design Description

#### Interface Control Documentation

The Contractor shall define and prepare a RWSL Interface Control Document (ICD) as a part of the systems engineering process and in accordance with CDRL HW01.  The Contractor shall design and develop the physical and functional interfaces in accordance with FAA-STD-025F.  The ICD shall meet the requirements as specified in the ASDE-X to RWSL Interface Requirements Document (IRD) and consistent with the Interface Design Document for the ASDE-X Program.  Interface controls shall be established, coordinated, and maintained for interface requirements and documents, and include applicable Contractor, subcontractor, and vendor contract items, and GFP/GFE computer programs, facilities, and data.  The Contractor shall submit the ICD to the Government for approval. The Contractor shall develop interface control documentation based on an analysis and decomposition of the requirements contained in the RWSL System Specification FAA-E-3001 and FAA-E-2942. The resultant ICD shall define and illustrate performance, physical, and functional characteristics in sufficient detail to ensure that all details on the interface can be determined solely from the information in the ICD.  The Contractor shall use Interface Control Document RWSL processor to Field Lighting System (FLS) Interface for the design of the interface between the RWSL processor and the FLS.  The Contractor shall participate in TIMs with FAA and Contractor personnel who support or develop the systems to which the RWSL System interfaces.

CDRL  HW01  Interface Control Document

#### Human Engineering Design

##### Objective

The objective of the HFE effort shall be to assure that the system design is consistent with the capabilities and limitations of air traffic control personnel (i.e., front-line manager or controller-in-charge) and maintainer in the operational environment.  Further, the HFE effort is intended to ensure the usability of the system from the user’s perspective and should also ensure that the implementation of RWSL does not negatively impact situational awareness or workload for air traffic control personnel or maintainer.

##### Planning and Execution

An adequately staffed Human Factors Engineering (HFE) effort shall be dedicated to and be an integral part of the analysis, design, and test process of the RWSL processor cab control panel, and maintenance interface. An HFE program shall be planned and implemented in accordance with MIL-HDBK-46855A, as applicable to the system's COTS or NDI program objectives, and human-in-the-loop performance requirements, characteristics and constraints. The Contractor shall develop an HFE program plan and document it as part of CDRL PM01, RWSL Program Management Plan.  The plan should detail how Human Factors (HF) analyses/studies, prototyping tradeoffs, user participation, and demonstrations will provide design solutions in a timely manner and support the achievement of the major RWSL milestones.  This document shall also describe the conduct of the HFE development, risk reduction activities, and Government and Contractor HFE participation in major design reviews. The HFE Program Plan should delineate a schedule of activities for the execution of the tasks contained in the Plan and the costs associated with the execution of the Plan. HFE should be an integral part of the RWSL program and contribute towards fielding a usable system

##### HFE Program Emphasis Areas

Within the context of the above considerations, the HFE program shall include, as a minimum, the following emphasis areas:

- Cab Control Panel: Effectiveness of user controls, legibility, and identification of system status.

- Cab Kill Switch: Effectiveness of user control, protection from accidental tripping.

- Maintenance Interface:  Suitability of maintenance hardware/software procedures to facilitate meeting system human-in-the-loop performance requirements including accomplishing the following:

  - Maintenance tasks related to fault isolation, system optimization, manipulation, access, removal, replacement, and repair.

  - Manual operations involving pulling, pushing, lifting, or carrying.

  - Compatibility of tools with tasks, hand-wear, and environment..

- Test and Evaluation: HFE requirements shall be integrated into system test and evaluation to demonstrate the capability of the cab control panel, interface with RWSL (e.g., RELs and THLs), and maintenance interface to required system performance characteristics (i.e., system requirements for maintenance and controller interfaces,  in accordance with DOT/FAA/CT03/05 (HF-STD-001), Human Factors Design Standard for Acquisition of Commercial-off-the-Shelf Subsystems, Non-Developmental Items, and Developmental Systems).  HFE tests may be integrated into other system tests.  However, dedicated HFE tests shall be performed when validation of critical task accomplishments is necessary.

No more than two (2) user working groups shall be convened at the vendor facility to address HF design specifications as applicable.

HFE reviews shall be conducted as a part of all design reviews. Each HFE review shall cover at least the following:

- HFE Program Accomplishments.

- Principal Human Performance Requirements: System operation and maintenance requirements which depend on human performance shall be summarized.

- Human Engineering Design: Compliance of controller and maintenance interfaces with engineering design requirements shall be presented.

The Contractor shall provide a Human Engineering Design Approach Document for the Operator and for the Maintainer in accordance with CDRLs HE01 and HE02.

CDRL  HE01  Human Engineering Design Approach Document – Operator

CDRL  HE02  Human Engineering Design Approach Document – Maintainer

#### Engineering Services

The Government may choose to exercise an option for engineering services at any time during the life of the contract.  The Engineering Services may include engineering analysis, requirements development and analysis, engineering design and tradeoff analysis, design and engineering of changes, including cost-benefit and risk analysis, safety, human factors and security analysis, or other engineering services.

### Software Development

The Contractor shall design, code, integrate, test, and deliver the RWSL processor and FLS software required to meet the requirements of the RWSL System Specification FAA-E-3001 and the FLS Specification FAA-E-3002.  The Contractor shall document software developed under this contract as required in the following sub-paragraphs. The Government Furnished Information (GFI) software is provided as an example of an implementation that has proven effective in prototype trials in an operational setting. However, use of this software is not a requirement of this SOW and does not relieve the Contractor of responsibility for meeting the requirements in this SOW or the RWSL specifications. The Contractor may choose to use the same methods in the GFI software or may choose his own.

#### System Software Design

Where RWSL requirements cannot be met by using commercially offered software packages, the Contractor shall develop the required computer software. The following guidelines shall apply:

- Firmware (software that resides on programmable memory) shall be treated as software.

- Commercially available operating systems used in the RWSL shall be Portable Operating System Interface (POSIX) compliant and be the most recent release or update.

- RWSL software shall be in accordance with the operating system, COTS application manufacturer recommendations, and applicable industry standards.

- Updates and revisions will be implemented by the Contractor as they occur until the test readiness review. If the Contractor chooses to modify commercial software, he shall supply the justification for the change to the Government. The justification shall state the method of documentation. All changes shall require Government approval.

For standard commercial product software employed to satisfy RWSL system requirements, corresponding commercial documentation, licensing agreements, and usage limitations shall be submitted to the Government for approval. The Contractor shall ensure that the Government has unrestricted access to additional copies of commercial software documentation.

The Government shall have ownership and modification rights to all source code of all software and firmware developed to satisfy the requirements of this SOW and RWSL system specifications.

##### Software Documentation

The Contractor shall provide the software documentation for requirements allocation, design, test, quality assurance, delivery, installation, operation, maintenance, and support of each computer resource CI and CSCI. The Contractor shall submit software documentation to the Government for review and approval.

The following sections describe the required software documentation to be provided by the Contractor.

##### Software Development Plan

The SDP is a tool for documenting the management processes for software development, the methods to be used, the approach to be followed for each activity, and project schedules, organization, and resources. The SDP describes how to conduct the RWSL processor and FLS software development effort.

The Contractor shall prepare, use, maintain, and update the SDP throughout the performance of the contract. The SDP shall be developed in accordance with DID-SW001 and is subject to Government approval.

The SDP shall not relieve the Contractor from complying with all other requirements of the RWSL specifications and this SOW.  The Contractor shall ensure that software products developed by subcontractors are in accordance with all prime contract requirements. The Contractor shall specify the means by which this is to be accomplished in the SDP.

CDRL  SW01  Software Development Plan

##### Software Requirements Specification

The purpose of the SRS is to provide a complete allocation matrix of all software requirements (explicit and derived) from the RWSL System Specification FAA-E-3001, RWSL FLS Specification FAA-E-3002, and SSDD.

The SRS shall be prepared in accordance with DID SW-002 and is subject to Government approval.

Following delivery to the Government, the SRS shall be subject to configuration control.

CDRL  SW02  Software Requirements Specification

##### Software Design Description

The SDD shall be prepared in accordance with DID SW-003 and is subject to Government approval.  Upon completion of the PCA, the SDD, as part of the SPS, shall be entered into the product baseline for the CSCI. Subsequent to approval, the SDD shall be subject to formal configuration control and shall not be changed without prior Government approval.

CDRL  SW03  Software Design Description

##### Software Version Description

The Contractor shall provide a SVD for each CSCI. The SVD shall be used by the Contractor to release CSCI versions to the Government. The SVD shall accompany the shipment of each CSCI to the Government. The Contractor shall use and maintain a system that ensures that each CSCI change is accounted for, following approval by the Government. The SVD shall be updated as required to describe all changes to any CSCI version delivered subsequent to the initial CSCI delivery.  The SVD shall be prepared in accordance with DID SW-004 and is subject to Government approval.

CDRL  SW04  Software Version Description

##### Software User Manual

The Contractor shall provide one SUM for the RWSL program. The Software User Manual shall provide user personnel with instructions sufficient to utilize the RWSL system for its intended purpose. Functions described shall include, but are not limited to, operations, log-in, and operator switch settings/changes. The SUM shall be prepared in accordance with DID SW-005 and is subject to Government approval.

CDRL  SW05  Software User Manual

##### Software Product Specifications

The Contractor shall prepare and provide a SPS for each CSCI.  The SPS shall address all COTS/Non-Developmental Item (NDI) products used in the CSCI.  The SPS shall include the design documents, software listings, and source code for software and firmware. Upon Government approval, the SPS shall establish the product baseline for the delivered CSCI.  The SPS shall be prepared in accordance with DID SW-006 and is subject to Government approval.

CDRL  SW06   Software Product Specification

##### Interface Design Document

The Contractor shall provide a detailed design of the Hardware Configuration Item to CSCI interfaces and the CSCI to CSCI interfaces. The Interface Design Document shall be used to specify the design for those interfaces. Following delivery to the Government, the Interface Design Document shall be subject to configuration control.  The IDDs shall be prepared in accordance with DID HW-002 and are subject to Government approval.

CDRL  HW02   Interface Design Description

##### Development of Non-Operational Software

The Contractor shall provide any non-operational software such as simulation software, test software and development/maintenance tools with documentation. This includes software used to test operational system software via system level simulations and developmental software used to create operational software and tools for maintaining operational software. The development of non-operational software excludes licensed commercially available software. In these cases, the Contractor will need to supply a description of the software, manufacturer, and version.  Non-operational software that is required for development, installation, test, support, maintenance or optimization of the RWSL system shall be subject to validation.

Any programs developed on this software shall also be deliverables.

##### Hardware Identification and Selection

The Contractor shall provide a detailed design of the RWSL hardware with requirements traceability to the RWSL system and FLS specifications. This design and development shall be in accordance with, and meet the requirements of each. The Contractor shall make maximum use of readily available COTS hardware systems which satisfy the functional and performance requirements of the specification. Hardware subsystems, assemblies, or components which meet the requirements of the specification shall be procured according to applicable FAA regulations and orders. COTS hardware shall remain consistent across all sites (same manufacturer, type, and hardware family) and shall remain consistent upon completion of any hardware upgrade of RWSL equipment/design. During the engineering design process, the Contractor may propose, for Government review and approval, a new configuration item, developmental Line Replaceable Unit (LRU), or modified COTS/NDI if it is justified as best value on a cost/benefit basis. The Contractor shall document the interrelationships between the system/subsystem/equipment drawings in an Engineering Drawing Tree, CDRL TD01, as defined in Section 3.6.6.1, Technical Drawings and Associated Lists. The documentation of the selected COTS equipment design shall be as defined in Section 3.6.6.4, COTS Manuals and Documentation and MIL-HDBK-454B, Requirement 7.  The interchangeability shall be applied at the unit level.

##### Interchangeability

All like components of each system shall be interchangeable between systems, and identical units within each system shall be interchangeable.  Identical components shall be identified with identical part numbers and unlike parts shall not have the same part number.  This requirement does not prevent the readjustment or calibration of exchanged modules nor does it prohibit exchange of control panels due to the runway identification number.

##### Access to System Development Environment

The Contractor shall provide the FAA full and timely access to the RWSL system development environment. This shall include, but not be limited to, access to data, documentation, draft CDRLs, source code, and the physical plant. FAA access shall include access for FAA employees and FAA contractor support personnel. FAA access shall also include FAA Training Academy personnel in support of their development of Technical Operations Technical Operations training.  To facilitate such access, the Contractor shall:

- Provide the FAA with weekly physical access of not less than forty (40) hours.

- Provide access to contract deliverables prior to delivery.

- Provide the FAA with electronic access to data, documentation, and RWSL processor and FLS development environment elements, other than physical plant facilities.

- Propose an alternative method of providing access, where remote electronic access is not feasible, subject to acceptance and approval by the Government.

- Provide timely notification to the Government of any adverse impact to the development effort arising from the cooperation and access afforded to the FAA as specified herein.

- Provide password protected Internet access to documents selected by the Government.

##### Reliability Program

The Contractor shall establish a reliability program in accordance with FAA RMA Handbook 06A and MIL-HDBK-781A to ensure that the reliability requirements of the RWSL system and this SOW are satisfied. The Contractor's overall methodology for conducting a reliability program shall be documented in a Reliability Program/Demonstration Plan in accordance with FAA-HDBK-06A and MIL-HDBK-781A.  The Contractor shall propose a Reliability Growth Program consistent with FAA-HDBK-06A.  For the limited production systems, the Contractor shall be responsible for the following:

- Performing reliability predictions in accordance with MIL-HDBK-781A and document these in the Reliability Program/Demonstration Plan.  Changes in predicted numbers resulting from development and test activities shall be calculated and shall be presented at PMRs and TIMs.

- Tracking failed hardware (including receiving failed equipment from the fielded sites and returning them to the equipment manufacturers for repair/replacement) and software. Part of this effort shall include using the associated failure data as part of the Contractor's reliability program and for calculating reliability growth.

- Documenting all failures (hardware and software) in PTRs and presenting these to the Government’s Reliability Review Board for decision based upon the FAA-HDBK-06A.

- Analyzing failures, presenting failure data and discussing engineering remedies/actions at TIMs and PMRs.

- Aggressively correcting all PTRs to prevent recurrence and to meet Reliability requirements of this Contract.

- Documenting the overall methodology for conducting a reliability program, including the process(es) for tracking failed hardware, using the failure data for reliability purposes in a Reliability Program/Demonstration Plan and conducting a successful Reliability Growth Program.

CDRL  RP01 	 Reliability Program/Demonstration Plan

##### Maintainability Program

The Contractor shall establish and demonstrate a maintainability program to ensure that the maintainability requirements of the RWSL system specifications and this SOW are satisfied. The Contractor's overall methodology for conducting a maintainability program shall be documented in a Maintainability Program/Demonstration Plan in accordance with MIL-HDBK-470A. The Contractor shall develop maintainability predictions in accordance with the guidance contained in MIL-HDBK-470A, Appendix D, Method B, and submit them in the Maintainability Program/Demonstration Plan.  Changes in predicted numbers resulting from development and test activities shall be calculated and shall be presented at PMRs and TIMs.

CDRL  MP01	  Maintainability Program/Demonstration Plan

##### Electromagnetic Interference and Susceptibility

The Contractor shall design and construct the system to meet the interference and susceptibility requirements of the RWSL specifications. If a deficiency exists between the system and the requirements, the Contractor shall correct these deficiencies. The RWSL FLS shall not cause interference to, or be susceptible to, interference from other airfield lighting systems.

##### Security Program

The Contractor shall establish and implement a security program in accordance with FAA Order 1370.82A, FAA Order 1600.72A, FAA Order 1600.75, and the RWSL System Specification FAA-E-3001.  The Contractor shall prepare an RWSL Security Plan, CDRL SE02, documenting the applicable security features and their proposed implementation for the RWSL.  The Security Plan shall describe the information necessary to support the FAA Security Certification and Authorization Package (SCAP) process.  The Security Plan shall detail the security risk assessment of all NDI software and commercial item hardware to establish the vulnerabilities of the system.  Upon approval of the plan by the FAA, the Contractor shall conduct the contract effort in accordance with the provisions in the approved plan, including support to the Government in development of the SCAP.

CDRL  SE02  Security Plan

##### Personnel Security

The Contractor shall comply with the requirements of FAA Order 1600.1E in all personnel security matters.  The Contractor shall submit the security forms for all personnel so identified to the Government for processing in accordance with FAA Order 1600.1E.

##### Information Security

The Contractor shall comply with the requirements of FAA Order 1600.75 in the handling of all sensitive unclassified information (SUI) received from the Government or developed by the Contractor.

##### Physical Security

The Contractor shall comply with the requirements of FAA Order 1600.6E and FAA Order 1600.69B in all physical security matters.

### System Test and Evaluation

The Contractor shall develop and submit a Contractor’s Master Test Plan (CMTP) to the Government for approval.  The CMTP shall provide the plan for the conduct and documentation of an integrated test and evaluation program in accordance with the SOW and for the testing of all requirements in the RWSL System Specification FAA-E-3001, RWSL FLS Specification FAA-E-3002, and this SOW.  The Contractor shall designate a Contractor Test Director to oversee the planning, conduct, and documentation of an integrated test and evaluation program in accordance with this SOW and the Government approved CMTP using the Acquisition Management System Test & Evaluation Process Guidelines and the attached Data Item Descriptions as guidance. The CMTP shall serve as the overall test philosophy, definition, and control document for the Contractor’s RWSL Test and Evaluation Program. The test program shall verify that the entire RWSL system and its support elements meet the physical, functional, interface, and performance requirements as stated in the RWSL System Specification and the RWSL FLS Specification.

The Contractor shall develop test schedules, test plans (TE02), and test procedures (TE03) as required by the CDRLs of this SOW.  The Contractor shall conduct tests and generate test reports (TE04) as required by this SOW.  The Contractor shall get approval by the Government for each level of Contractor test documentation prior to the submittal of the next lower test documentation or test conduct. The CMTP shall be approved by the Government prior to lower level Test Plan submittals.  Each Test Plan shall be approved by the Government prior to the submittal of associated Draft Test Procedures.  Draft Test Procedures shall be approved by the Government prior to the conduct of the associated Development Test and Evaluation (DT&E) Preliminary Qualification Test (PQT).  The completion of the PQT and the final Test Procedures shall be approved by the Government prior to the conduct of the associated DT&E Formal Qualification Test (FQT).  The completion of the FQT must be approved by the Government prior to the submittal of the associated Test Report. The Contractor shall submit separate test documents (test plans, procedures and reports) for the Factory Development Qualification Tests (FDQT), Site Development Qualification Tests (SDQT), 1st Article Tests, Factory Acceptance Tests (FAT), and Site Acceptance Tests (SAT).

CDRL  TE01  Contractor Master Test Plan

CDRL  TE02  Test Plan

CDRL  TE03  Test Procedure

CDRL  TE04  Test Report

#### Development Test and Evaluation

The Contractor shall perform DT&E. The purpose of DT&E shall be primarily to assist in the engineering design, development, and implementation process by determining incrementally the degree to which functional engineering specifications are attained.  DT&E shall consist of FDQT, 1st Article Tests, and SDQT.

##### Test and Evaluation Management

The Contractor shall furnish equipment, space, and personnel required to perform Contractor-conducted factory tests. The Contractor shall coordinate testing to be performed and ensure that there is minimal redundancy of effort or data. The Contractor shall assign a Test Manager to oversee the Contractor’s responsibility for integration, control, oversight, and coordination of all Contractor and Subcontractor testing, and support for Government site tests.

Contractor-proposed test tools, documentation, and test-support hardware and software shall be approved by the Government prior to the start of testing. The Contractor shall conduct Test Issue Resolution Process meetings in accordance with CDRLs PM 10 and PM11 with the Government as part of the approval process to review comments and to finalize all test plan and procedure approaches, to meet the CDRL requirements of this SOW and the specifications. The Contractor shall integrate test schedules into the overall RWSL program schedule. The Contractor shall notify the Government of testing schedules at least five (5) working days prior to the start of each test. The Government reserves the right to witness, on a non-interfering basis, Contractor testing during any test phase or level.

The Government may require, and the Contractor shall cooperate with and perform, in-process quality inspections at any time in a manner not disruptive to Contractor fabrication and assembly operations.

##### Configuration Management Inspections

In addition to its own in-house configuration management, the Contractor shall cooperatively allow and perform random configuration management inspections at the determination of the Government.  These inspections shall not require the preparation of formal plans or procedures. The Contractor shall be prepared to show internal configuration management documentation at these inspections.  Any results of non-compliance or unexplainable anomalies shall be entered into the Contractor’s problem reporting system as a SPR, and shall be formally tracked until resolution.

##### Test Support

The Contractor shall provide all required support throughout the entire test period as defined in the CMTP and approved by the Government, including any Government testing.  This shall include support continuing through RWSL baseline and field acceptance for all Contractor equipment.

##### Test Equipment

The Contractor shall be responsible for assuring that all test equipment required for the successful completion of testing is available, on time, properly calibrated, and fully operational to support tests. Use of Government test equipment may be permitted where Government test equipment is (1) on site, (2) available, and (3) meets specified test equipment requirements. Test equipment used by the Contractor during Factory or Site Tests that is COTS shall not be modified without prior written approval of the FAA. Test equipment shall operate in the manner specified by the test equipment manufacturer. Ancillary equipment required by the Contractor for test purposes shall be furnished by the Contractor for the duration of the tests and approved by the Government. The Government Test Director may require the Contractor to re-calibrate any test equipment provided by the Contractor to be used in the test program due to either of the following:

- The test equipment is removed from the test set-up for unrelated purposes.

- The test equipment fails, is damaged, or appears to be operating in a faulty manner based on Government evaluation of test results.

##### Verification Requirements Traceability Matrix

The CMTP shall contain a Verification Requirements Traceability Matrix (VRTM) as an attachment for Government approval. Each requirement from RWSL System Specification FAA-E-3001, FLS Specification FAA-E-3002, and this SOW shall be specifically addressed in the VRTM and correlated to a verification method from the methods listed below:

R (Design Review) - Requirements verification by design review shall determine requirements compliance by review and approval of a specific design data through the presentation of a Design Review Data Package (TE05) at formal reviews.

I (Inspection) - Requirements Verification by inspection shall determine requirements compliance through visual observation, mechanical measurements of equipment, or examination of or comparison to engineering documents and standards in accordance with approved inspection procedures, data collection, and pre-defined success criteria.

A (Analysis) - Requirements verification by analysis shall determine requirements compliance by comparing the applicable aspects of the subsystem design with known, established, and certified (or certifiable) technical data, scientific/technical principles, procedures and/or practices which validate the requirement in accordance with approved analysis procedures and pre-defined success criteria through the submittal of an Analysis Report (TE06).

D (Demonstration) - Requirements verification by demonstration shall determine requirements compliance by the observation of the qualitative determination of properties of an end-item or unit and requiring procedures and pre-defined success criteria. Software demonstration is an activity that is limited to a readily observable functional operation to determine compliance with requirements (e.g., the proper response at a site as a result of a specified interrogation or command to be processed by the program).

T (Test) - Requirements verification by test shall determine requirements compliance by the measurement of the subsystem performance under specific configuration and load conditions with controlled application of known input stimuli. This results in the measurement of quantitative data which may be subject to reduction and analysis to validate the results against pre-defined success criteria, and which requires the employment of procedures and data collection.

TD (Test with Data) - Requirements verification by test with data shall determine requirements compliance by means of an attachment to the CMTP that supplies data as obtained from prior testing. At a minimum, the data shall consist of the “as run” test procedure, a test report, and documentation of the “as run” test configuration. Data obtained from prior testing must conform to the following conditions:

- The data was obtained from an equivalent system that matches the baseline for the RWSL test program (this is determined by the Government examination of system configuration data for the baseline system and the system from which the data was obtained).

- The data was verified by an independent agent or Government (the Government will determine if the agent was independent based on verification of substantiation provided by the Contractor).

- The data is sufficient to fully satisfy the requirements of the contract (the Government will determine if the data is sufficient).

- Those RWSL requirements, which are to be verified by prior test data, shall be clearly indicated in the CMTP and the VRTM.  Any use of the Test with Data verification method is subject to Government approval.

Each requirement from the RWSL System Specification FAA-E-3001, the RWSL FLS specification FAA-E-3002, and this SOW shall be specifically addressed in the VRTM and correlated to at least one system configuration on which the requirement is to be verified from the configurations listed below.  The configuration must fully test the requirement:

- Full RWSL System

- FS (Full System) – Full RWSL Processor Subsystem, Full Field Lighting Subsystem

- Partial RWSL System

- FR - Full RWSL Processor Subsystem

- PR - Partial RWSL Processor Subsystem

- FF - Full Field Lighting Subsystem

- PF - Partial Field Lighting Subsystem

Each requirement from the RWSL System Specification FAA-E-3001, the FLS Specification FAA-E-3002, and this SOW shall also be specifically addressed in the VRTM and correlated to at least one verification method with which it will be verified.  For each requirement, the Contractor shall also indicate in which test plans the requirement will be satisfied. Individual test plans, procedures, and reports shall clearly indicate where their particular VRTM requirements are being addressed, executed, and met in the proposed test sections therein. Separate test plans and test procedures may be submitted for individual tests to allow those tests to progress prior to the submittal and approval of the test plans and test procedures for other tests.

The Contractor shall submit the final CMTP to the Government for review and approval. As part of this final CMTP, and in accordance with CMTP requirements, the Contractor shall perform a final mapping of the VRTM.  Post-“final mapping” changes after Government approval of the CMTP shall be submitted in change pages for approval by the Government.

CDRL  TE05  Design Review Data Package

CDRL  TE06  Analysis Report

##### Test Conduct

Test conduct shall be conducted by Contractor test personnel assigned by the Contractor’s Test Director and witnessed by personnel assigned by the Government Test Director.

            - Preliminary Qualification Test

The Contractor shall conduct a Preliminary Qualification Test (PQT) or “dry run” for each test event.  The Contractor shall provide the Government five (5) days advance notice of all PQT activities as defined in the CMTP.  The Government reserves the right to witness the PQTs.  Draft test procedures approved by the Government shall be used for the PQT.  The draft test procedures may be red-lined during the PQT to necessitate test completion and accuracy.  For inspections, demonstrations, and tests, a PQT is complete when the associated test procedures have been run in their entirety in a repeatable manner (legible redlines) and all failures encountered have been documented with SPRs.  For analysis, the PQT is complete when a walkthrough of the draft analysis report verifies that the forthcoming analysis will be sufficient to verify the requirement’s success criteria.  The results of a fully successful (no failures encountered, minimal red-lines required) Government-witnessed PQT may, with the approval of the Government, be used in place of a formal FQT.

Following the completion of each test, the Contractor shall present and discuss SPRs, test log entries, and test results with the Government representatives at a test debriefing, but no formal decision shall be made by the Government at the debriefing relative to the formal satisfaction of test requirements.  The Contractor shall publish test debriefing minutes (CDRL PM11).

Formal Qualification Test

The Contractor shall conduct a Formal Qualification Test (FQT) for each test event. All requirements (in accordance with the approved CMTP VRTM) shall be verified during each formal test event.  All formal test events require five (5) days advance notice to the Government by Notification of Test Letter (CDRL TE07) that a formal test event is scheduled.  Final Test Procedures approved by the Government shall be used for the FQT.  The final test procedures may only be minimally red-lined during the FQT to necessitate test completion and accuracy.

Prior to a formal test event, the article under test shall be described and the complete configuration of the article shall be provided to the Government for inspection and concurrence, such that the configuration is adequately documented.  Test data and test logs (CDRL TE08) shall be collected and authenticated as part of the RWSL Test Program.

All formal testing shall be conducted on test articles, which exactly conform to the configurations documented in the associated test plans and procedures.  These tests shall employ only the baselined software image as resident and operational.  In the case of multiple First Articles, the hardware and software configurations under test shall be identical with the exception of application-specific configuration differences (e.g., number of lights).

All test tools shall be certified by demonstration and/or inspection prior to test, and the results validated by the Government prior to use in any formal test event.

Each FQT shall be conducted on a pass/fail basis.  The pass/fail success criteria for each requirement shall provide a clear and unambiguous objective for the determination of requirement verification.  If the requirement has been modified by deviation, the success criteria shall be updated appropriately.  A requirement verified by test, inspection, or demonstration shall be considered passed when the test has been executed without aborts or errors (unless they are part of the test procedure) and when expected results and all analysis performed verify correct operation in accordance with the specified success criteria.  A requirement verified by analysis shall be considered passed when an analysis which verifies the requirement’s success criteria and has been completed and approved by the Government.  A requirement for which a waiver has been submitted shall be considered completed with no pass or fail status.

Each FQT shall be capable of being repeated to achieve the same results.  Discrepancies between actual and expected test results shall be explained by analysis of test data.  Each FQT shall not be considered successfully completed until:

- The Contractor has received written Government approval of the final test procedures.

- The Government representative has witnessed the actual test.

- The test has been conducted to the Government’s satisfaction in accordance with the Government approved plans and procedures.

- The test report (CDRL TE04), including all data analysis, test results, and corrective actions, has been approved by the Government.

- All associated waivers and deviations have been approved by the Government.

Following the completion of each test, the Contractor shall present and discuss SPRs, test log entries, and test results with the Government representatives at a test debriefing, but no formal decision shall be made by the Government at the debriefing relative to the formal satisfaction of test requirements.  The Contractor shall publish test debriefing minutes (CDRL PM11).

CDRL  TE07  Notification of Test Letter

CDRL  TE08  Test Log

##### Factory Development Qualification Tests

The Contractor shall perform Factory Development Qualification Tests (FDQT) to verify that the implemented design meets functional and performance requirements of the RWSL system and FLS specifications and this SOW.

##### REL/THL Algorithm Test

The Government will provide recorded ASDE-X surveillance log data and corresponding airborne departure timing data to be used to test requirements from section 3.3.1 of the RWSL System Specification.

##### Parameter Test

The Contractor shall test all parameters developed from section 3.1.2 and 3.1.3 of the RWSL System Specification to verify all parameters perform as designed.  The Contractor shall test in as an efficient manner as possible, using a minimum of three parameters per variable, including an out of range parameter if pertinent.

##### Capacity and Throughput Test

System capacity and throughput tests shall be conducted using Government provided scenarios (i.e., ASDE-X log data) to test the system’s throughput while the system is operating under capacity load conditions.

##### Human Factors Test

Human factors requirements that apply to the cab control panel shall be verified by design review.  Human factors requirements that apply to the maintenance interface shall be verified during the maintainability demonstration.  Further human factors test and evaluation will be conducted by the government during the Government operational test.

##### First Article Tests

##### Inspection Test

The First Article Inspections shall be conducted on the First Article unit, module, or assembly. The mechanical inspection shall include a visual examination to determine compliance with the applicable specification requirements defined in FAA-G-2100H for strength and rigidity, accessibility, types of components and materials, choice of insulation, layout of chassis, panels and wiring, finishes, workmanship, and similar attributes.  The inspections as defined in the CMTP VRTM shall be conducted, in accordance with approved (and preliminary qualification test) inspection plans and procedures.

##### Electromagnetic Interference Test

The Contractor shall show compliance for COTS equipment by showing that all such COTS equipment meets the requirements of FAA-G-2100H and all appropriate Federal Communications Commission (FCC) authorizations as defined in 47CFR 2 and 47CFR 15 of the FCC Rules and Regulations. For equipment chosen for use in the RWSL system that has not been certified to meet Electromagnetic Interference (EMI )specified requirements through FAA advisory circulars or FCC authorizations, the Contractor shall perform EMI tests and provide data showing that the equipment meets EMI requirements.

##### Environmental Test

The Contractor shall show compliance for all designed and COTS equipments by testing in accordance with the requirements of FAA-G-2100H.

The Contractor shall show compliance with environmental requirements by supplying manufacturer specifications for COTS equipment as stated in section FAA-G-2100H.  If COTS equipment is placed in an enclosed cabinet, then said equipment/cabinet must be tested to comply with the requirements FAA-G-2100H. For equipment chosen for use in the RWSL system that has not been certified to meet current environmental requirements stated in the FAA-G-2100H, the Contractor shall perform environmental tests and provide data showing that the equipment meets environmental requirements.

##### Reliability, Maintainability, and Availability Analysis

Reliability, Maintainability, and Availability (RMA) analysis shall be performed in accordance with sections 3.3.1.13 and 3.3.1.14 of this document.  Maintainability tests shall include nondestructive fault insertion for each LRU to demonstrate BIT compliance.  Removal and replacement of each LRU shall be conducted to verify applicable requirements from FAA-G-2100H.  With Government approval large LRU removal and replacement may be conducted by paper walk through.

For RMA testing, individual light bulbs shall be considered consumables. Individual light failures shall not be considered critical failures as long as the resultant light failure(s) do not cause the RWSL system to exceed the light timing requirements. Any failure that causes the RWSL system to exceed light timing requirements shall be considered a critical failure. For the RMA analysis it can be assumed that individual light failures will be repaired within 45 days. The Contractor shall estimate the maximum number and type of light failures that might occur in 45 days.

            - Reliability Development Growth Test (RDGT)

The Contractor shall conduct a RDGT through the life of the contract. This test shall be conducted on all equipment following site acceptance. The Contractor shall maintain a chronological log throughout the RDGT. The RDGT log shall provide the dates and times of all significant events. At a minimum these events shall include:

- Power on and off times of each system or subsystem.

- A running total of the number of RDGT hours for the Subsystem/system.

- Start and Stop times of testing, all interruptions, including all failure details, any unusual conditions in the equipment under test, auxiliary equipment, source power, or environment, any repairs or adjustments made as well as parts replaced.

- Start and Stop times of any simulators.

The RDGT shall be conducted to identify, analyze, and resolve system reliability problems over the life of the contract. During the RDGT, all failures, including critical, non-critical, relevant, and non-relevant, shall be analyzed and corrective action proposed by the Contractor. Failure relevance shall be determined in accordance with Section 3.4.1.3.4.2.  Each failure shall be recorded and analyzed and all relevant failures shall be corrected by repair and/or design or manufacturing changes to cure the identified cause of the failure.  The Contractor shall be required to correct all relevant failures in accordance with the corrective action proposed by the Contractor and approved by the Government.  The Government will approve repair and/or design or manufacturing changes to correct all relevant failures.  The Government will witness each time the system is maintained to assure that each failure is recorded and that preventive maintenance, corrective maintenance, and incorporation of design and/or manufacturing improvements are done in accordance with prescribed maintenance procedures or approved system improvements.

All systems delivered to the Government shall incorporate all approved design and/or manufacturing improvements that result from the RDGT.

As part of the RDGT, the Contractor shall collect light bulb usage and failure rate data. This data shall be compiled to determine the average number of hours a bulb lasts based on the number of hours from installation and the number of light illumination hours. This data shall be compiled separately for REL fixtures and THL fixtures and reported for each airport individually.

Failure Relevance Definitions

A relevant failure is a failure, which can be attributed, after failure analysis, to any of the following:

  - Any maintenance or software action required to maintain specified system performance.

  - Failure of the system to reconfigure automatically within the specified channel switchover and restoration time so as to maintain specified system performance.

  - Hardware or software/firmware design defects.

  - Manufacturing process, material or workmanship defects.

  - Physical or functional deterioration (such as wear out, fatigue, or tolerance degradation).

  - Failure of parts of known limited life occurring prior to the end of the stipulated period.

  - Intermittent failure.

  - Failures due to incorrect instruction in the technical manuals.

  - Any other failure that is not listed as a non-relevant failure.

A non-relevant failure is a failure, which can be attributed, after failure analysis, to any of the following:

  - Damage resulting from improper installation.

  - Failure of test instrumentation or monitoring equipment that is external to the test equipment under test.

  - Interrupted operation caused by external power failures.

  - Equipment failures caused by externally applied over-stressed conditions in excess of the specified requirements.

  - Damage resulting from accident or mishandling by personnel performing the RDGT.

  - Failures due to procedural errors by technicians or operators.

  - Dependent failure (i.e., a failure of a part(s) as a direct result of a failure of another part within the same LRU).  The vendor shall determine that the failure(s) was dependent upon another part failing and was not an unrelated incident occurring at the same time.

  - Failure of certain parts (limited life parts) occurring after their known useful life has expired will not be counted as relevant if identified and approved by the Government prior to start of the RDGT.

##### Electrical Test

The contractor shall comply with the electrical power requirements as defined in the RWSL System Specification FAA-E-3001, RWSL FLS Specification FAA-E-3002, and FAA-G-2100H. For equipment that will be installed in the FAA tower, the Contractor shall provide assistance to the FAA Technical Center Power Test Group while they are performing additional electrical power tests prior to the equipment being placed on the FAA electrical bus.

##### Maintainability Demonstration (M-Demo)

The M-Demo shall be performed in accordance with MIL-HDBK-470A, Task 301.  The Contractor shall conduct an M-Demo using MIL-HDBK-470A as guidance for the development of the M-Demo test plan. The Contractor shall use MIL-HDBK-470A as guidance to calculate the MTTR of each RWSL LRU to determine that MTTR requirements are met.

##### Site Development Qualification Test (SDQT)

The Contractor shall perform a SDQT at the key site to satisfy those requirements that require an operational environment not available at the Contractor’s facility.  SDQT shall be conducted on a 1st Article system.

In general, targets of opportunity shall be used during the conduct of SDQT.  If needed, the Government will provide test vehicles or test aircraft.

##### System Timing and Performance Test

The Contractor shall perform a RWSL system timing and performance test on site to verify all RELs and THLs are meeting system timing and performance requirements. The Contractor shall demonstrate correct system timing performance with the maximum number of light failures as determined in the RMA analysis.    This will be done by masking the lights on the field, individually failing RELs, THLs and individual light components, and collecting timing and performance data on the RWSL system.

##### System Adaptation and Map Verification Test

The Contractor shall verify the system adaptation and map set for the entire airport movement area.

##### Cable High Potential Maintenance Test

##### The Contractor shall perform a cable high potential maintenance test in accordance with FAA Order 6950.22.

#### Operational Test and Evaluation

The Contractor shall provide system maintenance and operation support during the Government conducted operational testing at the First Article Key Site.  This includes, but is not limited to, Operational Test and Evaluation and Independent Operational Test and Evaluation.

#### Regression Tests

The Contractor shall be responsible for corrective action necessary to ensure full specification compliance. Failure of the RWSL system equipment to meet specified requirements as identified in the SPR shall cause the Contractor to determine the reason for the non-compliance. The Contractor shall complete repair or rework prior to submission for re-testing. The Government Test Director will determine the extent of re-testing required. No formal re-testing shall be commenced until the Contractor has submitted in writing all information concerning the non-compliance and the corrective action taken, and the Government Test Director agrees to start the re-testing. If a review of the reasons for failure to comply with RWSL system or FLS specification requirements indicates that the cause may exist as latent defects in items previously accepted, the Contractor shall be responsible to correct the defects in a timely manner, even those previously accepted by the Government. The Contractor shall re-verify, by the verification method identified in the RWSL system VRTM, that the defect(s) have been corrected. The Contractor shall utilize the problem reporting system for reporting the re-testing plans, procedures, and results.

#### Production Acceptance Test and Evaluation (PAT&E)

The Contractor shall perform PAT&Es on each delivered system to verify that end-items (1) conform to applicable specifications, (2) are free from manufacturing defects, and (3) are substantially identical to the qualified hardware. These tests shall ensure compliance to system-level hardware and software requirements of the RWSL System Specification FAA-E-3001. PAT&E shall consist of FAT and SAT.

##### Factory Acceptance Test (FAT)

The Contractor’s quality assurance function shall perform FATs at the factory for each delivered item to verify that it (1) conforms to applicable specifications, (2) is free from manufacturing defects, and (3) is substantially identical to the qualified hardware. The FAT procedure is validated after DT&E at the factory on the production system.

##### Site Acceptance Test (SAT)

The Contractor shall perform SATs at each field site before acceptance of the system by the FAA. SAT procedures are validated during DT&E and constitute part of PAT&E when being conducted at field deployment sites.

### Construction, Delivery, Installation and Checkout

The Contractor shall be responsible for all construction, equipment delivery, installation, integration, checkout and support to the Government for Operational Test and Evaluation or other activities as directed by a Government issued Task Order. All activities at the airport shall be in accordance with the applicable advisory circulars referenced in Section 2 of this SOW.  The construction at some airports may be accomplished by the Government and/or the airport authority when it is more cost-effective or advantageous to do so. In addition, at airports where it is determined that there is no room in existing vaults or where it is advantageous to the Government, some of the RWSL equipment may be installed in Government Furnished Shelters.  In such cases, the Government will provide GFP shelters for the housing of the RWSL equipment.  The Contractor shall ship all shelter components to the Mike Monroney Aeronautical Center (MMAC) Logistics Center for installation of the equipment into the shelter.  This equipment may include, but is not limited to, constant current regulators (CCRs), master light controller (MLC), fiber optic converters and switches, and remote monitoring equipment. The Government will install the equipment within the shelter per the Contractor specifications.  The Contractor will provide an on-site representative for quality assurance for the first six (6) shelters.  The Government will ship the fully populated shelter to the site for Contractor installation and integration. Should the Government elect to provide such shelters as GFP, the Government will inform the Contractor who will then provide their required delivery schedule to support the contractual RWSL site installation completion date.

The Contractor shall be responsible for providing the following:

- Personnel, equipment and materials required for the safety, quality control, and establishment of each RWSL system at designated sites.

- Construction on airport property, when directed as part of the Government issued task order.

- Installation, integration, test, implementation, alignment, checkout, and acceptance testing of the RWSL system.

- Full-time supervision and direction of its personnel and subcontractors during all site activities.

The breadth and depth of services required shall be determined at each site and shall be based upon site surveys plus coordination with site personnel. The Contractor shall consider a typical RWSL installation to include the RWSL processor, all FLS equipment and supporting infrastructure, and systems required for operation of the RWSL system. The Government will designate an FAA Installation POC for coordination and oversight of all on-site activities. The Contractor shall provide Airport Construction Coordinators (ACCs) to cover all periods of time when construction activities take place within the Airport Operations Area (AOA) of the airport for the entire life of the project.

The Contractor shall also comply with the following Government regulations:

- National Environmental Policy Act (NEPA) of 1969.

- FAA Order 1050.1E, Policies and Procedures for Considering Environmental Impacts.

- FAA Order 1600.1E, Personnel Security Program.

Installation of the FLS equipment will comply with all applicable codes, rules and regulations on the site as well as AC 150/5370-2E, Operational Safety on Airports During Construction.

#### Implementation Management

The Contractor shall submit an Implementation Task Plan for each site in accordance with DID IC01 providing the details of the plans for construction, installation, integration and test of the full RWSL system at the site.  The Contractor shall manage the implementation and shall perform the following activities:

- Site engineering.

- Subcontract design specification preparation, award, administration, inspection, and acceptance

- Management and coordination of subcontractors’ activities.

- Integration and management of facility site preparations and physical facility modifications.

- Construction on airport property, when directed as part of the Government issued Task Order.

- Management of equipment installation at the site, to include installation of in-pavement lights on the airport movement area.

When so directed through the task order, the Contractor shall perform the Engineering Site Survey, prepare a Contractor Site Engineering Report (CSER) (3.5.2.3), prepare construction design specifications, and obtain any construction permits necessary before the installation.

After the installation of the FLS, the Contractor will provide required support during the systems integration and interface testing of the RWSL system.

CDRL  IC01  Implementation Task Plan

##### Priority and Coordination of Activities

Air Traffic Control (ATC) activities and services shall have priority over all Contractor construction and installation activities. There shall be no compromise for the safe and timely control of aircraft during the installation period. The Contractor shall provide services in such a manner which avoids disruptions to ATC facilities and conforms to the procedures considered essential by the Government for assuring safety for air traffic control. Site preparation, physical facilities construction, installation, inspection, and acceptance testing and the movement (on/off airport or on/off other FAA sites) of equipment shall be coordinated through the FAA POC. The FAA POC will coordinate such activities with local and regional air traffic and airways facilities personnel for final scheduling. Any required shutdowns of facilities to accommodate the RWSL installation or testing shall be coordinated through the FAA POC.

Facility heating, ventilation and air conditioning systems, any primary/secondary power, and telecommunications systems shall not be impacted during installation; supplemental HVAC shall be provided as required.

Work shall proceed on a regularly scheduled basis through completion.  The Contractor shall notify the Government of any equipment, item, part or service necessary for the proper installation of the RWSL not specifically identified herein or in the RWSL System Specification FAA-E-3001 or the RWSL FLS Specification FAA-E-3002 ninety days prior to the delivery.  Equipment, items, parts, or services specifically required to install and test the RWSL within the designated area shall be provided by the Contractor.  Any installation hardware shall be new material.

##### Site Security

A security program to minimize risk to personnel, equipment, and other RWSL assets on-site shall be incorporated in the CSER for construction and installation phases of the program. The Contractor shall use the applicable security requirements contained in FAA Order 1370.82A as a guide. Implemented security shall be subject to Government approval.

The RWSL Contractor shall comply with FAA security controls as determined by the FAA POC.  All personnel security policies, requirements and procedures, as stated in FAA Order 1600.1E, “Personnel Security Program”, shall be followed. The Contractor shall ensure that appropriate technical, administrative, physical, and personnel security requirements are implemented to ensure integrity, availability, and confidentiality throughout the contract.  RWSL system provider personnel shall comply with FAA security controls implemented in accordance with FAA policy.

The Contractor shall provide the FAA POC with a list of Contractor's personnel and subcontractor’s personnel who will require access to the site.  The list shall be kept current during project work.  The Contractor shall provide all personnel with readily identifiable numbered badges during the period their access to the site is required.  Badges shall be shown to the Government on-site representative prior to site entry and shall be worn on outer clothes while at work at the site.

The Contractor shall adhere to all specific security requirements in accordance with airport policy and procedures.  These should be discussed as part of the initial site survey visit and documented in the Security Plan portion of the CSER for approval by the Government.

##### Clean Up

The Contractor shall be responsible for removing from the site all surplus material such as tools, equipment, etc., belonging to the Contractor and to clean up rubbish and debris resulting from the modification/installation work. The Contractor shall leave the site in a neat and workmanlike appearance. The Contractor shall conduct a foreign object damage (FOD) inspection upon completion of work and prior to releasing for operation.   Upon completion of "clean-up" operations and FOD inspection, the Contractor shall obtain a written release from the FAA POC that the site has been restored to a satisfactory condition.

##### Damage to Site

Damage to facility buildings or premises caused by the Contractor's activities shall be repaired by the Contractor to “as new” condition.  Damage and finish degradation of any building, electronic subsystem interior or exterior surface and other installed equipment resulting from transportation and installation activities shall be repaired or replaced by the Contractor.  Damage to critical operations infrastructure shall be reported immediately and repaired immediately, with notification to the FAA POC.  All repairs shall be fully documented. The Contractor shall be responsible for all such repairs at no additional cost to the Government.

##### Contractor Use of Premises

The Contractor shall have access to facility environmental equipment only after receiving approval from the on-site Government representative.  The job site shall be maintained by the Contractor in a neat and orderly condition.  This includes the daily removal of rubbish, waste, tools, equipment, and materials not required for the work in progress.

#### Construction

The Contractor shall be responsible for all construction activities when directed through the Government issued Task Order.  This shall include the planning, site survey, site engineering report, construction and any required support activities, clean-up, and site inspection and acceptance by the Government and the Airport Authority.

##### Site Survey Criteria

The Contractor shall adhere to the following criteria as part of the site survey:

- The interior equipment installation and spacing rules shall follow Standard 29 CFR 1910, Occupational Safety and Health Standards.

- FAA-C-1217F, Electrical Work, Interior, FAA-STD-032, Design Standards for National Air Space Facilities, and NFPA No. 70, National Electrical Code, shall be used as facility design standards for each specific location of an RWSL system.

- System(s) shall not create obstructions to visibility or movement within the Air Traffic Control Tower cab. Additional physical space requirements to install the RWSL system shall not restrict existing operations.

- RWSL system(s) placement shall be in accordance with Federal Air Regulation 14 CFR, Part 77, Objects Affecting Navigable Airspace, and AC 150/5300-13, Airport Design Standards.

- Installation and placement of in-pavement lights shall be in accordance with AC 150/5340-30C, Design and Installation of Airport Visual Aids, and the FLS Specification FAA-E-3002.

- Installation of the in-pavement lights on the movement area of the runway must adhere to Advisory Circular, AC 150/5370-2E, Operational Safety on Airports During Construction.

- Installation of equipment in a movement area shall comply with obstacle limitation requirements as contained in title 14 CFR, Part 77.

- RWSL system installation shall meet seismic safety requirements as stated in Executive Orders 12699 (Seismic Safety of Federal and Federally Assisted or Regulated New Building Construction) and 13286.  Local jurisdiction ordinances may also apply.

- The facility heating, ventilation and air conditioning systems in the Air Traffic Control Tower (ATCT) and airfield lighting vaults/shelters shall not be impacted during installation of RWSL.

- FAA-G-2100H, Electronic Equipment, General Requirements, Appendix I, “Applicability to Procurements for COTS/NDI equipment” or the National Fire Protection Association’s National Electrical Code® (NFPA 70) and other national standards related to the specific needs of emerging technical requirement for ATC systems, shall apply.

- The Airport Layout Plan (ALP) shall be supplemented and verified by visual inspection of utility locations prior to construction.

- The RWSL system shall be located in a controlled access facility.

- All cables and other components connecting to the rest of the RWSL system shall be routed along mullions or within other existing structural elements of the cab tower to minimize visual blockage and interference with personnel movement.

- All field cable installations shall be in accordance with the requirements of FAA-C-1391B, Installation and Splicing of Underground cables.

##### Site Survey Requirements

The Contractor shall conduct a site survey for all designated sites.  The Contractor shall conduct site surveys of the first 21 sites starting 90 days after contract award, with two (2) site surveys convening each month until all site surveys are complete.  Site surveys will be conducted by personnel familiar with RWSL Siting Criteria to ensure that the selected sites satisfy all requirements.  The Government will provide operational requirements and priorities for each airport by letter.  This information will include specific equipment requirements (e.g., number and location of FLS systems).   The Government will provide site information to the Contractor to show geographic locations with each preliminary equipment destination, Airport Layout Plans including airport movement and non-movement area engineering drawings, physical interfaces, available Government resources, facility drawings, POCs, and other available information to assist the Contractor in planning each site installation. This information will be provided no later than 30 days prior to the scheduled site survey. The information will, as a minimum, identify to the Contractor the specific locations that define the intended site.

The site survey visit shall be coordinated at least 30 days in advance of the proposed start of the site survey.  A site survey meeting will be convened to exchange information with the Government and airport authorities, to provide notification of work to be accomplished in the site survey and to obtain information on procedures to be followed, do’s and don’ts, and airport specific rules, regulations, or other information that could affect the conduct of the survey. The agenda for the meeting will be provided in advance by the Government.  The Contractor shall document the results of the meeting in meeting minutes per CDRL PM11.  The site survey visit shall begin with a briefing to site personnel describing the RWSL system, interconnections, information to be gathered, and a discussion of the potential impact to operations during the installation phase.  The Contractor shall prepare a generic site survey checklist that shall be used to conduct the site surveys and shall be adapted for each site, according to a Government-approved survey schedule, to acquire site-specific information required for performance of the system installation activities. The Contractor shall also complete a survey of each RWSL location to include all RWSL components, according to a Government-coordinated survey schedule, to acquire site-specific information required for performance of the system installation and integration activities.  The siting shall be in accordance with RWSL GFI siting criteria document as well as airport design criteria.  The Contractor shall coordinate the survey with the FAA POC. The Contractor shall allow the FAA POC to fully participate in the survey.  The Contractor shall further discuss siting methodology and requirements with the FAA POC such that the POC fully understands survey objectives and results

The Contractor shall conduct a site survey for all designated sites. The Contractor shall prepare a list of system installation constraints, such as maximum cable lengths, power requirements, space requirements and building or construction requirements, weight, and HVAC loads and shall submit the list to the Government as part of the CSER (3.5.3.3).  Space shall be identified for prime mission equipment, physical storage space, monitor and control space, maintenance space, Airfield Lighting Equipment and other administrative space required to support the life cycle of RWSL system.  At each site survey, the Contractor shall work with the Government to determine installation requirements for that specific site.

##### Site Engineering Reports

The Contractor shall provide a CSER to the Government for each FAA designated site in accordance with CDRL IC01. After the site survey for each site, the Contractor shall develop a Site Survey Report, which will be delivered as part of the preliminary CSER.  Based upon the information provided by the Government prior to the site survey and the information gathered at the site survey, the Contractor shall document in the report 1) the actions that shall be performed by the Contractor prior to system delivery and 2) the actions that will be performed by the Government.  A cost estimate shall be included for each site.  The Government will identify Airport Authority, FAA Air Traffic, FAA Technical Operations, and any other personnel for coordination to obtain instructions and requirements regarding safety, insurance, bonding, and movement of Contractor personnel and equipment on the airport. As part of each CSER, the Contractor shall deliver site-specific drawings that include certified engineering drawings for the FLS and runway in-pavement light installation part of the system. The site-specific drawings shall be in an integrated drawing package with information from several sources superimposed with new RWSL site installation data. These drawings shall contain the appropriate regional title block and site-adapted notes referencing the RWSL site or other drawing numbers used to produce them. The Contractor shall participate in the Government’s risk mitigation planning using the FAA Pre-Construction and Maintenance Project Safety and Health Checklist, Order 3900.57.  Storage and security of on-site materials shall be the responsibility of the Contractor and shall be addressed in the CSER in accordance with CDRL IC01.  After Government review of the Preliminary CSER, the Contractor shall incorporate changes and provide a final CSER with completed cost information for Government approval.  The Contractor shall not commence any site installation activity until final approval of the CSER is received from the Government.

CDRL  IC02  Contractor Site Engineering Report

##### Red-lined and Government Facility Drawings

The Contractor shall red-line site specific (e.g., airport movement and non movement areas) and FAA facility drawings to show any changes resulting from the installation and actual placement of RWSL equipment. Red-line markings shall include, but not be limited to, wiring diagrams (including color-coding), identification, and terminations. All markings shall be legible and depicted in a manner that will enable the Government to verify corrections to the original drawings. All drawings and changes shall be in accordance with FAA-STD-002F. The following drawings shall be made current to reflect the particulars of a given site:

- Installation Drawings. These drawings shall be modified to indicate actual dimensions, cable runs, and concretion specifics.

- Government Facility Drawings. These drawings shall include Government drawings of the ATCT and support buildings that show details of cable trays, equipment rooms, and console layouts. These drawings shall also include the Facilities General Layout Plan.

- Engineering drawings for airport movement and non-movement areas: These drawings shall include airport drawings that show details of cabling, in-pavement light locations on the runway and taxiways, equipment rooms, and installation methods. These drawings shall also include the Airport General Layout Plan.

- Facility Standard Drawings. These drawings are specific to the individual requirements of the RWSL equipment. Facility Standard Drawings will require Government approval.

CDRL  IC03  Red-Lined Drawings

CDRL  IC04  Facility Standard Drawings

##### Facility Site Preparation, Construction and Physical Facility Modification

After Government approval of the CSER, the Contractor shall perform site preparation and site modifications to prepare for installation of each RWSL system. The facility site preparation and physical site modification shall be accomplished in accordance with the RWSL FLS Specification FAA-E-3002 and the approved CSER in accordance with applicable ACs. The Contractor shall determine, select, provide, and install cables and connectors necessary to connect the RWSL equipment to the Government-designated power sources. All facilities shall be grounded and bonded in accordance with current FAA orders, specifications and NFPA requirements.  Facility modification and design shall be in accordance with current FAA orders, specifications and NFPA requirements.  Power installation shall be to the power bus. The services required for the movement of Contractor personnel, mail, and materials at each location shall be the Contractor's responsibility. Construction shall allow for installation of FLS components into designated runway/taxiway entrances; provision and routing of electrical and fiberoptic communications cabling; and provision, installation and connection of electrical equipment, where adequate equipment does not exist, e.g., disconnect switch, 480 volt input panel, high voltage output cabinet, utility transformer, distribution panel, etc.

The Government will provide to the Contractor three (3) acceptable specifications and elevation drawings for the GFE shelter foundation to be constructed at each site.  The size of the shelter will be determined by the Government from the CSER.  The Contractor shall select the most suitable foundation type from the three specifications provided for consideration, based upon the Contractor’s determination of the applicable soil type, drainage requirements and other pertinent information. The Contractor shall ensure that the appropriate footing sub-grade, bearing pressure and anticipated settlement are considered and applied to the construction of the shelter foundation.  The Contractor shall ensure that all local and national building codes and seismic codes are followed in the design and construction.  Areas disturbed during construction shall be returned to the original or natural state.  Preventive measures shall be taken to ensure proper drainage of the site and to prevent erosion or run off of excavated soil.

For all construction activities, the Contractor shall:

- Participate in the pre-construction meeting with the FAA, airport representatives and other affected parties for discussion of activities, schedules, associated plans and procedures, and rules and regulations. The Contractor shall provide an Agenda and Minutes in accordance with CDRLs PM10 and PM11.

- Perform the civil site preparation per approved plans.

- Comply with environmental assessment/categorical exclusion requirements, if applicable.

- Perform clearing, earthwork, grading and drainage at each facility location.

- Engage in construction for the RWSL, FLS and associated equipment, as applicable.

- Install power and control cables in accordance with the requirements of FAA-C-1391B, installation and Splicing of Underground Cables.

- Provide trenching and cabling for all intra-airport RWSL connections.  Land line communications from the ATCT to each vault/shelter shall be installed via fiber optic cable and comply with FAA-STD-057 Airport Fiber Optic Communication System (FOCS) Standards.

- Coordinate site restoration and facility clean-up.

- Prepare “as-built” design drawings, CDRL IC05.

- Notify the designated FAA POC and Airport designated authority within 5 minutes if any problems occur during any phase of the construction.  After action, provide an incident report, including any required OSHA reporting, in accordance with instructions to be furnished by the RWSL Program Management Office within 24 hours.

- Secure all state and local permits, as applicable.

- Coordinate any required storage and security of all equipment delivered to the project site for purposes of installation.

- Coordinate a contractor’s staging area.

- Coordinate all required access to the RWSL sites for construction activities.

- Ensure securable warehouse or hangar space is adequate; otherwise, space appropriate for a construction office trailer will suffice.

- Provide a list of submittals and technical documentation for Government Furnished Material/Information List to be installed in support of the construction.  The submittals shall be included in the specific airport CSER.  The FAA will review and approve the submittals.

- Conduct a construction final inspection and Site Acceptance with the Government as described in the Implementation Task Plan.

- Coordinate all shift start/stop times in advance with FAA POC and designated airport authority.

- Conduct daily clean-up and foreign object damage inspection upon completion of work and prior to releasing for operation.

#### System Installation

The Contractor shall install the CLIN 001 RWSL system at the location listed in Section F, as well as additional sites in accordance with approved CLINs.  Install FLS hardware per the following table:

Table 2: FLS Equipment

| Item | Relationship |
| --- | --- |
| Light Computer | Nominally one per airport (dependent on a site-by-site basis in accordance with the FLS specification) |
| Constant Current Regulator (CCR) | Nominally two per equipped runway, one for RELs and one for THLs |
| RWSL Processor | One per airport |
| Control Panel | One per Air Traffic Control Tower (ATCT) |
| Master Light Controller | One per CCR |
| Remote Maintenance Display | One per vault/shelter |
| Semi-Flush Light Fixtures - THL | Nominally thirty-two (32) per array |
| Semi-Flush Light Fixtures - REL | Nominally six (6) per Intersection |

Installation at RWSL sites includes, but is not limited to, the following typical items:

- Electrical wiring and FLS equipment (including CCRs, cable, conduit and in-pavement lights).

- Mechanical mounting and grounding of all RWSL components.

- Connection with distribution, demark, and terminal panels, boxes, and cabinets.

- All required testing for quality assurance of construction and installation.

- All required documentation in accordance with this SOW, CDRLs and specifications.

As part of the installation, the Contractor shall install the RWSL system including processor, FLS, and auxiliary equipment in accordance with the Government approved CSER, and shall ensure the following:

- The RWSL system installation and implementation shall be accomplished within the framework of NEPA of 1969 and FAA Order 1050.1E, “Policies and Procedures for Considering Environmental Impacts.”

- The installation and spacing rules shall follow Standard 29 CFR 1910.

- The facility heating, ventilation and air conditioning systems shall not be impacted during installation of RWSL.

- Conduits and cables shall be of standard type and appropriate for their applications in accordance with FAA-C-1391B, Installation and Splicing of Underground Cables.

- Installation and checkout shall be performed without disrupting current air traffic services and will not require additional workload from Air Traffic (AT) or Technical Operations (AF) personnel at the facility while performing their normal duties.

- Integration with existing equipment and coordination with facilities shall be the responsibility of the Contractor under the direct guidance of the designated the FAA POC.

- Preliminary work done in advance of installation that will disrupt ATC operations or airport operations shall be performed during non-peak operating hours.

- All work to be performed on-site shall be coordinated with the FAA POC.

- The Contractor and all subcontractors shall be responsible for meeting the security requirements of the airport authority and obtaining necessary access badges. Access to movement and non-movement areas of the airport may require Government escort.

- The Contractor shall provide paper red-lined drawings for all FAA official drawings affected by the installation.

The Contractor and subcontractors shall use only factory-trained personnel for installation supervision of field work. Subcontractors used by the Contractor (e.g., electrical, rigging, crane service, labor, trash removal, and other miscellaneous work and services) shall be the responsibility of the Contractor and under direct supervision at all times.

The Contractor shall be responsible for the unloading, care, and protection from weather, theft, vandalism, or other factors of all materials (GFE, Contractor Furnished Equipment, etc.) delivered until completion and final acceptance by the Government.

##### Site Optimization

The Contractor shall provide analytic and software adaptation support to the Government for site optimization of the First Article RWSL key site prior to SAT.  Site optimization shall determine and tailor/implement the site specific parameters to airport users and site environment conditions. The Contractor shall provide a guide that can be used by the Government for accomplishing successful site optimization at additional sites.

##### Test Equipment

The Contractor shall furnish all necessary standard test equipment and special test equipment for maintenance, testing, and installation activities on the RWSL system during installation and acceptance. Required installation procedures, tuning/optimization adjustments, maintenance procedures, and testing shall be performed using only the test equipment, special and common, identified by the Contractor to the Government for this purpose in accordance with  the RWSL specification and this SOW. The use of any other test equipment by Contractor is prohibited unless approved by the Government.

##### Final As-Built Drawings

The Contractor shall accurately and promptly amend (for all original drawings) the changes, revisions, or additions resulting from the RWSL installation. This amending process shall reflect the current "As-Built" status. The amendment process shall apply to all site-specific Contractor-generated drawings and Government facility drawings that were "red-lined" during installation, and also to any RWSL standard drawing. The drawings shall be amended with the appropriate regional title block, facility title, and completed revision block. The application of FAA-STD-002F, Standard Engineering Drawing Preparation & Support, is required for all construction drawings.  The As-Built Drawings shall be prepared and submitted in accordance with CDRL IC05.

CDRL  IC05  Final As-Built Drawings

##### Contractor Acceptance Inspection

At the completion of all construction, installation and test activities, the Contractor shall perform the Contractor Acceptance Inspection (CAI) to demonstrate conformance with equipment specification and standards at each site.  At completion of testing, in accordance with the requirement of Section 3.4.4.2 of this SOW, the Contractor shall submit a complete report (TE04) of the results of the SAT tests to the Government for approval. The contractor in conjunction with the Government shall perform a CAI using a CAI checklist to confirm that the RWSL system is working according to system specification.  The successful completion of the CAI results in the official transfer of ownership of the system to the FAA.

### Integrated Logistics Support

The Integrated Logistics Support (ILS) effort begins upon contract award and evolves throughout the development, test, installation and Interim Contractor Depot Level Support (ICDLS). The Contractor shall plan, manage, and execute an ILS program that addresses applicable elements of logistics using the Acquisition Management System ILS Process Manual as guidance. The ILS Process Guide is located on the FAST toolset at fast.faa.gov (go to “Specialty Functions, Processes and Guidance, under the Integrated Logistics Support heading). The Contractor shall establish and maintain an ILS Program in accordance with this SOW.  The ILS is an interrelated, unified, and iterative approach to the managerial and technical activities that support the RWSL Program. The analyses associated with ILS influence system configuration to minimize the life cycle cost. Through the ILS process, support requirements are identified and acquired. The following paragraphs describe the intended minimum ILS activities associated with the development of the RWLS design and implementation activities.

#### ILS Program Management

The Contractor shall designate an ILS Manager to serve as a single point of contact between the Contractor and the Government Associate Program Manager, Logistics (APML) in all matters relating to the ILS requirements of the contract.

A joint Government/Contractor sponsored ILS Management Team (ILSMT) for RWSL shall be established and shall serve as the primary management vehicle for monitoring the status of the ILS program. The chairperson of the ILSMT is the FAA APML. The ILSMT provides a means for coordinating and monitoring logistics-related schedules and contract performance, and reviews the adequacy, timeliness, and compliance with related contract requirements. The ILSMT shall meet semi-annually or when requested by the APML, not to exceed four meetings per year. ILSMTs shall be conducted at mutually convenient locations, but usually at the Contractor's facility.

The Contractor shall be responsible for the following:

- Providing an agenda and minutes for each meeting. The agenda shall also provide for status reporting and analysis of problem areas. The agenda and meeting minutes, accompanied by a summary of action items, and all presentation materials used, shall be submitted for Government approval in accordance with CDRLs PM10 and 11.

- Attending ILSMT meetings and assuring that subcontractor and engineering personnel are available when requested.

- Briefing the status of the logistics elements and address support issues identified on the agenda.

##### Conferences

##### Logistics Guidance Conference

A Logistics Guidance Conference (LGC) shall be conducted at the Contractor's facility in conjunction with the post-award conference.  The FAA APML will chair the meeting.  Contractor logistics personnel shall present the Contractor’s approach to accomplish the required logistics tasks. The Contractor shall support the conference with the required resources (e.g., briefings, personnel, and facilities).  The Contractor shall provide an agenda and all presentation materials prior to the meeting and minutes and action items after the meeting for Government approval. The LGC shall clarify provisioning requirements and issues (e.g., provisioning deliverables, data requirements, technical documentation, and Engineering Data for Provisioning). The subjects the Contractor shall be required to address at the LGC include the following and shall follow CDRLs PM10 and 11:

- Maintenance Planning

- Manpower and Personnel

- Supply Support

- Support Equipment

- Technical Data

- Training and Training Support

- Computer Resources Support

- Packaging, Handling, Storage, and Transportation

- Facilities Integrated Logistics Support (ILS) Management

##### Provisioning Conference

The Contractor shall host and support a Provisioning Conference to be conducted at the Contractor's facility no later than 30 days after the PCA. Subsequent Provisioning Conferences (not to exceed three) shall be conducted when requested by the Government. The Contractor and subcontractor/vendors, as determined by the Government, shall attend, participate, and contribute expertise to the Government in resolution of provisioning and supply support problems or issues. The Contractor support to the conference shall also include facilities, materials, office equipment, clerical personnel, mockups, and technical data to include drawings.  The Contractor shall provide an agenda, minutes, and presentation materials in accordance with CDRLs PM10 and 11, as well as a summary of action items, for Government approval.

#### Integrated Support Plan

The Contractor shall prepare and implement an Integrated Support Plan (ISP) that provides a detailed description of the procedures, actions, events, milestones and organizations the Contractor intends to employ to successfully accomplish the ILS Program.

CDRL  LM01	  Integrated Support Plan

#### RWSL Maintenance Concept

The RWSL maintenance concept is comprised of two-levels, site and depot, with maintenance to be performed at both levels.

Site maintenance is intended to be centered on removal and replacement of LRUs and will include periodic, preventative and corrective maintenance. Periodic and preventative maintenance for the system will be required no more frequently than four times per year and will require no more than four hours and one person to perform with the exception of visual inspection of the field lighting system which may be more frequent and require two persons to perform.

Depot level maintenance will consist of repairing or replacing failed, repairable LRUs that have been removed in the field. Depot support will be available for the RWSL processor, cab control panel and maintenance display LRUs and components. Initial depot maintenance and inventory support shall be provided by the Contractor, and may migrate to organic (FAA) depot.

#### Logistics Management Information

##### LMI Requirements

The Contractor shall develop and deliver to the Government, in accordance with MIL-PRF-49506, the data products contained in the Logistics Management Information (LMI) Data Products Worksheet in the format attached to DID LM-002. MIL-PRF-49506 describes the information required by the Government to perform acquisition logistics management functions. The LMI Data Products Worksheet consists of the data that a requiring authority needs in order to develop internal materiel management processes. The data products shall represent the system design configuration to the component level including systems, subsystems, components, assemblies, subassemblies, support and test equipment, and training equipment required for RWSL.  Temporary items are not required. The Contractor shall adhere to the data definitions, edits, and data formats as described in MIL-PRF-49506, Appendix B, the attached LMI Data Products worksheet, and the RWSL Data Products Format attachment to DID LM-002.  Modified data product requirements shown on the LMI Data Products Worksheet and the RWSL Data Products Format shall take precedence over MIL-PRF-49506. The Contractor shall update the LMI Data Products based on changes to the LMI.

CDRL  LM02	 LMI Data Products

##### LMI Data Reviews

The Contractor shall host an LMI Data Review 90 days following the LGC. Topics shall include the Contractor's progress in LMI development and plans for future efforts. Additional data reviews, not to exceed four each year, may be held in conjunction with ILSMT meetings and at the discretion of the APML.  An agenda, meeting minutes, presentation materials shall be provided in accordance with CDRLs PM10 and 11.

##### LMI Acceptance Criteria

Upon receipt of data submittals, the Government will verify that the data is documented as specified in 3.6.4.1 and that it meets the data definition, edit, and data format requirements of MIL-PRF-49506 and the attached worksheet.  Data will not be accepted unless:

- The submitted data reflects a level of detail to the component level as identified in 3.6.4.1.

- The data is verified to accurately reflect the current design configuration.

- The data conforms with the delivery requirements stated in DID LM-002.

- The required data elements are provided as specified on the attached LMI Data Products Worksheet.

#### Supply Support

##### Site and Depot Spares

The Contractor shall develop and submit a list of site spares that consists of LRUs, removable modules, common and bulk items, and any other parts necessary to perform site maintenance. Upon Government approval of the site spares list, the Contractor will be required to deliver the approved range and quantity of site spares to each site.  The Contractor will update site spares list as required.

CDRL  LM03	  List of Recommended Site Spares

##### Consumables

The Contractor shall identify all site consumables required for operation and maintenance of the RWSL system.  A consumable is any hardware item that can be removed and replaced to restore the system, and is a low-cost, non-repairable item (e.g. fuses, light bulbs, knobs, wire, battery terminal lugs, cleaning fluid) that is uneconomical to repair.

CDRL  LM04  List of Recommended Consumables

##### Support and Test Equipment

The Contractor shall identify all site and depot common, RWSL unique, and peculiar tools, handling, support and test equipment required to support FAA planning and training. The Contractor shall also provide RWSL unique support and test equipment for each system, but shall make every effort to standardize support and test equipment with current FAA inventory.

CDRL  LM005	 Support and Test Equipment List

##### LRU Identification and Marking

The Contractor shall use commercial marking practices for the purposes of product identification and inventory management to control and identify RWSL LRUs.  The Contractor shall be responsible for marking all RWSL LRU components including LRU spares.  All LRU components and LRU spares shall be marked with bar code symbology that is consistent with commercial product identification in accordance with AIM-BC1 Uniform Symbology Specification Code 39.  Bar code markings shall be applied to each LRU, or where impractical, on the individual LRU packaging.  LRU markings shall be sufficient to clearly and visually identify the LRU and the contents of an LRU package in accordance with MIL-STD-129P.

CDRL  LM06 	LRU Markings Report

#### Technical Data

The Contractor shall be responsible for obtaining, integrating and providing the necessary operations and maintenance technical data required to maintain RWSL. The Contractor shall be responsible for ensuring that RWSL technical data is updated to reflect Government-approved engineering changes prior to establishment of the product baseline.

##### Technical Drawings and Associated Lists

The Contractor shall develop technical drawings and data for the implementation and support of the RWSL. The Contractor shall develop an engineering drawing tree that will identify all items to be delivered as part of the drawing package.

Modified COTS is to be considered as COTS equipment that has been modified or altered in any fashion to integrate it into the end product or system.  In such cases, the Contractor shall provide the documentation required in paragraph 3.6.6.4 of this SOW, in addition to the drawing(s) and data reflecting what was modified or altered to the COTS item.

CDRL  TD01  Engineering Drawing Tree

##### Product Drawings

For developed items, the Contractor shall provide product drawings in accordance with MIL-PRF-28000B, Initial Graphic Exchange Specification (IGES) Class 2 & 3 and associated lists shall be in accordance with MIL-DTL-31000C paragraph 3.6.2.3.

CDRL  TD02  Product Drawings

##### COTS Drawings

For all commercial items associated with the RWSL, the Contractor shall provide all vendor supplied commercial drawings, technical documentation and source control documents.  The Contractor shall not be expected to provide commercial drawings other than what is normally provided by the vendor.

CDRL  TD03  COTS Drawings

##### COTS Manuals and Documentation

For all COTS (hardware/software) associated with the RWSL, the Contractor shall provide all vendor supplied commercial drawings, technical documentation and source control documents.  The Contractor shall not be expected to provide commercial drawings other than what is normally provided by the vendor. The Government shall be provided with reproduction rights on all deliverable COTS documentation. The following are examples of COTS documents to be provided:

- Operator/User's Manuals

- Hardware/Repair Manuals

- Installation Requirements (Space and Power) Manuals

- Software/Software Development Tool Manuals

- Diagnostics/Diagnostic Interpretations Manuals

- Installation/Removal/Maintenance Instruction Manuals

- Schematics/Wiring Diagrams

- Parts Lists/Catalog

CDRL  TD04  Commercial Off the Shelf (COTS) Manuals

##### COTS Hardware Description Document

The Contractor shall develop a COTS hardware description document for use in provisioning and baselining the system. This document shall be developed to the LRU level and contain sufficient data (such as input/output specifications, performance specifications, dimensions, etc.) to provide the Government the information needed to procure the items from commercial and other sources.

CDRL   TD05  COTS Hardware Description

##### Technical Instruction Books

The Contractor shall prepare and submit for Government approval, a separate Technical Instruction Book for the RWSL processor, FLS, and any associated Contractor-furnished peculiar Support/Test Equipment.

Each Technical Instruction Book shall comply with the requirements set forth in the latest version of FAA-D-2494B.

##### Manuscript Plan

The Contractor shall prepare and submit for Government approval a Technical Instruction Book Manuscript Plan which describes the contractor’s plan to comply with the requirements of the latest version of specification FAA-D-2494B.  The plan shall include a schedule for manuscript preparation, review, and validation.  The manuscript plan shall also include a schedule for submittal and Government approval of a prospectus for the manuscript. A separate manuscript plan shall be provided for each of the RWSL processor and the FLS Technical Instruction Books.  Each Manuscript Plan shall comply with the requirements of the latest version of specification FAA-D-2494B, paragraph 3.2.

CDRL  TD06  Manuscript Plan

##### Manuscript Prospectus

The Contractor shall prepare and submit for Government approval a Prospectus for the Technical Instruction Book.  The prospectus shall be in the form of a detailed outline, developed in accordance the content requirements of the latest version of specification FAA-D-2494B, and prepared to the level of paragraphing necessary to show the major physical and functional aspects of planned coverage.  Each section and paragraph title shall be followed by a brief statement outlining the data to be presented and the planned approach.  A listing of illustrations, charts, tables, and graphs shall be included.  Government approval of the prospectus must be obtained before work on the manuscript begins.  A separate prospectus shall be provided for each of the RWSL processor and FLS Technical Instruction Books.

CDRL  TD07  Manuscript Prospectus

##### Verification and Validation Plan

The Contractor shall prepare and submit for Government approval a Technical Instruction Book Verification and Validation Plan which describes the contractor’s plan to accomplish the verification and validation requirements described in section 4 of the latest version of specification FAA-D-2494B.  Reviews other than in-process may be performed either on a chapter-by-chapter basis during preparation of the manuscript or upon completion of the manuscript.  The plan shall provide a schedule of reviews indicating completion dates for each of the tasks listed in paragraphs 4.3, 4.4, and 4.5 of the latest version of specification FAA-D-2494B.  A separate Verification and Validation Plan shall be provided for each of the RWSL processor and FLS Technical Instruction Books.

CDRL  TD08  Verification and Validation Plan

##### Draft Manuscript

The Contractor shall prepare and submit for Government approval draft Technical Instruction Book in accordance with the approved manuscript plan and prospectus.  The draft Technical Instruction Books shall comply with the requirements set forth in paragraph 3.3.1 of FAA-D-2494B.  A draft Technical Instruction Book shall be submitted at each of three in-process review stages: 30-percent complete; 60-percent complete; and 90-percent complete.

A separate draft shall be provided for each of the RWSL processor and FLS Technical Instruction Books.

CDRL  TD09	 Manuscript

##### In-Process Review

In-process reviews for each of the 30%, 60%, and 90% draft Technical Instruction Book submittals shall be conducted in accordance with paragraph 3.3.1.1 of FAA-D-2494B. In-process reviews may be conducted at the contractor’s facility or as determined by the Contracting Officer and shall be accomplished as listed in the manuscript schedule contained within the approved manuscript plan. The Contractor shall provide drawings, illustrations and support materials to assist in manuscript review. Comments from the reviews shall be incorporated into the draft manuscripts prior to their next submission. The Contractor shall submit a Comment Resolution Report in accordance with CDRL TD10 for each review listing of all comments received, indicating those accepted and incorporated into the revised draft and those not accepted, along with the reason for rejection.  The Contractor shall prepare meeting minutes and action items resulting from the meetings in accordance with CDRL PM11.

CDRL  TD10  Comment Resolution Report

##### Final Manuscripts for FAA Review

The Contractor shall prepare and submit for Government approval final draft Technical Instruction Books. Final draft manuscripts shall be provided after comments from the 90% in-process review have been incorporated. The drafts shall be provided for review and approval by the Government. Government comments shall be incorporated into the manuscripts.  A separate final draft shall be provided for each of the RWSL processor and the FLS Technical Instruction Books.  The Contractor shall submit a Comment Resolution Report listing in accordance with CDRL TD10 of all comments received, indicating those accepted and incorporated into the final manuscript and those not accepted, along with the reason for rejection.

##### Final Manuscript

Upon Government approval of the draft manuscript, the Contractor shall prepare and submit for Government approval a final reproducible version of Technical Instruction Books, with all corrections incorporated, in accordance with the schedule contained within the approved manuscript plan.  The final Technical Instruction Books shall comply with the requirements set forth in paragraph 3.3.2 of the latest version of specification FAA-D-2494B.  A separate final version shall be provided for each of RWSL processor and the FLS Technical Instruction Books.

CDRL  TD09  Final Manuscript

##### Support/Test Equipment Manuals

Separate, stand-alone instruction books shall be provided for the operation, description, maintenance, and repair of the Contractor-furnished peculiar support/test equipment. The instruction books may be in the original equipment manufacturer's format. Electronic media, programs, or documentation required for data analysis shall be provided with electronic test equipment.

CDRL  TD11	  Support/Test Equipment Manuals

##### Technical Instruction Books Validation

The Contractor shall validate each Technical Instruction Book in accordance with the approved Verification and Validation Plans.  Validation shall be conducted by actual performance of operating and maintenance procedures unless written authority is obtained from the Government to use simulation for selected procedures.  The Government reserves the right to witness each procedure validation.  Upon completion of the each Technical Instruction Book validation, the Contractor shall prepare and submit a

letter to the Contracting Officer indicating successful completion of validation.

##### Verification

To assure that the contractor has fulfilled all requirements of the validation process, the government reserves the right to witness any contractor validation activities.  Verification may also include the actual performance, by government personnel, of any instruction contained in the Technical Instruction Books.  The Contractor shall provide engineering and technical assistance support during Government verification of all Technical Instruction Books.

##### Air Traffic Controller Operator's Manual

The Contractor shall prepare and deliver a draft and final Operator's Manual. The draft shall be provided for review and approval by the Government. The manual shall contain the following information:

- Description of the uses of the equipment.

- Indication of the relationship to other program documentation.

- Description of the function of all operator controls.

- Description of the use of all peripheral equipment (including immediate interface equipment).

- Description of operating procedures.

Copies of this manual shall be provided for each site.

CDRL  TD12  Air Traffic Operator’s Manual

##### FAA Installation POC Manual

The Contractor shall develop and deliver a draft and final reproducible/POC manual, in accordance with FAA-D-2494B for review and approval by the Government, which will describe how all of the equipment is integrated into a single operational system.  The manual will provide information regarding installation, integration, test, implementation, alignment, checkout, and acceptance testing of the RWSL system.

CDRL 	TD13  FAA Installation Point Of Contact Manual

#### Technical Operations Specialists Training

##### Implementation

The Contractor shall develop and deliver resident (lecture with lab exercises) training to provide designated FAA personnel with the knowledge and skills required to ensure competence in performing their respective duties as it relates to the RWSL system.  The Contractor shall develop and deliver all training and training materials in accordance with FAA-STD-028C, Contract Training Programs and Technical Operations Training, AMA-400 EHOT-DoP  Policy and Procedures, as modified by the Government in this document.  The Contractor shall perform the training tasks outlined in the following subsections and prepare all course materials in a Government-approved contractor format.

All material developed for the Government by Contractors shall be the sole property of the Government and shall not be used by the Contractor for any purpose other than those in the contract unless approved by the Government.

##### Training Guidance Conference

The Contractor shall participate in a Government sponsored RWSL Training Guidance Conference (TGC).  The purpose of the TGC is to provide the Contractor with guidance or clarification on training requirements and plans and associated CDRLs and DIDs.  The TGC will be held at a Government-approved Contractor or Government facility.

During the TGC, the Contractor shall be prepared to discuss their understanding of the work to be performed, training requirements, and other related items wherein the Contractor desires Government guidance.  As a minimum, the TGC shall include the following:

- Review of contract requirements such as training deliverables, personnel, schedules, training locations, and FAA-STD-028C.

- Discussion of the Contractor Personnel Qualifications Report.

- Discussion of the Contractor’s schedule for completing the training development process and the requirements associated with each deliverable.

- Deliverable review and comment process.

- Discussion of methods for completing the Task and Skills Analysis (TASA).  A sample TASA will be provided by the Government.

- Discussion of the Training Development Plan (TDP). A sample TDP will be provided by the Government.

- Permit inspection of the contractor’s facility and establish a working relationship with contractor personnel.

- Discuss classroom administration requirements.

In the event the Government convenes a joint Air Traffic and Tech Ops guidance conference, separate sessions will be held to discuss specific Technical Operations and Air Traffic training requirements.  In accordance with CDRL PM10 and 11 the Contractor shall develop the TGC agenda and prepare and distribute minutes.

##### Training Materials

The Contractor shall develop training and reference materials to support delivered training.  The Contractor shall provide each student with a complete a set of course materials for the respective course.  Course conduct shall make maximum use of all materials distributed.  Student manuals and guides will encompass a “how to” approach and work in concert with the instructor materials (lesson plans, PowerPoint presentations, figures, handouts, etc.).  The Contractor shall furnish and maintain all reference, instruction and student materials for each class.  The Contractor shall make one set of Technical Instruction Books available to each student during the training classes.

At the conclusion of each class, students will retain all student course materials issued to them.  The Technical Instruction Books, made available as reference material, shall be retained in the classroom.  The Contractor shall submit all course materials for review and approval prior to conducting training classes. Training materials shall incorporate all Government-approved revisions prior to conducting any additional reviews and/or classes, and students in follow-on classes shall be provided clean copies of student materials.

In addition the Contractor shall provide the following:

- A copy of all student materials used in the course or briefing session for each Government instructor participating in designated courses or Operational Tryout.

- Sufficient sets of classroom technical documentation reference materials, which shall be retained in or near the classroom as a reference library

- Suggested list and quantities of reference materials needed for each course.

All training materials shall comply with RWSL Technical Instruction Books.

##### Environmental Occupational Safety and Health

All training developed or revised by a Contractor must meet or exceed the appropriate Occupational Safety and Health Administration (OSHA) regulations in accordance with OSHA 29 CFR1910.  OSHA safety regulations are to be integrated into course content, as appropriate.

The Contractor must emphasize, in its developed instructional program, each person’s individual accident prevention responsibilities as well as their responsibilities as representatives of the Government.  Safety precautions related to training on the operations, maintenance, and/or troubleshooting of equipment must be a prominent part of the training.

##### Contractor Furnished Training Equipment

The Contractor shall furnish all training equipment, safety equipment, including personal protective and material handling equipment, special tools, etc., necessary to conduct training.  Any equipment/system furnished for training development and/or conduct shall include all software, special tools, test equipment, simulators, emulators, and support equipment required to provide the end product or service.

The Contractor shall maintain all equipment in an operable and usable condition except for planned disassembly and fault isolation training exercises.  The Contractor shall notify the Government immediately by telephone if training equipment becomes inoperable and/or unusable.  Pre-faulted LRUs and components (printed circuit boards, power supplies, cables, etc.) shall be included as training equipment.  If Contractor furnished training equipment is to be returned to stock for subsequent delivery to the Government, the Contractor shall keep configuration management records on the equipment in accordance with FAA-STD-028C. Any training aids, demonstration items, charts, mock-ups, etc., used in training shall be provided to the Government at the conclusion of Contractor training.

##### Contractor Furnished Training Site(s) and Facilities

The Government shall approve in advance all training sites. The Contractor’s facility shall be the preferred training site for all training, and unless otherwise provided for in this contract, all training shall be conducted at the Contractor’s facility.  The Government may inspect any training sites and/or facilities furnished by the Contractor during the contract period.  The following conditions will be appraised and must be approved:  space, lighting, noise, heating and cooling, safety of environment, cleanliness and sanitation, and furniture.  The contractor shall correct any known deficiencies identified before the start of training.

The contractor shall provide training aids such as chalkboards, overhead projectors, viewgraphs, etc., as identified in training documentation.

##### Government Furnished Training Equipment and Materials

If training is conducted at an FAA field site, the Government shall make all system or other equipment to be used in training available to the Contractor.  The Government shall maintain Government-furnished training equipment in an operable and usable condition except for planned disassembly and fault isolation training exercises.  Practical application activities requiring use of the system or equipment shall be coordinated with the FAA training representative onsite, at least 24 hours prior to need.  The Contractor is not responsible for damages sustained by Government-furnished training equipment except if caused as a result of Contractor negligence.

##### Training Requirements

##### Hardware Maintenance Training

The Contractor shall develop and conduct this course in such a manner that Technical Operations personnel completing this training shall be equipped with the knowledge necessary to provide onsite RWSL system maintenance.  Course content will include, but not be limited to, the following:

- System overview.

- Theory, or concept, of operation.

- Maintenance concepts and responsibilities.

- System block and LRU diagrams.

- In-depth parameters.

- System and subsystem interfaces.

- Operational, functional, and adjustment checks in accordance with the manufacturer’s instructions or applicable FAA orders.

- Routine periodic and preventive maintenance using the checks and procedures established for the RWSL system in accordance with FAA orders.

- Fault isolation and diagnostics procedures for failures to the LRU level and restore the equipment to operational service through removal and replacement of the faulty LRU.

- Required adjustments to restore the system to operational service following removal and replacement of the faulted LRU.

- Configuration, restoration, and verification in accordance with RWSL technical instruction manuals and certification of service in accordance with FAA orders.

- Software upgrades on remote site hardware.

- Safety.

- Use of RWSL system software for maintenance, restoration in accordance with RWSL technical instruction manuals and certification of service in accordance with FAA orders.

##### General Course Requirements

The Contractor shall provide RWSL system maintenance training via lecture and laboratory.  The lecture and laboratory training shall be conducted at the Contractor’s facility or a designated FAA site and shall meet the following requirements:

- Submittal of a course outline and formats for training materials to the Government for approval prior to use. Student manuals and lab manuals shall be developed using Content Design format.  FAA shall provide the template to the contractor.

- Thoroughly tested course objectives in written and/or graded lab practical examinations.

- Training:

  - Shall be based on a Task and Skills Analysis (TASA) with cognitive and performance objectives directly derived from the TASA.

  - Training course materials shall be based on the system/equipment Technical Instruction Book(s). Course materials shall include an instructor manual and an instructor laboratory guide with detailed lesson plans for consistent training, a student manual and a laboratory manual with performance exercises to enable students to practice the skills being taught.

  - Instruction shall be comprised of 50 percent lecture and 50 percent lab exercises.

  - Upon training completion, each student shall be able to perform all preventive maintenance, as well as identify, isolate, and correct faults to the LRU level (corrective maintenance).  Students shall understand the functional capabilities and operational concepts of the equipment/system.

- Written exams:

  - Shall be multiple-choice items.  The number of test items shall be sufficient to adequately measure student mastery of all the objectives.

  - Each objective shall have three different versions of each exam item of equal difficulty.

  - Exams shall be such that a student achieving a 70 percent score possesses the requisite knowledge of the equipment/system.

- All students shall be given the opportunity to complete written evaluations during, or at the end of, the conduct of training.

##### Training Development

The Contractor shall develop and conduct this training in accordance with FAA-STD-028C, Contractor Training Programs, and Programs and Technical Operations Training, AMA-400 EHOT-DoP Policy and Procedures.

The Contractor shall revise and maintain all course materials, curriculum materials and courseware until all contractor-conducted training has been completed.  The Contractor shall deliver final training documents and materials in hard copy form and on electronic media files in the latest version of Microsoft Office 2003.

##### Personnel Qualifications Report

The Contractor shall submit a resume of training experience for each person assigned to develop courseware and/or conduct classes under this contract.  Each resume must include the name of organizations where the person developed and/or conducted training, points of contact, including phone numbers, and training dates.

The Contractor shall submit a Personnel Qualifications Report for the training staff in accordance with DID TP-001 prior to the TGC.

CDRL  TP01  Personnel Qualifications Report

##### Task and Skills Analysis

The Contractor shall prepare and submit a Task and Skills Analysis (TASA) Report in accordance with  DID TP-002.  The TASA Report must identify the impact the introduction of the RWSL system equipment and technology shall have on the current work force and identify the skills required to monitor, control or maintain the system.

CDRL  TP02  Task and Skills Analysis Report

##### Training/Course Schedule

The training shall be conducted on an eight-hour academic day, five business days per week schedule.  Course instruction, labs, and testing shall be included in this time frame.  Class instruction periods for lecture will be 50 minutes in duration with a 10-minute break between periods of instruction.  The length of the practical application (laboratory exercises) shall vary as the subject matter dictates.

Start and end times for classes conducted at FAA field locations may vary to accommodate work schedules for FAA personnel.

Class shall not be held on Federal holidays.  Federal holidays shall not be absorbed into the overall course length.  The Government shall establish class start and stop times and class days.

Maximum class size is 8 students of FAA technicians, engineers and/or supervisors, per class.  The student-to-instructor ratio may be no greater than 8-to-1 for classroom training, and no greater than 4-to-1 for lab training.  The number of RWSL systems available for lab exercises will determine the final class size.

The Contractor shall conduct a minimum of 2 classes with additional classes purchased as needed upon successful completion of the Operational Tryout and the First Course Conduct.

The Contractor shall develop course schedule(s) to be included with the student training materials.  The schedule(s) shall provide an overview of the course chronology and shall show the major segments of the course and their time allotments.  The schedule shall be updated throughout the development process as needed.

Government representatives, may at any time, monitor contractor conducted training purchased for this program.

##### COTS Training Materials

COTS training materials may be used for part or all of the training; however, the Contractor must follow the same planning and validation steps as for any other training developed for the Government.  COTS training materials are defined as existing training regularly offered to the general public and/or Government personnel in the course of normal business operations; they are not “on-the-shelf technical documents.”

For COTS training materials, the Contractor shall submit a COTS Training Materials Report in accordance with DID TP-004.  The report must include an assessment of the suitability of the proposed COTS materials against the training requirements identified in the TASA Report.  When COTS materials are proposed for use for FAA training, the contractor shall follow the same planning and validation steps as any other training developed for the FAA and shall match requirements as identified in the TASA.

The proposed COTS training materials must be submitted along with the report.  If the contents do not match the TASA Report, or are unavailable, unacceptable, or do not fully meet the requirements as identified in General Course Requirements of this SOW, the contractor shall develop and submit training to cover the portion of the required training that is not in the COTS materials.

CDRL TP03 COTS Training Materials Report

##### Development of Training Materials

The Contractor shall develop the following documents for this training:

CDRL  TP04  Training Development Plan

CDRL  TP05  Course Design Guide

CDRL  TP06  Test

CDRL  TP07  Classroom Training Materials

##### Student Welcome Packages

All students attending contractor conducted training shall receive prior notification of the content and methods to be used in the training.  This notification shall be provided to the Government, in electronic format, in the form of a Welcome Package and shall include a description of the course contents, directions to the Contractor’s facility, class dates and times, and restaurants for the local area.

CDRL  TP08  Student Welcome Packages

##### Validation of Training Courses

##### Contractor’s Presentation

The Contractor’s Presentation is a formal step in the validation of the training materials in accordance with DID TP-009.  During the presentation, the Contractor shall present a shortened version of each fully developed draft lesson, including draft test items.  Each lesson shall be given in enough detail and depth that the integration and effectiveness of the instructional materials, learning sequence, performance exercise, tests, and the time allocations, can be fully assessed by the Government.

The Contractor’s Presentation shall be conducted at the Contractor’s facility using materials that will be used in the actual training course.  Contractor personnel responsible for the design, development, and technical accuracy of the training materials shall be available during the presentation to answer questions about the course.  Additionally, if the Government requests their presence, the Contractor shall require additional Contractor personnel to include instructor(s), developer(s), and appropriate subject matter experts, available to answer questions during and after the presentation.  Government representatives shall be as identified by the Government.

The Contractor shall correct errors, omissions and deficiencies in student and instructor materials discovered during the Contractor’s Presentation and shall submit corrected copies of the course materials for Government review and approval.  The Contractor shall also ensure that all copies requiring correction are corrected prior to their use in any class.

CDRL  TP09  Contractor’s Presentation

##### Operational Tryout

The Operational Tryout is a continuation of the training materials validation process conducted in accordance with CDRL TP10.  Completed draft lessons are presented to representatives of the target population to determine if the instructional approach is appropriate and effective, test items and time allocations are appropriate, and the format of the materials is easy to use.  Information obtained from the Operational Tryout is used to revise and improve the instructional effectiveness of the materials prior to the First Course Conduct.

The Operational Tryout shall be conducted at the Contractor’s facility and must be planned to last one and a half times the length of the proposed course.  Government representatives selected as monitors shall not count against the class enrollment.  The Contractor shall correct errors, omissions and deficiencies discovered during the Operational Tryout and resubmit materials as directed by the contract.  Subsequent classes shall not commence until a successful Operational Tryout has been conducted and is approved by the Government.

The contractor shall submit an Operational Tryout Report upon completion of the Operational Tryout.  The Operational Tryout class shall not count against the number of classes to be conducted by the Contractor.

CDRL  TP10  Operational Tryout Report

##### First Course Conduct

The Contractor shall provide the First Course Conduct in its entirety in the intended training environment to the target population to ensure the course accomplishes the objectives established in accordance with  DID TP11.  The Contractor shall submit a First Course Conduct Report upon completion of the First Course Conduct class.

Course acceptance shall be contingent upon Government approval of the First Course Conduct Report.  The First Course Conduct class(es) shall not count against the number of classes to be conducted by the Contractor.

CDRL  TP11  First Course Conduct Report

##### Course Evaluations

All students shall be given the opportunity to complete written evaluations during, or at the end of, the conduct of training.  The Government shall provide the evaluation forms to the Contractor for distribution to the students.  These forms may include, but not be limited to, student lesson critiques, time logs, errata sheets, and end-of-course critiques.

During the Operational Tryout and First Course Conduct, the Government shall review the forms and identify necessary changes to training materials.  The Contractor shall incorporate the revisions.  At subsequent course conducts, the Contractor shall administer the designated evaluation forms and forward them to the Government designee.

##### Certificate of Training

The Contractor shall deliver a certificate of training to each student who successfully completes the training.  The certificate shall contain, as a minimum:

- Student name

- Length of training, in hours

- Course number and title

- Location of training

- Date completed

- Issuing official

#### Air Traffic Training

The Contractor will be responsible for the required Air Traffic training elements identified in this section.

##### Air Traffic Scenarios

The Contractor shall provide PC-based, animated scenarios of RWSL in operation on the runway and taxiway.  The scenarios shall demonstrate the timing of illuminating and extinguishing of both REL and THL light arrays to show the air traffic controller how the system operates on the airport.  The scenarios shall be operable within a Windows PowerPoint environment. The Contractor shall provide a CD-ROM with executable and support files in accordance with CDRL TP12.

CDRL  TP12  CD-ROM with Executable and Support Files

##### RWSL Cab Control Panel Trainer

The Contractor shall provide a PC-based software program that will simulate all air traffic functions and displays of the cab control panel, which controls brightness and the on/off function.  The program shall be operated on a laptop computer with touch-screen capability to accept controller input and then reflect the status of the input. The Contractor shall provide a CD-ROM with executable and support files in accordance with CDRL TP12.

##### Installation Point of Contact Training

This course shall support installation point of contacts by providing a high level familiarization and general overview of the RWSL system.  Training materials shall be prepared in accordance with TP07, Classroom Training Materials.  The Contractor shall (1) Apply best commercial practices, (2) Provide modular training, ensuring that each module shall address a single major topic or several closely related topics, and (3) Develop instructional media materials in support of training

For COTS training materials proposed and approved by the Government, the Contractor will conduct one with the option for two additional courses.

#### Second Level Engineering Training

The Contractor shall provide second level engineering training services including training equipment (e.g., tools, test and support equipment) to the Program Support Facility (PSF) at the Mike Monroney Aeronautical Center in Oklahoma City, Oklahoma.  The system or equipment shall duplicate to the maximum extent possible the actual operating environment.

This course shall support the PSF, NAS Engineering, ATO-W, by providing advanced user training and software instruction necessary to maintain the RWSL system.  Training materials shall use best commercial practices. Training content shall ensure that NAS Engineering personnel achieve a level of competency needed to perform their respective duties.

Training shall be modular in nature.  Each module shall address a single major topic, or several closely related topics, as contained in the training outcomes, which provide a logical training sequence. The Contractor shall correct any errors, omissions, and deficiencies in the revised course materials, which were discovered during the Government review prior to training.  Classroom instruction shall be supported by lab exercises.

A Government furnished End-of-Course Evaluation Questionnaire will be submitted to students at the conclusion of training.  Completed questionnaires shall be submitted to ATO-W.

The Government will maintain all training equipment in operable and usable condition during the training course except for planned disassembly and fault isolation training exercises.  The Contractor shall notify the Government immediately if training equipment is inoperable and/or unusable.  If Contractor furnished training equipment is to be returned to stock for subsequent delivery to the Government, the Contractor shall keep configuration management records on the equipment in accordance with ISO 10007:2003. Any training aids, demonstration items, charts, and mock-ups used in training shall be provided to the Government at the conclusion of Contractor training.

The Contractor shall provide Course Materials in accordance with DID TP-007.

##### Technical Interchange Meetings

TIMs may be held to discuss in detail any training issues that require mutual resolution or further clarification.  The Contractor shall attend and provide expertise to the Government, as well as access to the vendor’s system and expertise. Refer to 3.1.7.4 for TIMs.

#### Contractor Support and Services

The Contractor shall provide support and services in accordance with the provisions in this SOW for complete supply support which includes stocking, storing, issuing, receipting of LRUs and the repair of returned LRUs from the field, and stocking, storing and issuing site level consumables.

The Contractor shall provide site, depot and second level engineering support services as described in this SOW.

##### Definitions

The following definitions are applicable and are included for information only:

  - Exchange and Repair Item. Any hardware LRU, except expendable, when unserviceable, is returned to the Contractor after a serviceable replacement. The designation of an item of supply as Exchange and Repair (E&R) indicates the logistic status assigned for inventory management purposes rather than the physical condition of an item. A serviceable item is sent from the Contractor to a Government facility upon request by the FAALC inventory manager and an unserviceable item is returned to the repair facility (Contractor) in exchange for the serviceable item, unless otherwise authorized. In most cases these items will consist of critical supply LRUs (i.e., high value and/or special manufacture).

  - Expendable Item. Any hardware LRU, except E&R, that can be removed and replaced to restore the system. An expendable LRU possesses characteristics, qualities, and low cost that make it uneconomical to restore the defective LRU.

  - Line Replaceable Unit. An LRU is defined as an item that may consist of a unit, an assembly (circuit card assembly, electronic component assembly, etc.), a subassembly, or a part, that is removed and replaced at the site maintenance level to restore the system/equipment to its operational status.  An LRU can be either an E&R item or an expendable item.

  - Piece Part.  The lowest replaceable item of an assembly or SRU removed or replaced at an intermediate or depot maintenance level.

  - Repairable. The condition of an item that can be returned to service after repair or rework in accordance with  procedures, tolerances, and limits established by the overhaul and repair instructions issued by the item manufacturer, or as otherwise authorized under the provisions of the Government regulations.

  - Serviceable. The condition of an item in a good state of preservation that can be placed in service  in accordance with applicable manufacturers overhaul limits and instructions and/or pertinent regulations of the Government without repair.

  - Shop Replaceable Unit.  An SRU is defined as an item that may consist of a unit, assemblies, and piece parts.  An LRU may consist of one or several SRUs.

  - Test. A test or check of equipment in its operational (or functional) environment, using equipment, procedures, and limits specified in applicable authorized manufacturer publications, manuals, and specifications and technical orders or Government authorized changes in procedures and limits.

##### Key Site Support

The Contractor shall provide full maintenance support at the RWSL key site.  This support shall include site level maintenance, depot repairs, and second level engineering support.  On-site maintenance will be under a separate delivery order of this contract. The Contractor shall provide inclusive maintenance support prior to initial operating capability, with the exception of the key site as well as maintenance support through commissioning of the key site.

##### Second Level Engineering Support

The Contractor shall provide on-call maintenance support to the Government. On-call hardware support shall consist of providing assistance in resolving problems or providing additional expertise should unexpected problems develop. Software on-call maintenance shall be directed toward resolution of software problems until the establishment and operations of the PSF. It is anticipated that after the establishment of the product baseline, the accumulation and the simultaneous implementation of routine software changes will be minimized with a corresponding limit of interim software versions and related documentation changes. The Contractor shall be responsible for maintaining the production RWSL software, investigating software problems, and incorporating approved software changes until such time as control of changes is passed to the PSF. The Contractor shall provide the necessary materials required for this effort. This shall include all software and procedural documentation required for the development, generation, modification, CM, maintenance, testing, analysis, and debugging of all RWSL software, as specified in the contract.

Second level engineering support services shall include:

- Services for the restoration, integration, optimization, and maintenance of the system

- Site restoration assistance to field personnel.

- Development, prototype and production assistance, testing, and   introduction of engineering solutions in response to problem reports and approved case files.

- Configuration and documentation maintenance, release, and control.

- Assuring the supportability of system software releases before they are deployed into the NAS.

The hardware and software engineering support service shall be available during normal business hours, 40 hours per week.  The Government may require support services outside normal business hours during the week and including weekends.  Criticality of the RWSL system is essential.  The Contractor shall certify that all Contractor personnel are fully trained and qualified to provide the above engineering support services.  Training for all engineering support services shall be the responsibility of the Contractor.

#### Interim Contractor Depot Logistics Support Requirements

The following requirements apply to Interim Contractor Depot Logistics Support (ICDLS):

  - The Contractor shall provide ICDLS for the RWSL systems throughout the duration of this contract. This shall include stocking, storing, issuing, and shipping expendable, consumable and repairable items.

  - Those items covered by warranty shall be replaced at no cost to the Government.

  - The Contractor shall repair, as required, all repairable Exchange and Repair (E&R) LRUs returned from FAA field sites. This repair cost shall not exceed 65% of the cost of a new item, unless approved by the contracting officer.

  - The Contractor shall furnish all labor, tools, test equipment, parts, software, and any other technical or administrative support necessary to provide the required ICDLS.

  - The Contractor shall be required to provide depot level support 7 days a week, 24 hours a day, to meet a priority one request from the field.  The government will designate the priority as follows:

    - Priority 1 is used when either the prime or standby equipment is inoperative or when a facility is operating at a reduced performance that adversely affects ATC operations.  Shipment to the designated facility is to be within 24 hours, including weekends and holidays, after notification by the Government’s authorized representative.

    - Priority 2 is used when a facility is operating with substandard equipment or operating conditions indicate imminent facility failures or outage.  Shipment to the designated facility is to be received within 48 hours after receipt of notification by the Government’s authorized representative.

    - Priority 5 is used with a routine requirement or stock replenishment.  Shipment to the designated facility is to be received within eight days after receipt of notification by the Government’s authorized representative.

##### E&R LRU Repair Procedure

The following requirements apply to E&R LRU Repair Procedures:

- E&R items shall be repaired to the extent necessary to restore them to a condition in which the items are capable of meeting all operational and functional requirements for which they were designed.

- Any modification to items required by the contract and  not previously accomplished shall be made by the  Contractor at the time of repair.

- All property removed during repair shall become the property of the government.  Disposition of removed parts shall be at the direction of the Contracting Officer.  Unusable parts are those items that cannot be placed in service without the item itself being repaired.

##### Depot and Lay-in Spares

The Contractor shall lay-in and maintain a quantity of spares to support the availability rate defined in the RWSL System Specification FAA-E-3001. Initial lay-in will be funded by the Government and will be controlled as GFP/GFE. Replenishment of piece parts will follow established/approved policy as funded and authorized by the contracting officer. The Contractor shall maintain an inventory listing of these repair items to include:

- Part number and manufacturer's cage code

- Nomenclature or description

- Quantity

- Unit of issue or Unit Ordering Quantity (UOQ)

- National Stock Number

##### Contract Repair Service Status Reporting

The Contractor shall provide a monthly repair service status report. These status reports shall contain the following information on failed LRUs:

- Part number

- Serial number

- Description

- Site

- Date of request for repair

- Date of shipment from site to repair facility

- Date of repair

- Date of shipment

- Contractor's shipping number

- Failure analysis

Failed components replaced in the repair process, shall be identified by part number, quantity, probable cause of failure (including identification of failures that cannot be duplicated), and be tracked back to the failed LRU. The monthly failure report shall also include cumulative failure information for each contract year, mathematical calculations of observed availability by LRU type, and statistical data that show repair trends, common failures, and site comparisons.

CDRL  RP02  Contractor Repair Service Status Reports

##### Obsolete Parts Program

To properly advise the Government of the status of parts used in the production systems, the Contractor shall implement an obsolete parts program.  This program shall include the maintenance and update of a parts database, similar to a SMART database, of microcircuits and semiconductor devices and a forecast of their lifecycle.  The results of this assessment shall be reported at PMRs.

Obsolete parts replacement shall be in accordance with Section H.26.  All documentation acquired with the purchase of the obsolete replacement parts, including, but not limited to data, drawings and test results, shall be furnished to the Government as change pages to existing Technical Instruction Books.

#### Post-Commissioning Technical Site Support

The FAA will be responsible for site-level maintenance for each site after it reaches commissioning. When notified by the Government, the Contractor shall provide assistance to resolve any RWSL site maintenance or logistics problem. These services may vary from phone consultation to Contractor on-site activities. If a Contractor on-site presence is required, the Contractor shall arrive at the site no later than 24 hours after notification that Contractor on-site assistance is necessary. The Contractor shall provide the number of skilled personnel, support equipment, and RWSL LRUs/components necessary to return the RWSL to its operational performance level as specified in the RWSL specifications.

##### Contractor Transition Plan

The Contractor shall prepare for Government review and approval a Contractor Transition Plan (CTP). The CTP establishes the procedures and means for the orderly transfer of the system support and maintenance management activities from the Contractor to the FAA. The CTP shall detail the activities that the Contractor shall undertake to ensure a smooth transition from Contractor to Government operations, and the preparations, facilities, and personnel that the Government will require to assume responsibility for the conduct of all or some maintenance and logistics services provided by the Contractor. The CTP shall include an itemized list of Government-owned hardware/software used during development that will be transferred to the FAA.

CDRL  LM07	  Contractor Transition Plan

#### System Support Equipment/Facilities Services

##### Special Test Equipment

The Contractor shall provide special test equipment and items required for operation, use and maintenance including cables, and operation, maintenance and vendor data manuals. Documentation shall be delivered concurrently with special test equipment. Electronic media, programs, or documentation required for data analysis shall be provided with electronic test equipment.

##### Program Support Facility

The Contractor shall plan, install and establish an RWSL PSF at the Mike Monroney Aeronautical Center, Oklahoma City.  The physical facility will be provided by the Government. The PSF shall include those portions of the RWSL system, equipment, supporting software, firmware, and documentation (including revisions and upgrades) required for the generation, maintenance, testing, analysis, and debugging of all the functional software in accordance with the RWSL System Specification and FLS Specification. Operation, maintenance and vendor data manuals for PSF equipment shall be provided in accordance with FAA-D-2494B concurrent with the PSF delivery. The PSF shall execute the RWSL operational software, hardware, firmware and documentation to validate programs (and associated tests) for test and debugging purposes. The PSF shall provide the capability to modify the resulting changes. Non-COTS software shall include Contractor-developed software and any implemented GFP software. PSF personnel will be provided the training to read, manipulate, evaluate, and display field-recorded time series and data. The Contractor shall ensure that all appropriate Computer Aided System Engineering (CASE) tools are in place and operational at the PSF, prior to transition of the Software Maintenance effort from the Contractor to the PSF.  The PSF shall be established after a successful PCA/FCA and prior to CAI.

##### Software Transition Plan

The Contractor shall plan for transition of life-cycle support of the RWSL software to the Government using FAA-STD-026 as guidance. The Contractor shall identify the hardware, software, and other resources needed for life cycle support of deliverable software and describe the Contractor's plan for transitioning deliverable items to the Government. Resources shall include the programming environment, peripherals, memory, compilers, assemblers, and linkers for all non-COTS software. The Contractor shall use existing documentation when it is available and meets the data content intent of FAA-STD-026.

CDRL  SW07  Software Transition Plan

##### Second Level Engineering Tools and Equipment

The Contractor shall provide the second level engineering tools identified by the Contractor such as system performance tools and site adaptation generation tools.

##### Software Tools and Source Code

The Contractor shall provide two licensed copies of all software development tools identified in the Software User Manual that were not delivered in CLIN 001, or that have changed since CLIN 001 delivery.

The Contractor shall provide source code, as updated, to include changes described in Section 3.3.1.9, for all non-proprietary, Contractor-generated RWSL operational, support, including developmental, tools, second level engineering tools, simulation computer, and test support software including source code listings. Source code and source code listings shall be provided as part of the Software Product Specification, CDRL SW06.  The Contractor shall also provide all software programs used to develop required test data, technical design data, or documentation data. Software development files shall be included.  In addition, the Contractor shall provide all software programs necessary to load, analyze, modify, reassemble, and reproduce the system's executable software and/or firmware.  The Contractor shall provide above software programs as part of the SDD.

The Contractor shall identify the specific software components that are proprietary.  All proprietary software used during the linking process shall be included in executable form.  Software development tools used such as compilers, linkers, and libraries shall be included.  Instructions for building the RWSL, second level engineering tools, and simulation computer software using the source code, software development tools, and proprietary executables mentioned above shall be included.

Flow charts and fully documented source code listings and object code for all Contractor-developed software and firmware shall be provided on CD-ROM in accordance with CDRL SW06.

##### Computer Programmer’s Manual

The Contractor shall develop a Computer Programmer’s Manual (CPM) that will provide maintenance programmer personnel with information necessary to effectively maintain each Computer Program Configuration Item (CPCI) of the RWSL.  The CPM shall include development tool installation and setup, CPCI build procedures, and firmware programming/CPCI installation instructions.  The CPM shall identify the software programming environment, peripherals, memory, compilers, assemblers, and linkers.  All software development tools including hardware and software shall be identified.  The CPM shall satisfy the task oriented instruction mode requirements of FAA-STD-026A.  The Contractor shall validate the CPM.

CDRL  SW08  Computer Programmer’s Manual

#### Contractor Support Services

This section further defines the scope of the time and materials provisions in Section H of this Contract. The Government will use Contractor Support Services for second-level support of the RWSL system, excluding Contractor depot level maintenance.

At the request of the Government, the Contractor shall provide support at Government sites, the Contractor's plant, or elsewhere, in specific areas including, but not limited to:

- Telecommunications network applications, planning, design, engineering, hardware, installation, and operation;

- RWSL problem investigation (e.g., communications, hardware, software, firmware);

- Planning, implementation, maintenance, and/or update of RWSL system;

- Non-envisioned or catastrophic repair of RWSL equipment;

- Field Modifications or retrofit activities;

- Porting of Geographic Situation Display and Ribbon Display Terminal functionality to different COTS hardware platforms;

- Graphical User Interface modifications;

- Development of a remote RWSL Maintenance Data Terminal;

- Additional interface development and modifications;

- Additional hardware, as required, needed to support the RWSL program;

- Software development;

- Review of RWSL operational modes and procedures; and,

- On-site maintenance.

The Contractor shall provide qualified engineering and technical personnel for these services as necessary to complete assigned tasks. These services shall be provided on a time and material basis with the Contractor indicating any incidental hardware required to perform services not otherwise covered in the RWSL contract.

Tasks shall be preceded by an estimate of the time, material, and corresponding cost from the Contractor at the request of the Government. Tasks shall begin after written Government authorization has been received.

## Full Production and Deployment Requirements

The Contractor shall produce, update, test, deliver, install, and optionally support the Full Production RWSL in accordance with the specifications, associated interface documentation, and the requirements cited in this SOW.  This includes production of hardware, software adaptation for each site, integration of software on hardware platforms, delivery of the system to the designated site, construction, installation and checkout of the full RWSL system, test and evaluation (SAT) and Government acceptance.

In addition, the Contractor shall also provide continued program management functions (configuration management, data management, quality management, security, risk management, EVMS, IMS, PMRs and PSRs); depot logistics support, maintenance, second level maintenance, and residual training; and set up of the Government depot and program support facility in accordance with the approved Interim Contractor Depot Level Support (ICDLS) Transition Plan (ICDLSTP); and set up of the RWSL training system at the FAA Academy.

### Depot Setup

The Contractor shall furnish all labor, tools, test equipment, hot test bench, parts, software, documentation, training and any other technical or administrative support necessary to transition the required depot level logistics support to the FAALC.  The physical facility will be provided by the Government. The depot system shall include those portions of the RWSL system required for the performance of depot level repair activities. Depot training course materials shall be developed in accordance with CDRL and DID TP07.

### Interim Contractor Depot Level Support Transition Plan (ICDLSTP)

The Contractor shall prepare and provide to the Contracting Officer an ICDLSTP. The ICDLSTP shall detail the activities required to ensure a smooth transfer of the RWSL ICDLS operation from the Contractor to the FAALC. These activities shall include the preparations, facilities, and personnel that the FAALC will require to assume responsibility for the conduct of the RWSL repair services. The ICDLSTP shall recommend the time required to ensure a smooth transition with minimal interruption to repair activities. The ICDLSTP shall be in the Contractor's format and shall include, but not be limited to, recommendations for the following items:

- Formal/on-the-job training/familiarization required to support the repair functions.

- Duration and type of Contractor support required, if any, at the FAALC facilities during the transfer or FAALC repair startup.

- Disposition of lay-in stock, to include all accounting records.

- Operating methods to be employed to assure repair service during the transition period.

- Method or procedures of transitioning management of the vendor/OEM repair contracts to the FAA.

- Approximate cost of managing vendor repair subcontracts for the life cycle of the system.

- Preservation, packing, packaging and marking of any items shipped to FAALC in accordance with MIL-STD-129P (Marking for Shipment and Storage); and AIM-BC1 Uniform Symbology Specification Code 39.

- Recommendations for additional equipment, processes, and documentation which would be beneficial to the FAALC operation of the transitioned Contractor Repair Service.

#### Tools and Test Equipment List

A list of recommended support items is required.  These are items that are not an integral part of the end item but are required to inspect, test, calibrate, service, repair or overhaul the RWSL system and any of its components.  The Contractor shall provide the Tools and Test Equipment List in accordance with DID LM-008.

CDRL  LM08  Tools and Test Equipment List

#### Depot Test Equipment Manuals

For each unit of test equipment, a maintenance manual is required.  The manual should contain, at a minimum, procedures and guidelines for the maintenance of software, interface devices/fixtures and documentation included in each automated test equipment (ATE) test program set.  Instructions shall contain procedures and guidelines for the maintenance and/or modification of any in-circuit board test program and component models, including source code written for custom test and test not included in the standard board test libraries.  The manuals shall be provided in accordance with DID LM-009.

CDRL  LM09  Depot Test Equipment Manuals

#### Depot Test Procedures

Procedures are required for the operation, maintenance and overhaul of the RWSL system.  Use of existing repair manuals and documentation is encouraged to the maximum extent possible. The Contractor shall provide Depot Test Procedures in accordance with DID LM-010.

CDRL LM10  Depot Test Procedures

#### Depot Repair/Support Training

The Contractor shall develop a component-level training program on Shop Replaceable Units (SRUs) and LRUs that make up the system, which includes training to the FAA Logistics Center at Oklahoma City, Oklahoma.  The training shall include the following:

- Repair procedures and depot-level specifications.

- Use of special tools and test equipment, operational system troubleshooting and repair techniques.

- Operation and maintenance of peculiar test equipment.

- New or modified automated test equipment (ATE).

- RWSL-unique commercial test equipment, diagnostic test-beds and software operations in support of the repair and maintenance of the SRUs and LRUs.

The ATE training shall be a separate training module.  The students for the ATE training may not necessarily be the same students as for the component-level training.

The FAA Logistics Center (FAALC) will maintain all training equipment in operable and usable condition during the training course except for planned disassembly and fault isolation training exercises.  The Contractor shall notify FAALC immediately if training equipment is inoperable and/or unusable. If Contractor furnished training equipment is to be returned to stock for subsequent delivery to the Government, the Contractor shall keep configuration management records on the equipment in accordance with FAA-STD-021, paragraph 4.9. Any training aids, demonstration items, charts, mock-ups, etc., used in training shall be provided to the Government at the conclusion of Contractor training.

### FAA Academy Training Support System

The Contractor shall deliver and install an RWSL system at the FAA Academy in Oklahoma City.  The physical facility will be provided by the Government. The training support system will include those portions of the RWSL system required to conduct the site level hardware training course.

## Acronyms

AC	Advisory Circular

ACC	Airport Construction Coordinators

AF 	Technical Operations

ALP	Airport Layout Plan

AMS	Acquisition Management System

AOA	Airport Operations Area

APML 	Assistant Program Manager for Logistics

ASDE-X	Airport Surface Detection Equipment Model – X

AT	Air Traffic

ATC	Air Traffic Control

ATCT	Air Traffic Control Tower

ATE	Automated Test Equipment

CAI	Contractor Acceptance Inspection

CASE 	Computer Aided System Engineering

CCB	Configuration Control Board

CDR	Critical Design Review

CDRL	Contract Data Requirements List

CDROM	Compact Disc Read Only Memory

CFSR	Contract Funds Status Report

CI 	Configuration Item

CM	Configuration Management

CMP 	Configuration Management Plan

CMTP	Contractor's Master Test Plan

COTR	Contracting Officer's Technical Representative

COTS 	Commercial Off-the-Shelf

CPCI	Computer Program Configuration Item

CPM	Computer Programmer’s Manual

CPR	Cost Performance Reports

CSAR	Configuration Status Accounting Report

CSC	Computer Software Components

CSCI 	Computer Software Configuration Item

C/SCSC	Cost/Schedule Control Systems Criteria

CSER 	Contractor Site Engineering Report

CSU 	Computer Software Unit

CTP 	Contractor Transition Plan

CWBS	Contract Work Breakdown Structure

DFU	Display Functional Unit

DOD	Department of Defense

DQT 	Design Qualification Test

DT	Development Test

DT&E 	Developmental Test & Evaluation

E&R	Exchange and Repair

ECP 	Engineering Change Proposal

EMI	Electromagnetic Interference

EVMS	Earned Value Management System

FA	First Article

FAA 	Federal Aviation Administration

FAALC	FAA Logistics Center

FAST	FAA Acquisition System Toolset

FAT 	Factory Acceptance Test

FCA 	Functional Configuration Audit

FCC	Federal Communications Commission

FDQT	Factory Development Qualification Tests

FDR	Final Design Review

FLS	Field Lighting System

FOD	Foreign Object Damage

FQT 	Formal Qualification Test

GFE 	Government Furnished Equipment

GFI	Government Furnished Information

GFP	Government Furnished Property

GUI	Graphical User Interface

HEDA	Human Engineering Design Approach

HEDA-M	Human Engineering Design Approach for Maintainers

HEDA-O	Human Engineering Design Approach for Operators

HF	Human Factors

HFE	Human Factors Engineering

HVAC	Heating, Ventilation and Air Conditioning

HWCI 	Hardware Configuration Item

IBR	Integrated Baseline Review

ICD	Interface Control Document

ICDLS	Interim Contractor Depot Level Support

ICDLSTP	Interim Contractor Depot Level Support Transition Plan

ICS	Interim Contractor Support

IDD	Interface Design Document

IGES	Initial Graphical Exchange Specification

ILS 	Integrated Logistics Support

ILSMT 	Integrated Logistics Support Management Team

IMS	Integrated Master Schedule

IPR	In-Process Reviews

IRD 	Interface Requirement Document

ISO 	International Standards Organization

ISP 	Integrated Support Plan

LCN	LSA Control Number

LGC 	Logistics Guidance Conference

LMI	Logistics Management Information

LORA	Level of Repair Analysis

LP	Limited Production

LRU 	Line Replaceable Unit

LSA	Logistics Support Analysis

LSAP	Logistics Support Analysis Plan

LSAR	Logistics Support Analysis Record

MDT	Maintenance Data Terminal

NAS 	National Airspace System

NCP	NAS Change Proposal

NDI 	Non-Developmental Item

NEPA	National Environmental Policy Act

NOR 	Notice of Revision

NTSB	National Transportation Safety Board
O&SHA	Operating & Support Hazard Analysis

OEM	Original Equipment Manufacturer

PAT&E 	Production Acceptance Test & Evaluation

PCA 	Physical Configuration Audit

PDR	Preliminary Design Review

PHA	Preliminary Hazard Analysis

PM	Program Manager

PMP	Program Management Plan

PMR 	Program Management Review

POC	Point of Contact

POSIX	Portable Operating System Interface

PQT	Preliminary Qualification Test
PQY	Preliminary Qualification Test

PROM	Programmable Read Only Memory

PSF 	Program Support Facility

PSR	Program Status Reports

QSP 	Quality System Plan

RAR	Risk Assessment Report

RDT 	Ribbon Display Terminal

RE	Resident Engineer

REL	Runway-Entrance Light

RM	Risk Management

RMA	Reliability, Maintainability, and Availability

RMP	Risk Management Plan

ROM	Read Only Memory

RWSL	Runway Status Lights

SDD 	Software Design Description

SDM	Software Diagnostics Manual

SDP 	Software Development Plan

SDQT	Site Development Qualification Test

SHA	System Hazard Analysis

SMR	Source, Maintenance and Recoverability

SMS	Safety Management System

SOW 	Statement of Work

SPP	Security Program Plan

SPR	System Problem Reports

SPS 	Software Product Specification

SRMGSA	Safety Risk Management Guidance for System Acquisitions

SRMP	Safety Risk Management Panel

SRR	System Requirements Review

SRU	Shop Replaceable Units

SSAR	System Safety Assessment Report

SSDD	System/Subsystem Design Description

SSHA	Sub-System Hazard Analysis

SSPP	System Safety Program Plan

STD 	Software Test Description

STP 	Software Transition Plan

SUM	Software User Manual

SVD 	Software Version Description

TASA	Task and Skills Analysis

TDP	Training Development Plan

TGC	Training Guidance Conference

THL	Takeoff-Hold Light

TIM 	Technical Interchange Meeting

UOQ	Unit Ordering Quantity

UPS	Uninterruptible Power Supply

VRTM 	Verification Requirements Traceability Matrix

WBS	Work Breakdown Structure