## -CHANGE REQUEST COVER SHEET

## Change Request Number: 06-25

## Date Received: 3/7/06

Title:  GAO Findings Response and Standard FAA Program Milestones

# Name: David Woodson

Routing Symbol:  ATO-A, Acquisition and Procurement Policy Branch

Phone: 267-7601

Policy OR Guidance: Guidance

Section/Text Location Affected: Multiple

Summary of Change: This change proposal includes the following:

Guidance

- Establishes guidance for evolutionary product development.

- Establishes guidance for the FAA’s knowledge-based product development process for systems.

- Establishes guidance that identifies and defines standard program milestones for systems (sheet 1) and facilities (sheet 2).

- Adds to the introduction of the contracting module in the developmental hardware and/or software process flowcharts the requirement to include in any prime contract for system development those deliverables necessary for an investment program to satisfy decision criteria for transition from product integration to product demonstration and from product demonstration to full production.

- Modifies the development process flowcharts in FAST for developmental hardware and/or software to add the product demonstration decision.

- Modifies the implementation process flowcharts in FAST for developmental hardware and/or software to add the production decision.

Reason for Change: GAO Report 05-23, FAA’s Acquisition Management Has Improved, but Policies and Oversight Need Strengthening to Help Ensure Results, made the following recommendations for improving the FAA Acquisition Management System:

- Develop explicit written criteria for key decision points called for under best practices 1, including the capture of specific design and manufacturing knowledge

- Require corporate executive-level decisions at these key decision points (before an acquisition moves from integration to demonstration and again before it moves to production)

1 GAO Report 02-701, Best Practices, Capturing Design and Manufacturing Knowledge Early Improves Acquisition Outcomes.

The FAA Acquisition Executive agreed to implement the decision points and associated criteria, but stated that the decision-maker would be the Vice President or Director of the implementing service organization, as appropriate.

The change request also includes standard FAA program milestones requested by the ASAG Secretariat.

Development, Review, and/or Concurrence: Policy and guidance was developed by the GAO Response Team, established by the ASAG, with representatives from ATO-A, ATO-F, ATO-P, ATO-E, ATO-T, ATO-W, and ATO Quality Assurance.

Target Audience: AMS workforce

Potential Links within FAST for the Change: Multiple links between the new policy and guidance.

#### Attachments: KBDM – EPD Policy 02-06, KBDM – Final Investment Decision, KBDM – Final Investment Analysis, KBDM – Solution Implementation, KBDM Guidance R6, Evolutionary Product Development Guidance, KBDM – Contracting Activity Description, KBDM – Product Demonstration Decision, KBDM - System Integration Activity Descriptions, Program Milestones R3.

### ASAG Briefing Conducted: 3/7/06

ASAG Responsibilities: Review, comment, and endorse.

| FAST HOME | HELP | WHAT'S NEW | COMMENTS | SEARCH |
| --- | --- | --- | --- | --- |

GUIDANCE

System Process Flowcharts / System Development Work Activities (Revised 10/2005) Industry / Government Partnership System development work activities span the period from the final investment decision to the completion of the Design Qualification Test when the government accepts the development product from the contractor. The most important event in this entire process is selection of the developmental contractor and formation of the government / industry partnership. Both the government and contractor are stakeholders in the process, and it is vitally important to establish and maintain a positive working relationship. Neither can succeed without the other, and each has its own challenges and constraints. The government is the customer and senior partner in the enterprise. The government brings all team members to the table and integrates the diverse activities associated with system development, implementation, and lifecycle support. As the government’s agent, the Service Team focuses on technical leadership, the government / industry partnership, and overall program integration and management. Contractors and subcontractors, on the other hand, focus more on the very detailed engineering aspects of the system and its interfaces. Development contractors are faced with certain very real constraints that the Service Team must allow for. Companies cannot afford to have large teams of engineers sit idle waiting for a contract they may not receive. A significant amount of time is needed after contract award to form the developmental team. This effort is especially important during the initial phases of a system development, and is seldom taken into account by the government when planning contract schedules. The Service Team needs to recognize this condition and allow time for the contractor to 'gear up'. Government planners must also allow adequate time for a thorough analysis of requirements. In an effort to meet unrealistic early milestone dates, contractors often short change this analysis and fail to achieve a clear, mutual understanding of requirements with the government. Studies have shown conclusively that omissions occurring in the requirements analysis phase have a disproportionately greater effect on program cost and schedule than errors occurring in later phases. As a rule of thumb, it costs ten times as much to fix a problem after production than during design and development. Management and Assessment of the Engineering Development Process Programs rarely fail because of deficiencies in technology. Most failures stem directly from inadequate management. Everyone involved in program management must take a "proactive" role to ensure the deployment of a successful system. Each government employee must think beyond his or her individual piece of the system and take action to identify and meet challenges before they enlarge into serious problems. It is tempting to get down into the details and sometimes it is necessary. But Service Team members must take a broader view, and should perform the critical higher-level tasks of managing, assessing, integrating, and taking action to solve problems when they arise. It is critically important for the Service Team to insist on successful completion of early development activities, such as design of the system architecture and completion of critical design, and not allow the program to progress for the sake of "maintaining schedule". Proceeding to such activities as source code development without a sound overall system / software architecture usually results in a great deal of fruitless work, and has resulted in complete failure of entire investment programs. The key to a successful system investment program is the integration of all associated engineering disciplines into an efficient, coherent process that achieves the development of equipment that meets user requirements. Even when there is an "integrating contractor", the government must work very hard at achieving harmonious orchestration. The engineering management process depicted in this section governs and controls product development. It addresses all key aspects of total system performance (such as security, logistics support, and configuration management), and provides a technical baseline for program planning and execution. Its primary function is to provide a management and engineering framework with which the Service Team can structure developmental activity that will result in a product that meets cost, schedule, and performance objectives over the entire product lifecycle. The following are examples of contractor activities that Service Team members will find themselves overseeing and guiding during this intricate and detailed process: Trade-off studies among requirements (operational, functional, performance), design alternatives (and their related manufacturing, testing, and support processes), schedule, and lifecycle cost; Risk management to identify, evaluate, assess, and mitigate potential sources of risk associated with the contractor’s design, manufacture, test, and support approach; Configuration management of system products, processes, and related documentation. This effort includes identifying, documenting, and verifying the functional and physical characteristics of an item; recording its configuration; and controlling changes to the item and its documentation; Integrated data management to capture and control the technical baseline (configuration documentation, technical data, and technical manuals); provide traceability among requirements, designs, decisions, rationale, and other related program planning, reporting, and support configuration procedures; and serve as a ready reference for the systems engineering effort; The determination of metrics for use as measures of technical progress relative to what was planned in the areas of performance, risk mitigation, cost, and schedule. Performance measures must be traceable to performance parameters in the Program Requirements attachment to the Exhibit 300 Program Baseline and System Specification; The establishment of interface controls to ensure changes to all internal and external interface requirements are properly recorded and communicated to all affected configuration items; and The development of a structured review process that demonstrates and confirms completion of required accomplishments and their exit criteria, as defined in program planning. Assessing and Reporting Progress Rigorous internal program control systems are essential to effective and accountable program management. They enable acquisition functions to be performed efficiently and effectively by maximizing the use of resources. The focus should be on results, not process. One key to tracking cost, schedule, and technical performance is the application of Earned Value Management. Another is to ensure the individuals responsible for day-to-day management of the acquisition contract have ownership of and are responsible for their elements of the Work Breakdown Structure. When this approach is taken, the Service Team is more likely to achieve full integration of cost, schedule, and technical performance within the quantifiable terms of earned value – and not just rely on the completion of technical or schedule events or milestones. One of the most important outputs of Earned Value Management is reliable, timely, and quantifiable data that enables the Service Team Lead to accurately determine the Estimate at Complete (EAC). Historically, a lack of understanding of information in Contract Performance Reports or the processes and methodology used to generate them have made it difficult for the Service Team Lead to make critical program decisions. Knowing how the contractor earns value for a particular element of work allows the Service Team to manage their areas of responsibility with confidence. Providing Direction Sound direction from the government comes only from accurate assessment of where the program is compared to where it is supposed to be. Periodic program management reviews using Earned Value Management techniques provide a mechanism for determining where you are. With this information, the Service Lead can provide confident direction to each contractor and team member involved in the development program. Activity: Approve Contractor Management Plans D-1 Responsible Agent Product Approval Authority Tools and Aids Contractor develops Service Team specialists review and comment Approved contractor management plans Service Team Description: Soon after contract award, the Service Team reviews and comments on contractor management plans, which become part of the contractor’s management baseline after approval. Changes to these documents are coordinated with the Service Team before being implemented by the contractor. Examples of contractor planning documents include: Project Management Plan, System Engineering Management Plan, Software Development Plan (including quality assurance processes), Configuration Management Plan, Integrated Logistics Support Plan, Test Plan(s), Specialty Engineering Plan(s), and Subcontractor Management Plan. For software-intensive programs, the Software Development Plan is crucial. The quickest, cheapest way to build quality software is to avoid mistakes during development, and to remove errors early in design before beginning the coding. The driving factor behind successful software-intensive systems is software quality rather than simply cost or schedule. Quality software development depends on the use of sound software management processes and procedures. The contractor’s Software Development Plan should be scrutinized carefully to ensure sound software management practices are established and being used by the company. Go to http://sepo.nosc.mil/ and select the "SQA" menu item for some good tools on software quality assurance plans, processes, and procedures. Activity: Oversee System Requirements Analysis D-2 Responsible Agent Product Approval Authority Tools and Aids Contractor performs Service Team specialists oversee Revised System Specification Preliminary System, Segment Specification Interface Control Documents (Segment to Segment) Service Team lead engineer Description: System requirements analysis develops technical requirements for hardware, software, facilities, personnel, procedures, technical data, personnel training, verification matrices, spares, repair parts, and consumables needed to test, deploy, operate, and maintain a system. System requirements analysis is performed iteratively throughout the acquisition management lifecycle, beginning with development of preliminary program requirements during concept and requirements definition. During final investment analysis, system requirements analysis translates the functional, performance, and interface requirements in the Program Requirements attachment to the Exhibit 300 Program Baseline into a System Specification for use in the prime contract solicitation package. After contract award, the Service Team oversees and generally supports contractor assessment of system specification requirements and identification of technical risks associated with satisfying those requirements. Contract specifications are reviewed in great detail during this analysis through user interviews, simulations, prototyping, demonstrations, or any activity that gives confidence the requirements are well understood and well defined. This activity provides the basis for defining the entire system, its components and their interrelationships, as well as for providing a foundation for measuring the extent to which program requirements, objectives, and priorities are satisfied by system design. System requirements analysis typically involves: Assessing / refining system specification requirements; Identifying segments and allocating requirements to segments (i.e., Hardware Configuration Items (HWCIs), Computer Software Configuration Items (CSCIs)); Defining design constraints; and Defining and supporting external interfaces. It is extremely important for the Service Team to allow adequate time in the program schedule for the contractor to "gear up" its engineering team before the start of requirements analysis. Contractors do not normally build their hardware engineering teams until after contract award. Government schedules, however, often assume detailed requirements analysis will begin on the first day of the contract. Since the first few months of a new contract are usually spent recruiting, hiring, and training an engineering team, the contractor often performs an inadequate analysis of requirements or slips the schedule. Experience shows that without a complete and thorough analysis, the contractor simply cannot produce a good design. This leads to additional schedule slips as the contractor must redesign, rework, and retest. This holds true for hardware and software, but is probably more applicable to hardware because of the size of the teams and the varying nature of hardware development. Government planners can provide the contractor with sufficient time to build up its engineering staff by giving notice of contract award with a contract effective date at least six weeks later. This makes contract kick-off meetings much more effective and allows full use of the time allotted to the critical analysis of requirements. There are two commercial standards that define the requirements of a systems engineering process. They are: EIA Interim Standard 632, Systems Engineering IEEE Trial Standard 1220, Standard for Application and Management of the Systems Engineering Process Activity: Conduct System Requirements Review (SRR) D-3 Responsible Agent Product Approval Authority Tools and Aids Contractor conducts review Service Team specialists assess, evaluate, and comment Refined System Specification System, Segment Specification Interface Control Documents Service Team Description The System Requirements Review (SRR) forms the basis for determining (1) whether system requirements are consistent, achievable, and complete, and (2) whether the government and contractor have a clear and mutual understanding of them. While the contractor conducts this review, the government takes an active part by clearly defining expectations and standards before the review and by participating actively in the event. The review typically covers the System Specification, System / Segment Specification, and Interface Control Documents. The products of functional analysis, syntheses, and trade studies may also be reviewed. Activity: Oversee Design of System Architecture D-4 Responsible Agent Product Approval Authority Tools and Aids Contractor designs Service Team specialists oversee System Architecture Baseline Allocated Baseline Revisions to System Specification Revisions to System / Segment Specification Preliminary Software Requirements Specification Preliminary Interface Requirements Specification Preliminary Systems / Segment Design Document Requirements Traceability Matrix Update to Software Development Plan Service Team lead or designated specialist Description: The Service Team oversees and generally supports contractor activity to define, develop, and baseline the system architecture. The contractor partitions system requirements to software and hardware configuration items and evaluates alternative design approaches, leading to preliminary system / subsystem designs and the identification of system components. Each subsystem design is integrated into the total system and evaluated against program constraints of time and cost. The flow of data and the flow of control are also determined. Trade studies and system modeling may also be performed. The contractor develops a Requirements Traceability Matrix (RTM) that identifies which configuration item will achieve each requirement in the System Specification. Requirements are allocated in the System Architecture Baseline and Allocated Baseline. Functional analysis is a key aspect of system architecture design. Functional analysis defines and integrates a functional architecture to support the synthesis of solutions for people, products, hardware, software, and processes that achieve top-level requirements and minimize program risk. Functional analysis is conducted iteratively to define successively lower-level functions required to satisfy higher-level requirements. It turns big functions into smaller, simpler functions for which a tangible solution can be designed. The lowest level of this architecture yields a well-defined set of functions that must be performed by the components of the system to meet top-level requirements. This set of requirements is commonly referred to as the allocated baseline. If an open architecture has been chosen, point your browser to http://www.itl.nist.gov/div897/pubs/index.htm and see Special Publication 500-187, Application Portability Profile (APP). The U.S. Government's Open System Environment Profile, OSE/1, Version 1.0. is based on an open system environment defined by non-proprietary specifications. Components may be added or deleted as technology changes and as Federal requirements change. Activity: Conduct System Design Review D-5 Responsible Agent Product Approval Authority Tools and Aids Contractor conducts SDR Service Team specialists review contractor design documents Comments on documents Appropriate Service Team specialist Description: The contractor conducts the System Design Review (SDR) with the Service Team reviewing and evaluating the status and maturity of system design. This activity is intended to confirm that (1) system requirements can be met, and (2) the contractor has a sound top-level design with system requirements allocated to appropriate configuration items. The following should be complete prior to the System Design Review: All subsystem, functional, and interim system reviews with unresolved issues documented; Definitions of functional and performance requirements for system development, manufacturing, verification, deployment, operations, support, training, and disposal; System trade studies, as well as trade studies supporting the preparation of draft configuration item development specifications; System architecture to the specified level; Draft configuration item architecture to the specified level; Draft configuration item development specifications for both hardware and software to the desired level below the system specification. The following design documents are typically reviewed during the SDR: System / Segment Specification; Preliminary Software Requirements Specification; Preliminary Interface Requirement Specification; System / Segment Design Document; and Requirements Traceability Matrix. Activity: Oversee Software Requirements Analysis D-6 Responsible Agent Product Approval Authority Tools and Aids Contractor develops Service Team specialists and users evaluate Final System / Segment Specification Final Software Requirements Specification Initial CSCI Preliminary Design Final Interface Requirements Specification Updated System / Segment Design Document Updated Requirements Traceability Matrix Data from Feasibility Prototyping (if used) Data from Modeling and Simulation (if used) Responsible Service Team specialist Description: The Service Team oversees, tracks, and generally supports the contractor’s analysis of software requirements. This phase of software development converts system-level requirements allocated to software in the System / Segment Specification to statements of requirements that are complete, consistent, testable, and feasible for software implementation. As part of this process, the contractor develops the overall software architecture, identifies principal CSCIs / Computer Software Components (CSCs), and allocates requirements to them using the Requirements Traceability Matrix database. Results are documented in the Software Requirements Specification. This process also updates interface requirements and performance information. Risk management and fault prevention are extremely important at this point in the software development process. Errors discovered and corrected here are much less costly to correct than errors discovered during implementation or maintenance. Feasibility prototyping and modeling / simulation are the most common methods of risk mitigation. Feasibility prototyping may consist of conceptual prototyping or demonstration prototyping. Conceptual prototyping provides a tangible representation of the concept of operation and human / machine interface that can be reviewed critically by the customer or user. This class of prototyping often uses rapid prototyping techniques on non-target hardware, constraining the display and menu formats and medium (i.e., graphics, color, fonts, etc.) to those supported on the target machines. Demonstration prototyping seeks to ensure that at least one solution exists for a stated requirement. Demonstration prototyping is accomplished on the target equipment, and often demonstrates only those parts of the target environment that are impacted by the specific requirement being demonstrated. For instance, a demonstration prototype may show a solution on a computational server without simulating the entire network. Simulation and requirements modeling are used to demonstrate feasibility in those cases where mathematical or other techniques exist that provide insight into the question at hand, or for those questions where prototyping of a solution may be too expensive or time-consuming. Requirements modeling requires an evaluation plan that documents the proposed techniques to be used, type and amount of data to be collected, algorithms to be used, characteristics of the system to be included, and schedule to be followed. Activity: Oversee Hardware Requirements Analysis D-7 Responsible Agent Product Approval Authority Tools and Aids Contractor performs Service Team specialists and users evaluate Final System / Segment Specification Final Hardware Development Specifications Final Interface Requirements Specification Updated System / Segment Design Document Updated Requirements Traceability Matrix Data from Feasibility Prototyping (if used) Data from Modeling and Simulation (if used) Responsible Service Team specialist Description: The Service Team oversees, tracks, and generally supports contractor analysis of hardware requirements. This activity converts system-level requirements allocated to hardware in the System / Segment Specification to statements of requirements that are complete, consistent, testable, and feasible for hardware design and development. As part of this process, the contractor develops the overall hardware architecture, identifies principal hardware configuration items, and allocates resources to them using the Requirements Traceability Matrix database. Results are documented in hardware development specifications. This process also updates interface requirements and performance information. Requirements modeling and simulation are often used to demonstrate feasibility in those cases where prototyping may be too expensive or time-consuming. Requirements modeling requires an evaluation plan that documents the techniques and algorithms to be used, type and amount of data to be collected, characteristics of the system to be included, and schedule to be followed. Risk management and fault-prevention are extremely important at this point in the hardware development process. Errors committed here are typically the most expensive to correct. Activity: Conduct Software Specification Review D-8 Responsible Agent Product Approval Authority Tools and Aids Contractor hosts the review Service Team specialists review and comment Baseline Software Requirements Specification Allocated Baseline Service Team software engineer Description: The contractor conducts a formal review of the Software Requirements Specification (SRS) using a process similar to that outlined in MIL-STD-1521B. The intent is to demonstrate that all segment and interface requirements are allocated and traced to Computer Software Configuration Items, and that the methods of verifying and validating requirements are reflected in the SRS. The Service Team reviews the allocation of performance requirements to major architectural components, as well as external and internal interface requirements. Additionally, the Service Team evaluates the impact of any proposed changes to the System Requirements Specification. The Air Force Acquisition Model (AFAM) is a good tool to use when determining the requirements for all Systems Engineering Reviews, particularly for software. It is available on CD ROM and includes "Best Practices" and "Lessons Learned". Activity: Conduct Hardware Specification Review D-9 Responsible Agent Product Approval Authority Tools and Aids Contractor conducts review Service Team specialists participate and resolve problems Baseline Hardware Development Specification Description: The contractor and Service Team jointly review the Hardware Requirements Specification to determine (1) whether appropriate segment and interface requirements are allocated and traced to Hardware Configuration Items (HWCIs), and (2) whether the methods for verifying and validating requirements are reflected in appropriate specifications. This review must ensure all validated requirements are satisfied by some element of the system and all interfaces are defined and traced. Any discrepancies or conflicts must be corrected before proceeding further in development. If problems emerge, it may become necessary to change the System Specification. Activity: Oversee Software Preliminary Design D-10 Responsible Agent Product Approval Authority Tools and Aids Service Team software engineer Software Design Document Interface Design Document Preliminary Software Test Plan Updated Requirements Traceability Matrix Design prototyping data Operational prototyping data Software Development Folder(s) Description: The Service Team oversees, tracks, and generally supports the preliminary design effort during which the contractor partitions Computer Software Configuration Items (CSCIs) into Computer Software Components (CSCs) and Computer Software Units (CSUs), and allocates requirements to them. The contractor also: Updates the Requirements Traceability Matrix to reflect the allocation of software requirements to each CSC or CSU; Generates preliminary software acceptance test descriptions and procedure; and Develops a preliminary Software Test Plan. As development progresses, the contractor finalizes the top-level software architecture and places products under software configuration management. The contractor may perform some design prototyping to assess all or parts of the CSCI design (e.g., interfaces with new hardware or new operating services). Because these prototypes demonstrate a solution, they often provide the bulk (if not all) of code delivered with the product. As such, prototyping can complete the design and accomplish some developmental testing while still formally being part of the design effort. The contractor assumes the risk of non-acceptance of code by the customer, and mitigates that risk by conducting reviews that match the reviews conducted on more classically developed software. The contractor may perform some operational prototyping during the design phase to meet high-priority user requirements or to demonstrate project-wide capabilities. Selecting a component for operational prototyping depends on the risk associated with remaining system design. Operational prototyping is especially recommended for: Computer-human interfaces; Critical operational considerations that support specific, narrowly defined user needs; Software augmentations to operating system services, data management, or network functions; Software back planes required to support multiple builds/releases; Libraries needed early in the development cycle; and Interfacing code to existing external systems to allow continued operation during switch-over. Operational prototypes are expected to provide fully operational code. They are totally designed, implemented, and tested while the actual design of the overall product is underway. As with design assessment prototyping, the contractor mitigates risk by conducting reviews at points within the prototype development that match more classically developed software. Activity: Oversee Hardware Preliminary Design D-11 Responsible Agent Product Approval Authority Tools and Aids Contractor develops hardware design Service Team specialists oversee and monitor Physical architecture Fully defined hardware configuration items Hardware design drawings and data sets Preliminary hardware Hardware test plans Interface Design Documents Service Team leader or engineering specialists Description: The Service Team monitors, tracks, and generally supports the hardware preliminary design effort, during which the contractor defines the system’s physical architecture and partitions Hardware Configuration Items (HWCIs) into hardware components. A configuration item is an aggregation of hardware, firmware, or computer software, which satisfies an end-use function and is designated by the Government for separate configuration management. Configuration items may vary widely in complexity, size, and type, from an aircraft or electronic system to a test meter. Any item required for logistic support and designated for separate procurement is a configuration item. Preliminary design translates functional and performance requirements, including interfaces, into a description of a complete system that satisfies the requirements. Preliminary hardware design defines the solution in terms of a physical architecture of people, hardware, and processes. System hardware solutions are iteratively defined through the preliminary and detailed design of the product and production processes. This activity develops the design in accordance with the system architecture. Results are defined and documented in the form of drawings and data sets. Activities of the Service Team during preliminary hardware design focus on ensuring the contractor has adequately: Defined a physical architecture that satisfies overall system-level requirements; Modeled the performance of both end-items and the integration of end items; Identified key performance design and safety requirements and key design requirements at each level of system or product indenture and translated them into design solutions; Identified key product characteristics and associated key production processes, and defined allowable design margins and capabilities for key production processes; Specified control requirements for product integrity during operation and support phases for key performance capabilities; Performed sensitivity analyses to establish design margins; Examined the effects of design requirement shortfalls and the tolerance to variations in use, producibility, supportability, and other determining factors; Conducted appropriate trade studies, prototypes, simulations, analysis, and design methodologies; Established and maintained a decision database that provides a traceable record of the results of analyses and trade studies that support key technical decisions; and Integrated design requirements for manufacturing (e.g., tooling data requirements) and support processes (e.g., diagnostics, maintenance requirements) with product design to facilitate ease of assembly. Reliable, maintainable, and available systems are achieved through a disciplined preliminary hardware design and engineering approach. In order to achieve user reliability, maintainability, and availability requirements, emphasis should be on: Understanding system readiness and mission performance requirements, physical environments (during use, maintenance, storage, transportation, etc.), resources (people, dollars, etc.) available to support the mission, and risks associated with these requirements; Managing the contributions to system reliability, maintainability, and availability that can be made by hardware, software, and human operators and maintainers; Preventing design deficiencies (including single-point failures), precluding the selection of unsuitable parts and materials, and minimizing the effects of variability in manufacturing and support processes; and Developing robust systems, insensitive to the environments to be experienced throughout the lifecycle and capable of being repaired under adverse or challenging conditions. Activity: Conduct Preliminary Design Review D-12 Responsible Agent Product Approval Authority Tools and Aids Contractor conducts Service Team specialists review and comment Formal review of contractor design approach Formal review of the physical architecture Formal comment on all design documents Verification that functional and performance requirements of each CI satisfy the functional baseline Completion of all CI / CSCI / HWCI development specifications Agreement that requirements for all CIs / CSCIs / HWCIs and the system are satisfied by the design approach Draft functional / performance interface ICDs Preliminary allocated baseline ready for start of detailed design for each CI / CSCI / HWCI Approval to start detailed design Approval of plans to CDR Service Team lead or designated specialist Description: The contractor presents the overall design approach and HWCI / CSCI structure and architecture to the Service Team at the Preliminary Design Review (PDR) using a process similar to that in MIL-STD-1521B. The PDR is intended to review formally the basic design approach for configuration items and to demonstrate the contractor has: Developed a satisfactory preliminary design for implementing segment requirements; Allocated and traced all software requirements to the CSC level; Allocated and traced all hardware requirements to the HWCI level; Identified all open issues and identified a plan for closing them; Identified all technical and programmatic high-risk areas; Developed a viable database design; Developed a complete and adequate plan for hardware, software and operations testing. During the PDR, the physical architecture and design is assessed to determine adequacy and completeness, and to determine the realism of proposed development functional requirements. Higher-level configuration items (integration and interface) are assessed to ensure they satisfy their portion of the functional baseline. Finally, the review confirms the integrated system meets functional baseline requirements and customer requirements. Examples of inputs to this extremely important review are: Results of all functional, subsystem, and interim reviews; System architecture updates; Preliminary CI / CSCI / HWCI architecture; Preliminary designs; Functional performance interface requirements; Design implementation trade studies; Make / buy decisions and documentation; and Compatibility between all CIs / CSCIs / HWCIs. Sometimes a series of PDRs is held, one for each configuration item or aggregate of configuration items, leading to a system PDR for completion. Each PDR must: Ensure the process used to arrive at functional and performance requirements for each CI is complete, including trades and allocations; Demonstrate a balanced and integrated approach; and Establish an audit trail from functional baseline to user requirements, substantiating changes as necessary. Activity: Oversee Software Detailed Design D-13 Responsible Agent Product Approval Authority Tools and Aids Contractor designs Service Team specialists oversee and support Preliminary Software Design Document Preliminary Interface Design Document Updated Software Test Plan Preliminary Software Test Description Updated Requirements Traceability Matrix Test Requirements Matrix Updated Software Development Folder(s) Service Team software specialist Description: The Service Team oversees, tracks, and generally supports the contractor’s detailed software design effort during which each Computer Software Component (CSC) is decomposed into a complete structure of lower-level CSCs and Computer Software Units (CSUs). Interfaces are described to the lowest component level, data structures and contents are defined, input and output details are designed, and decisions are made on handling errors. As design activities proceed, the contractor finalizes the Software Design Document and Interface Design Document, begins development on the Software Test Description, and updates the Requirements Traceability Matrix. Activity: Oversee Hardware Detailed Design D-14 Responsible Agent Product Approval Authority Tools and Aids Contractor develops detailed design Service Team specialists oversee and monitor Preliminary Hardware Design Document Updated Hardware Test Plan Preliminary Hardware Test Description Updated Requirements Traceability Matrix Hardware Test Requirements Matrix Service Team Leader or designated specialist Description: The Service Team oversees, tracks, and generally supports the contractor’s detailed hardware design effort, during which each hardware component is decomposed into a complete structure of lower-level units, and interfaces are described to the lowest component level. Virtual or synthetic prototyping is now in wide use throughout industry to create accurate, realistic, and low-cost digital representations of each part, component, or end-item product being designed. Powerful CAD / CAM programs are standard engineering design tools in most contractor facilities, even the smallest. It is now possible to create digital models of greater fidelity than a standard engineering mockup. This allows the contractor to create and rapidly evaluate numerous design iterations and optimize them for performance and producibility before "bending metal". The Service Team should ensure the expertise of experienced maintenance technicians and equipment operators is integrated into the preliminary and detailed design of the new system. Experienced maintenance technicians and equipment operators should be assigned to the contractor's facility, and should be an integral part of the contractor's development team during system and equipment full-scale development. During the detailed design phase, Service Team activity is intended to ensure the contractor adequately: Defines a physical architecture that satisfies overall system-level requirements; Models the performance of end-items and integrating these end-items; Identifies key performance design and safety requirements and key design requirements at each level of system or product indenture and translates them into design solutions; Identifies key product characteristics and associated key production processes, and defines design margins and capabilities for key production processes; Specifies control requirements for product integrity during operation and support phases to maintain the system or product operation within the user’s key performance capabilities; Performs sensitivity analyses to establish design margins and examine the effects of design requirement shortfalls, as well as the tolerance to variations in use, producibility, supportability, and other determining factors; Conducts appropriate trade studies, prototyping, simulations, analyses, and design methodologies; Establishes and maintains a decision database that provides a traceable record of the results of analyses, trade studies, etc., which support key technical decisions; Integrates design requirements for manufacturing (e.g., tooling datum requirements) and support processes (e.g., diagnostics, maintenance requirements) with product design, and facilitates ease of assembly through the use of geometric dimensioning. The Service Team also ensures the contractor: Provides resources necessary to integrate all technical disciplines and functional processes (e.g., manufacturing and logistics), and establishes effective communications with and among all participants; Identifies key product characteristics and is actively controlling design margins for the integrated / installed performance of system components; Establishes and accurately tracks internal and external software component margin allocation and budgeting; Identifies and manages technical risks; Identifies and actively manages critical interfaces; Has a methodology for preventing sub-optimal solutions by continually looking across all product teams; Provides quality interface control documents on a timely basis; and Appropriately applies the specialty functions (the "-ilities" – reliability, maintainability, etc.). Reliable, maintainable, and available systems are achieved through a disciplined detailed hardware design and engineering approach. In order to achieve user reliability, maintainability, and availability requirements, emphasis should be on: Understanding user readiness and mission performance requirements, physical environments (during use, maintenance, storage, transportation, etc.), resources (people, dollars, etc.) available to support the mission, and risks associated with translating these requirements into system requirements that can be implemented in design and verified; Managing the contributions to system reliability, maintainability, and availability made by hardware, software, and human elements of the system; Preventing design deficiencies (including single-point failures), precluding the selection of unsuitable parts and materials, and minimizing the effects of variability in the manufacturing and support processes; and Developing robust systems, insensitive to the environments experienced throughout the lifecycle and capable of being repaired under adverse or challenging conditions. Detailed hardware design should be based on established parts selection practices and guidelines. Past component history, physical and environmental stresses, and component criticality should be considered in the part selection process. The system should be designed such that it maintains minimum acceptable performance despite variations due to the manufacturing process, lifecycle environment, and component degradation or drift. Any items furnished by the Government or used off-the-shelf should be operationally suitable for their intended use and capable of meeting their allocated requirements. Activity: Conduct Critical Design Review D-15 Responsible Agent Product Approval Authority Tools and Aids Contractor conducts Service Team specialists review and comment Detailed HWCI / CSCI Design Documents Detailed HWCI / CSCI Interface Design Documents Preliminary Software Test Descriptions Draft HWCI / CSCI test procedures Updated Requirements Traceability Matrix Undated HWCI / CSCI development metrics Undated cost and schedule estimates Appropriate Service Team specialist Description: The Critical Design Review (CDR) for systems that contain developmental hardware and developmental software is often very complex. It must be well planned to address all design issues and review each component completely and thoroughly. The CDR is the last chance to affect system design before bending metal and developing software code. Changes must not be made without appreciation of the consequences, but if changes are necessary, making them here will be far less costly than after production begins. The contractor conducts the Critical Design Review using a process similar to that found in MIL-STD-1521B. The Service Team reviews and evaluates contractor activity and progress. The purpose is to review formally the design of each hardware and software configuration item and demonstrate that: All software requirements are allocated and traced to the CSU level; All hardware requirements are allocated and traced to HWCIs; Detailed designs reflect an architecture that satisfactorily minimizes risk; Database design is complete and meets all requirements; and A complete and adequate plan is in place for hardware, software, and operations testing. As part of this activity, the contractor should prototype each CSCI external interface and any CSCI internal interface to hardware. The contractor should also identify those requirements that have already been tested and for which test data is available (typically NDI / COTS components). A series of designs reviews are normally held, one for each configuration item or aggregation of configuration items in the specification tree. A system CDR is held after completion of all configuration item design reviews and aggregation of configuration item design reviews. This series of CDRs confirms that the detailed design satisfies requirements, as reflected in configuration item and system specifications. This includes verification of compatibility with higher-level and interfacing configuration items. The design must be confirmed to be comprehensive, addressing all products and processes. The reviews usually include confirmation from developmental test and evaluation that the design meets performance requirements. The overall method of risk mitigation and treatment of each risk issue is also evaluated. Inputs to the Critical Design Review include: System architecture updates; Update of the functional baseline; All configuration item architectures; Update of the allocated baseline; All Interface Control Drawings; All configuration item product / process specifications; and Preliminary product baseline. Activity: Make Product Demonstration Decision D-16 Responsible Agent Product Approval Authority Tools and Aids Service team leader provides information that demonstrates achievement of product integration decision criteria Product Demonstration Decision Memorandum Vice President (ATO) or Director (non-ATO) of the implementing service organization Discussion: The service team leader presents the results of product integration to the Vice President (ATO) or Director (non-ATO) of the implementing service organization. The Vice President or Director, as appropriate, reviews product knowledge to determine if the following decision criteria have been satisfied: Key product characteristics are defined; Stakeholders agree that product design and functionality satisfy customer requirements; System design reviews are complete; Engineering drawings are complete; Detailed software/firmware design is complete, including critical software processes and threads; RMA goals are defined and planning is complete; Failure modes and effects analysis is complete; and Critical manufacturing processes are identified If so, the decision authority issues a decision memorandum authorizing the investment program to proceed to initial manufacturing of first-article units for use in product demonstration. Findings are recorded in the decision memorandum along with any required actions. Activity: Oversee Software Coding and CSC Testing D-17 Responsible Agent Product Approval Authority Tools and Aids Contractor performs Service Team oversees, tracks, and supports CSU code Updated Software Development Folder(s), including CSU Test Procedures Updated RTM Test Requirements Matrix Test Development Folder(s), including Software Turnover Plan Service Team software specialist Description: The Service Team oversees, tracks, and generally supports contractor software CSU coding and testing. Coding and testing generally begins after completion of detailed design and a successful CDR, although some prototype code may have been produced during requirements analysis or preliminary design. Coding and CSU testing implements the design validated by the CDR. This activity produces a set of program units that completely implement the functional requirements specified in the Software Requirements Specification. Go to http://www.stsc.hill.af.mil/ and click on the subject "SW Testing" in "Technology Areas" for information on ATPS, a set of expert system-based tools designed to aid acquisition staffs in the oversight of test and evaluation. Activity: Oversee Hardware Fabrication and Assembly D-18 Responsible Agent Product Approval Authority Tools and Aids Contractor fabricates and assembles hardware Service Team Quality Reliability Officer enforces contract provisions and accepts qualified units Fabricated hardware units Quality Reliability Officer or designated official Description: The contractor fabricates and assembles the hardware components of the system. The Service Team ensures hardware components are fabricated in accordance with provisions of the contract, and accepts delivery of hardware units upon completion of all testing and quality checks. Hardware fabrication and assembly includes the total set of activities necessary to convert product definition into an affordable, producible end-item product. The Service Team should ensure the hardware contractor provides: A complete definition of the factory environment in which the product is to be produced; A capable, efficient factory design as a result of the detailed design phase; Development and production items fabricated in support of delivery requirements; and Adequate insight into how production facilities are performing during contract execution. Manufacturing management processes should inform the Service Team as to how the product is being built and what actions may be necessary to reduce risk. Unit production cost and earned-value analysis are very useful for providing insight into whether fabrication and assembly are proceeding according to plan. The manufacturing process should support the systems engineering process by integrating the design of the product and production facility. If production costs are to be controlled, there must be up-front planning toward that end. There must also be a continuous interchange between product design activities and fabrication facility design activities. In other words, the capabilities of the fabrication facility must be considered in product design and vice versa. To determine the impact of the facility on production cost, such factors as process capacity and capability, environmental concerns, standard work content, factory flow, and assembly methods must be evaluated. The contractor may use factory modeling to validate the compatibility of product design and factory capability in terms of cost, schedule, and quality. Activity: Conduct Software Integration Test Review D-19 Responsible Agent Product Approval Authority Tools and Aids Contractor conducts review Service Team reviews and evaluates contractor readiness to integrate and test Comments on code quality Permission to proceed to integration testing Service Team software specialist Description: The contractor conducts the CSC / CSCI Integration Test Review (ITR) at the completion of CSC testing and before release of code for integration. The Service Team evaluates the quality of CSC code and reviews contractor readiness to enter integration testing. This review examines: Correctness of code interactions as specified in Interface Control Documents and Design Interface Agreements; Completeness and consistency of CSC test results with the predicted output; Correctness of data transformation within the code; Ability of code to meet timing, resource, or performance restrictions; and Ability of code to deal with error conditions, out-of-tolerance processing conditions, and out-of-limit data values. Following the Integration Test Review, software is presented to the integration test organization for review, evaluation, and eventual turnover. Upon acceptance, CSCI code and supporting test data is placed under formal configuration control, and the change authority is transferred from the developing organization to the project change control board. Activity: Oversee CSC / CSCI Integration & Testing D-20 Responsible Agent Product Approval Authority Tools and Aids Contractor performs Service Team oversees, tracks, and supports Integrated software baseline Updated Test Development Folder(s), including integration test results Updated Software Development Folder(s) Service Team software specialist Description: The Service Team oversees, tracks, and generally supports contractor CSC / CSCI integration and testing. CSC / CSCI integration testing assembles partitioned CSU components into the respective CSC, and those CSCs into the whole CSCI that represents part or all of the product under development. The integration of multiple CSUs into the parent CSC is an iterative process of accepting CSUs from unit test, testing them together, correcting any deficiencies, and repeating the process with the next CSU. This continues until all CSUs have been integrated into the parent CSC. Likewise, CSCs are then integrated and tested sequentially to form the CSCI. After completion of CSC / CSCI integration testing, software is turned over for CSCI integration and testing. Activity: Oversee CSCI Integration & Testing D-21 Responsible Agent Product Approval Authority Tools and Aids Contractor performs integration and testing Service Team oversees, tracks, and supports Final Software Design Document Final System Test Procedures Integrated software baseline (tested) Service Team software specialist Description: The Service Team oversees, tracks, and generally supports CSCI integration and testing by the contractor. Also known as software build / release testing, CSCI integration and testing identifies and corrects software problems through the execution of system test procedures before the start of Formal Qualification Testing. During this activity, the contractor: Executes system test procedures to verify that baselined software meets system requirements; Executes an endurance test to monitor system performance under sustained loading; Resolves any problems encountered during testing; Freezes the software; and Conducts a dry run of all system test procedures prior to the Test Readiness Review. Activity: Oversee Hardware Configuration Item Integration & Testing D-22 Responsible Agent Product Approval Authority Tools and Aids Contractor integrates and tests Service Team oversees Integrated and tested hardware units Quality Reliability Officer or designated official Description: The contractor tests each Hardware Configuration Item (HWCI) to confirm that each satisfies System Specification requirements allocated by the Requirements Traceability Matrix. In a similar manner as with CSCI integration and testing, the contractor sequentially links and tests hardware configuration items. When HWCI interfaces are provided by software, the integration and testing of HWCIs occurs during System Integration and Testing. During HWCI integration and test, the Service Team tracks and evaluates contractor activities to ensure it: Provides tools, databases, and development practices for the integration and test of hardware configuration items; Conducts incremental developmental analyses, simulations, and / or tests to develop needed design data and verify design requirements and producibility; Performs final qualification / performance verification that represents usage and environments expected over the life of the hardware component; Identifies test objectives and other critical information required to plan and execute testing; Predicts test requirements in terms of schedule and resources; Acquires and manages test resources, conducts required testing in a timely and effective fashion, and interfaces with manufacturing processes to ensure timely availability of test articles; Reports results accurately and establishes and maintains a verification database that provides a traceable record of performance verification; and Assesses the adequacy of verification for proposed COTS and NDI hardware, identifies additional verification requirements if needed, and integrates existing verification data into the overall system verification database. Point your browser at http://www.deskbook.osd.mil/, Defense Acquisition Deskbook, Section 1.4.3, "Test and Evaluation Products and Services: for a look at how DOD conducts integration, test, and evaluation. You can also find references to resources that are available to other government program managers for this essential process. Activity: Oversee System Integration & Testing D-23 Responsible Agent Product Approval Authority Tools and Aids Contractor performs integration and testing Service Team oversees, tracks, and supports Updated Software Development Folders Service Team lead or software specialist if designated Description: The Service Team oversees, tracks, and generally supports system integration and testing by the contractor. This activity integrates CSCIs with interfacing HWCIs and CSCIs, tests the groupings to determine whether they work together as intended, and continues the process until all CSCIs and HWCIs are integrated and tested as an end-to-end system. Software-related information such as analysis and test results is recorded in appropriate Software Development Folders. The keys to a successful HW / SW system integration and test program are: Early identification of test requirements; Formation of an integration and test team; Standardization of terminology; and Formal traceability of requirements. Test-unique requirements may include modifications to the system for test support. The cost to incorporate test-unique data ports and sensors during design is usually insignificant. Modifying systems after they are built is always more expensive, and in some cases may be out of scope of the contract. Significant lead times may be required to provide test resources such as aircraft, ground-based radar site modifications, special instrumentation, or data reduction / analysis software. Point your browser at: http://www.deskbook.osd.mil/, Defense Acquisition Deskbook, Section 1.4.3, "Test and Evaluation Products and Services" for a look at how the DOD conducts integration, test, and evaluation. You can also find references to the resources that are available to other government program managers for this essential process. The integration and test team should be involved in the development program during the earliest stages. Early involvement saves time, money, and resources. The Service Team may wish to establish a test planning working group (TPWG) with members representing the user, contractor, and participating test organizations. Having the first TPWG meeting during the contract proposal review is not too early. Early involvement ensures test-unique requirements are addressed and long-lead test resources are acquired. A TPWG should: Support the Service Team in developing and maintaining the test section of the Implementation Strategy and Planning attachment to the Exhibit 300 Program Baseline; Participate in setting test objectives, MOUs, and evaluation baselines; Define organizational responsibilities and relationships for testing; Help estimate integration and T&E costs; Develop a realistic integration and T&E schedule; Determine required test resources; Review and help prepare the test portions of SIRs and related contractual documents; Help evaluate contractor proposals for integration or test support; Set the scope and objectives of the integration and testing effort; Coordinate resource availability, including necessary facility upgrades and personnel requirements; Form subgroups such as a Computer Resources Working Group to address software T&E requirements; and Participate in the test readiness review. Activity: Conduct Test Readiness Review D-24 Responsible Agent Product Approval Authority Tools and Aids Contractor conducts review Service Team evaluates results and determines system readiness for FQT Final System Test Procedures Agreement to proceed with Formal Qualification Testing Service Team test specialist Description: The contractor conducts a System Test Readiness Review (TRR) using a process similar to that in MIL-STD-1521B to provide the Service Team with documented proof that all requirements necessary to start Formal Qualification Testing (FQT) have been met. The review is conducted at the software unit and component level to evaluate the completeness of test procedures, and to ensure the contractor is ready for formal testing. Test procedures are evaluated for compliance with the contractor Master Test Plan or similar document. Test plan descriptions are evaluated for adequacy in accomplishing test requirements. Preliminary testing is reviewed to compare results against baseline, and to ensure necessary coding changes have been accomplished. Informal testing and any updates to operational and support documents are also reviewed. At a minimum, the Service Team evaluates the following types of data and information to assess the readiness of the developed system for FQT: Results obtained from the dry-run of system test procedures; Results of lower-level hardware and software tests; Outstanding Program Trouble Reports and waivers, along with assessment of impact upon test readiness; and Formal recommendations by the quality assurance organization. Activity: Witness Design Qualification Test D-25 Responsible Agent Product Approval Authority Tools and Aids Contractor conducts DQT Service Team witnesses DQT and accepts system on completion Program Trouble Reports (resolved) Software Test Report Updated Software Development Folder(s) Fully qualified system Service Team Quality Reliability Officer or designated official Description: The Service Team and quality assurance representatives witness the Design Qualification Test (DQT) conducted by the contractor. The DQT demonstrates the system’s ability to satisfy all requirements of the System / Segment Specification and Interface Requirements Specification. This testing involves fully integrated CSCIs and HWCIs, with the CSCIs installed on the approved hardware configuration. The contractor executes all test scripts from approved system test procedures, and evaluates results against the acceptance criteria included in test documentation. All Program Trouble Reports opened during DQT must be resolved before the conclusion of testing. Successful completion of the DQT marks the end of developmental testing and transfer of ownership of the system to the FAA. Activity: Conduct Production Acceptance Test Each Unit D-26 Responsible Agent Product Approval Authority Tools and Aids Contractor conducts testing Service Team monitors Accepted production units Quality Reliability Officer or designated official Description: The contractor tests each production unit using test procedures approved by the FAA to verify the assembly line is producing units with the same quality and performance as the first article. The Quality Reliability Officer (QRO) monitors production acceptance testing, and is the approving official for successful compliance with test procedures and test criteria.